## Main
cell_index | question_index | question_text | opt_1 | opt_2 | opt_3 | opt_4 | 1nswer | mod | parent | sub | id
4 | 421 | What does monitoring and controlling involve? | Ensuring the project is ahead of schedule | Collecting, measuring, and assessing data and trends | Setting project performance objectives | Creating a project management plan | 2 | 5A | 2 | a | 5A-2a
4 | 422 | Which tool or technique is used for analysing project performance using cost and schedule data? | Stakeholder Analysis | Decision-Making | Earned Value Analysis | Alternatives Analysis | 3 | 5A | 2 | a | 5A-2a
4 | 423 | What is the purpose of a progress report in project management? | To provide a summary of completed project work | To forecast future project status based on past information | To describe the project's objectives | To analyse project risks | 1 | 5A | 2 | a | 5A-2a
4 | 424 | What is the significance of milestone monitoring in project management? | It helps in completing the project ahead of schedule. | It serves as a checkpoint for tracking progress. | It replaces the need for progress reports. | It is optional and not necessary for project success. | 2 | 5A | 2 | a | 5A-2a
4 | 425 | What information is typically described in the resource allocation section of a progress report? | Work completed and resources to be used in the next period | Capture the possible recruitment avenues for labour and suppliers | Detail the cost of different resources used | Highlight any resource constraints, surpluses, or changes in resource requirements | 4 | 5A | 2 | a | 5A-2a
4 | 426 | What is the purpose of a forecast report? | Record past project status and progress based on past information and trends | Describe where the project stands at a specific point in time | Describe what the project team has accomplished during a certain period | None of the options | 4 | 5A | 2 | a | 5A-2a
4 | 427 | You are working on a project and discover that one of the business users responsible for testing the product never completed the testing. She has written an email requesting that one of your team members drop everything to assist her with a problem that could have been avoided if she had performed the test. This employee reports to a stakeholder, not to the project team. You estimate that the project might not be completed on time due to this missed activity. Which of the following actions should you take? | You should recommend corrective action to bring the expected future project performance back into line with the project management plan because this employee failed to perform this activity. | You should recommend preventive action to reduce the possibility of future project performance veering off track because of this employee’s failure to perform this activity. | You should recommend a change request, which is an output of the Monitor and Control Project Work process, to get the project performance back in alignment with the project management plan. | You need to develop a risk response plan to deal with the impacts of this incomplete task. | 3 | 5A | 2 | a | 5A-2a
4 | 428 | You are performing the following activities: comparing actual performance against the project plan, assessing performance to determine if corrective action is necessary, identifying new risks, providing forecasts to update current cost and schedule data, and monitoring the implementation of approved changes. Which process are you in? | Perform Integrated Change Control | Monitor Communications | Monitor and Control Project Work | Monitor Stakeholder Engagement | 3 | 5A | 2 | a | 5A-2a
11 | 429 | Which formula is used to calculate the Cost Variance (CV)? | CV = AC – EV | CV = PV – EV | CV = EV – PV | CV = EV – AC | 4 | 5A | 2 | b | 5A-2b
11 | 430 | Which formula is used to calculate the Cost Performance Index (CPI)? | CPI = EV / AC | CPI = AC / EV | CPI = EV / PV | CPI = PV / EV | 1 | 5A | 2 | b | 5A-2b
11 | 431 | Which formula is used to calculate the Estimate at Completion (EAC) if the current cost performance index (CPI) or per cent complete (%C) is assumed to remain constant for the remaining portion of the project? | EAC = BAC / CPI | EAC = AC + (BAC − EV)/(CPI x SPI) | EAC = AC + BAC - EV | EAC = AC + Bottom-up ETC | 1 | 5A | 2 | b | 5A-2b
11 | 432 | Which of the following statements correctly describes the relationship between the Cost Performance Index (CPI) and the To-Complete Performance Index (TCPI)? | If CPI > 1, the project is under budget, and TCPI must be less than 1 to complete within the original budget (BAC). | If CPI < 1, the project is over budget, and TCPI must be less than 1 to complete within the original budget (BAC). | If CPI = 1, the project is on budget, and TCPI must be greater than 1 to complete within the original budget (BAC). | If CPI < 1, the project is over budget, and TCPI must be greater than 1 to complete within the original budget (BAC). | 1 | 5A | 2 | b | 5A-2b
11 | 433 | What does a Cost Performance Index (CPI) of 0.833 indicate? | The project is performing better than expected in terms of cost | The project is performing worse than expected in terms of cost | The project is on budget | The project is on schedule | 2 | 5A | 2 | b | 5A-2b
11 | 434 | You are managing a construction project with a budget of $800,000. The project involves two construction teams working for six months, totalling 10,000 hours of labour. According to your project schedule, 38% of the work should be completed by now. However, you've noted that 40% of the work is complete, but 50% of the budget has already been spent. What does this indicate about your project's status? | The project is ahead of schedule and under budget. | The project is ahead of schedule but over budget. | The project is behind schedule but under budget. | The project is on schedule but over budget. | 2 | 5A | 2 | b | 5A-2b
11 | 435 | Nine months into a two-year infrastructure upgrading project with a $4,200,000 budget, you have spent $1,650,000. The project's Cost Performance Index (CPI) is 0.875. Calculate the project's Estimate to Complete (ETC) based on this information. Assume future work is completed at the planned efficiency rate. | 2756250 | 3150000 | 4406250 | 3550000 | 1 | 5A | 2 | b | 5A-2b
11 | 436 | As a contracted project manager, you have been assigned a project with a budget of $1.5 million. The project is scheduled to last seven months, but your most recent earned value management (EVM) report shows that the project will finish ahead of schedule by nearly six weeks. If this happens, you will lose $175,000 in billable time. What should you do? | Bill for the entire $1.5 million since this was the approved budget. | Bill for the $1.5 million by adding work at the end of the project. | Report to the customer the project status and completion date. | Report the project status and completion date to the customer and ask if the customer would like to add any features to account for the money not spent. | 3 | 5A | 2 | b | 5A-2b
11 | 437 | Assume that you are the project manager for the construction of a 15-km road. Further, assume that the work is uniformly distributed over 12 weeks. The total approved budget for this project is $600,000. At the end of the first three weeks of work, $160,000 was spent, and five km of road were completed. What is the project's earned value at the end of the first three weeks? | 160000 | 200000 | 150000 | 600000 | 2 | 5A | 2 | b | 5A-2b
11 | 438 | Assume that you are the project manager for the construction of a 15-km road. Further, assume that the work is uniformly distributed over 12 weeks. The total approved budget for this project is $600,000. At the end of the first three weeks of work, $160,000 was spent, and five km of road were completed. What is the planned value of the project at this point in time? | 160000 | 200000 | 150000 | 600000 | 3 | 5A | 2 | b | 5A-2b
11 | 439 | Assume that you are the project manager for the construction of a 15-km road. Further, assume that the work is uniformly distributed over 12 weeks. The total approved budget for this project is $600,000. At the end of the first three weeks of work, $160,000 was spent, and five km of road were completed. What is the schedule variance? | 40000 | 50000 | Three weeks | Twelve weeks | 2 | 5A | 2 | b | 5A-2b
11 | 440 | Which performance measurement tells you what the projected total cost of the project will be at completion? | ETC | EV | AC | EAC | 4 | 5A | 2 | b | 5A-2b
11 | 441 | Which performance measurement tells you the cost of the work that has been authorised and budgeted for a WBS component? | PV | EV | AC | EVM | 1 | 5A | 2 | b | 5A-2b
11 | 442 | As the project manager, you review your team's earned value analysis report. The SPI is 0.87. What does this figure mean to you? | Your project is running according to the budget. | The project is getting 87 cents out of each dollar spent. | You are ahead of schedule. | Your project's progress is only 87% of what was planned, so you are behind schedule. | 4 | 5A | 2 | b | 5A-2b
11 | 443 | This measurement is the value of the work that has been completed to date compared to the budget. | PV | AC | EV | EAC | 3 | 5A | 2 | b | 5A-2b
11 | 444 | You are a contract project manager for a wholesale flower distribution company. Your project is to develop a website for the company that allows retailers to place their flower orders online. You will also provide a separate link for individual purchases that are ordered, packaged, and mailed to the consumer directly from the grower’s site. This project involves coordinating the parent company, growers, and distributors. You are preparing a performance review and have the following measurements at hand: PV = 300, AC = 200, and EV = 250. What do you know about this project? | The EAC is a positive number, which means the project will finish under budget. | You do not have enough information to calculate CPI. | The CV is a negative number in this case, which means you’ve spent less than you planned to spend as of the measurement date. | The CV is a positive number in this case, which means you’re under budget as of the measurement date. | 4 | 5A | 2 | b | 5A-2b
11 | 445 | Which of the following does a negative result from an SV calculation mean? | PV is higher than EV. | PV equals 1. | EV is higher than PV. | EV is higher than AC. | 1 | 5A | 2 | b | 5A-2b
11 | 446 | You are a contract project manager for a wholesale flower distribution company. Your project is to develop a website for the company that allows retailers to place their flower orders online. You will also provide a separate link for individual purchases that are ordered, packaged, and mailed to the consumer directly from the grower’s site. This project involves coordinating the parent company, growers, and distributors. You are preparing a performance review and have the following measurements at hand: PV = 300, AC = 200, and EV = 250. What is the CPI of this project? | 0.8 | 1.25 | 1.5 | 0.83 | 2 | 5A | 2 | b | 5A-2b
11 | 447 | You have accepted project performance to date and assume future work (ETC) will be performed at the planned efficiency rate. If BAC = 800, ETC = 275, PV = 300, AC = 200, EV = 250, and CPI = 1.25, what is the EAC? | 640 | 750 | 600 | 550 | 2 | 5A | 2 | b | 5A-2b
11 | 448 | You know that EAC = 375, PV = 300, AC = 200, and EV = 250. You expect the work of the project to continue as planned. What is the ETC? | 300 | 125 | 175 | 50 | 3 | 5A | 2 | b | 5A-2b
11 | 449 | You expect future project performance to be consistent with the project performance experienced to date for this work component. If BAC = 800, ETC = 275, PV = 300, AC = 200, EV = 250, and CPI = 1.25, what is the EAC? | 640 | 750 | 600 | 550 | 1 | 5A | 2 | b | 5A-2b
11 | 450 | Given that Variance at Completion (VAC) = BAC – EAC. You know that BAC = 500, PV = 325, AC = 275, CPI = 0.9, and EV = 250, and you are using actual costs to date and assuming EAC uses the planned efficiency rate. What is the VAC? | 25 | -52 | 52 | -25 | 4 | 5A | 2 | b | 5A-2b
11 | 451 | You know that BAC = 2500, PV = 1250, AC = 1275, EV = 1150, and assume CPI is constant for the remainder of the project. What is ETC? | 1467 | 2625 | 1503 | 2778 | 3 | 5A | 2 | b | 5A-2b
11 | 452 | According to the latest update of the project schedule, you realise that the project will be completed one month after the desired completion date. You have extra resources on hand, and the activity dependencies are preferential (i.e. dependencies are not rigid). The project is not of high risk, and the SPI up to now is 0.89. Under these circumstances, what would be your best course of action as a project manager? | Make more activities concurrent | Leveling the resources | Shift some of the resources from the preferential dependencies to the external ones | Eliminate some of the activities which are of lower importance | 1 | 5A | 2 | b | 5A-2b
11 | 453 | As a construction project manager, you are reviewing an earned value analysis report, which includes only the variance information. The schedule variance is $320,000, and the cost variance is $100,000. Your guess is that the planned value of the project at this point should be $2,000,000. It is after normal office hours, and you don’t have access to the analyst who prepared the report, though you see that the report shows an SPI of 1.16 and a CPI of 1.05. What does this information tell you about the project? | Your project is ahead of schedule and under budget. | Your project is behind schedule and under budget. | Your project is ahead of schedule and over budget. | Your project is behind schedule and over budget. | 1 | 5A | 2 | b | 5A-2b
7 | 468 | What is one of the primary purposes of the Control Scope process in project management? | Defining project objectives | Monitoring project progress | Managing changes to the scope baseline | Capturing lessons learned | 3 | 5A | 5 |  | 5A-5
7 | 469 | Which of the following is crucial for effective scope control? | A detailed project management plan | A comprehensive configuration management plan | A well-defined scope | A well-defined project schedule | 3 | 5A | 5 |  | 5A-5
7 | 470 | In project management, which of the following processes works synergistically with the Control Scope process to maintain alignment between the project's evolving scope and its overarching plan? | Perform Integrated Change Control | Perform Quality Control | Monitor and Control Project Work | Validate Scope | 1 | 5A | 5 |  | 5A-5
7 | 471 | Which of the following options identifies the key factors to consider when evaluating the impact of proposed changes? | Stakeholder satisfaction and risk | Budget, resources, and project objectives | Project complexity and available resources | Project timeline and scope | 2 | 5A | 5 |  | 5A-5
7 | 472 | What risks are directly associated with scope creep? | Extended timelines, reduced work, and improved quality | Increased project complexity, lower stakeholder satisfaction | Additional work, increased costs, and extended timelines | Lower quality, increased costs, and improved stakeholder satisfaction | 3 | 5A | 5 |  | 5A-5
7 | 473 | What is essential to prevent scope creep? | Quick response to the additional scope | Proactive and disciplined approach | Ignoring power dynamics between clients and the project team | Flexible communications with stakeholders | 2 | 5A | 5 |  | 5A-5
7 | 474 | You are working on a project that was proceeding well until a manufacturing glitch occurred that requires corrective action. It turns out the glitch was an unintentional enhancement to the product, and the marketing people are absolutely crazy about its potential. The corrective action is cancelled, and you continue to produce the product with the newly discovered enhancement. As the project manager, you know that a change has occurred to the product scope because the glitch changed the product's characteristics. Which of the following statements is true? | Changes to product scope should be reflected in the project scope. | Changes to product scope should be documented in the scope management plan. | Changes to product scope will result in cost changes. | Changes to product scope are a result of corrective action. | 1 | 5A | 5 |  | 5A-5
9 | 475 | What is the purpose of the iteration burndown chart? | Monitoring resource utilisation | Tracking progress and identifying risks in an iteration | Analysing project costs | Evaluating stakeholder satisfaction | 2 | 5A | 6 |  | 5A-6
9 | 476 | In controlling contractors' and suppliers' schedules, what is an effective way to monitor work progress? | Ensuring the accuracy of work performance data | Monitoring milestone status | Evaluating project costs | Reviewing project risks | 2 | 5A | 6 |  | 5A-6
9 | 477 | Which process ensures that any schedule baseline amendments are carefully managed? | Perform Integrated Change Control | Control Schedule | Develop Schedule | Monitor and Control Project Work | 1 | 5A | 6 |  | 5A-6
9 | 478 | When should schedule status reviews and walkthroughs be conducted in controlling contractors' schedules? | At irregular intervals | After project completion | As needed based on contractor requests | Regularly and at milestone points | 4 | 5A | 6 |  | 5A-6
9 | 479 | From a schedule control point of view, what are the purposes of having scheduled walk-throughs? | Ensuring quality of work | Ensure the reported progress is correct | Check that scope requirements are met | Check that the progress on site is ahead of schedule | 2 | 5A | 6 |  | 5A-6
9 | 480 | What are the performance measurements for the Control Schedule process? | SV = (EV – PV) and SPI = (EV / PV) | SV = (EV – AC) and SPI = (EV / AC) | SV = (EV – BAC) and SPI = (EV / BAC) | SV = (PV – EV) and SPI = (PV / EV) | 1 | 5A | 6 |  | 5A-6
9 | 481 | Why should you monitor the activities on the critical path more closely? | Because each activity on the critical path has zero float time and thereby poses a schedule risk | Because the activities on the critical path need to be performed before the activities on other paths are performed | Because the activities on the critical path are critical to the organisation’s strategy | Because the activities on noncritical paths depend upon the activities on the critical path | 1 | 5A | 6 |  | 5A-6
9 | 482 | You are a junior project manager currently performing schedule-controlling activities. You approach one of your experienced colleagues for advice on how to reanalyse the project and predict the project’s remaining duration. She tells you to analyse the activity sequence with the least scheduling flexibility. Which technique is she referring to? | Gantt Chart | Critical path method | Resource levelling | Precedence diagramming method | 2 | 5A | 6 |  | 5A-6
11 | 483 | What is the purpose of an Earned Value Analysis in the Control Cost process? | Provide a quantitative basis for updating the budget | Facilitate a quantitative risk assessment of project costs | Provide a basis for approving quality-related change requests | Provide the details needed for lessons learned related to cost management | 1 | 5A | 7 |  | 5A-7
11 | 484 | What is the primary purpose of continuously monitoring cost performance against the approved cost baseline? | Updating the project schedule | Identifying and managing cost variances | Forecasting project risks | Managing change requests | 2 | 5A | 7 |  | 5A-7
11 | 485 | What is the purpose of tracking costs at different levels, such as by period, work breakdown structure (WBS) component, and activity? | To facilitate detailed cost analysis and control | To improve project documentation accuracy | To ensure regulatory compliance | To enhance team collaboration and communication | 1 | 5A | 7 |  | 5A-7
11 | 486 | Which of the following is not a common project cost control action? | Influencing the factors that create changes to the authorised cost baseline | Ensuring that all change requests are acted on in a timely manner | Monitoring work performance against funds expended | Informing the regulator of all approved changes and associated cost | 4 | 5A | 7 |  | 5A-7
11 | 487 | What is the Estimate at Completion (EAC) used for in project cost management? | Updating the project schedule | Assessing project risks | Forecasting the total project cost | Managing changes to the cost baseline | 3 | 5A | 7 |  | 5A-7
11 | 488 | What does the approved cost baseline represent? | The actual cost spent on the project | The authorised budget for the project | The initial budget for the project | The performance measurement baseline | 2 | 5A | 7 |  | 5A-7
11 | 489 | You are a project manager for Laurel’s Theatre Productions. Your new project is coming in over budget and requires a cost change through the cost change control system. You know all of the following statements are true regarding Control Costs except for which one? | A description of how cost changes should be managed and controlled is found in the cost management plan. | Approved cost changes are reflected in the cost baseline. | EVM is used to determine the cost performance that must be realised for the remaining work of the project to meet the BAC goal. | This equation, EAC = BAC / CPI, forecasts an estimate at completion, assuming future project performance will be the same as past performance. | 3 | 5A | 7 |  | 5A-7

## Pre
cell_index | question_index | question_text | opt_1 | opt_2 | opt_3 | opt_4 | 1nswer | mod | parent | sub | id
4 | 421 | What does monitoring and controlling involve? | Ensuring the project is ahead of schedule | Collecting, measuring, and assessing data and trends | Setting project performance objectives | Creating a project management plan | 2 | 5A | 2 | a | 5A-2a
4 | 424 | What is the significance of milestone monitoring in project management? | It helps in completing the project ahead of schedule. | It serves as a checkpoint for tracking progress. | It replaces the need for progress reports. | It is optional and not necessary for project success. | 2 | 5A | 2 | a | 5A-2a
11 | 429 | Which formula is used to calculate the Cost Variance (CV)? | CV = AC – EV | CV = PV – EV | CV = EV – PV | CV = EV – AC | 4 | 5A | 2 | b | 5A-2b
11 | 434 | You are managing a construction project with a budget of $800,000. The project involves two construction teams working for six months, totalling 10,000 hours of labour. According to your project schedule, 38% of the work should be completed by now. However, you've noted that 40% of the work is complete, but 50% of the budget has already been spent. What does this indicate about your project's status? | The project is ahead of schedule and under budget. | The project is ahead of schedule but over budget. | The project is behind schedule but under budget. | The project is on schedule but over budget. | 2 | 5A | 2 | b | 5A-2b
7 | 468 | What is one of the primary purposes of the Control Scope process in project management? | Defining project objectives | Monitoring project progress | Managing changes to the scope baseline | Capturing lessons learned | 3 | 5A | 5 |  | 5A-5
7 | 470 | In project management, which of the following processes works synergistically with the Control Scope process to maintain alignment between the project's evolving scope and its overarching plan? | Perform Integrated Change Control | Perform Quality Control | Monitor and Control Project Work | Validate Scope | 1 | 5A | 5 |  | 5A-5
9 | 475 | What is the purpose of the iteration burndown chart? | Monitoring resource utilisation | Tracking progress and identifying risks in an iteration | Analysing project costs | Evaluating stakeholder satisfaction | 2 | 5A | 6 |  | 5A-6
9 | 478 | When should schedule status reviews and walkthroughs be conducted in controlling contractors' schedules? | At irregular intervals | After project completion | As needed based on contractor requests | Regularly and at milestone points | 4 | 5A | 6 |  | 5A-6
11 | 483 | What is the purpose of an Earned Value Analysis in the Control Cost process? | Provide a quantitative basis for updating the budget | Facilitate a quantitative risk assessment of project costs | Provide a basis for approving quality-related change requests | Provide the details needed for lessons learned related to cost management | 1 | 5A | 7 |  | 5A-7
11 | 487 | What is the Estimate at Completion (EAC) used for in project cost management? | Updating the project schedule | Assessing project risks | Forecasting the total project cost | Managing changes to the cost baseline | 3 | 5A | 7 |  | 5A-7

## currentQuiz
cell_index | question_index | question_text | opt_1 | opt_2 | opt_3 | opt_4 | answer | mod | parent | sub | id | explanation
0 | 1 | What is the main difference between projects and operations? | Projects are permanent, whereas operations are temporary. | Projects focus on generating unique results while operations maintain the business functions. | Operations typically focus on external stakeholders, while projects do not. | Projects require strategic goals, while operations do not. | 2 | 1 | 2 |  | m1-2 | The correct answer is "projects focus on generating unique results while operations maintain business functions" because projects are temporary endeavours with specific objectives. In contrast, operations involve ongoing, repetitive tasks that support business activities. The other options are incorrect as they do not accurately describe the distinction between the unique nature of projects and the continuous nature of operations.
0 | 2 | A series of activities to create a unique product or service by a specific date is best described as one of the following? | A program | An operation | A project | A subproject | 3 | 1 | 2 |  | m1-2 | A project is a temporary endeavour to create a unique product, service, or result, associated with deadlines and cost constraints. The term 'programme' is incorrect as it refers to a collection of projects working towards a common goal. Similarly, 'operation' is also inaccurate, as operations represent an organisation's ongoing activities. A subproject is defined as a project that is part of and supports a larger project, making it incorrect as well.
0 | 3 | Projects are temporary endeavours to create a unique product, service, or result. Which one of the following does not relate to the concept of “temporary” in project management? | The project team | The market window status on which the project is capitalising | The project manager | The project deliverable | 4 | 1 | 2 |  | m1-2 | The correct answer is “the project deliverable”, as most projects create a deliverable that will outlive the project itself. The other options are incorrect because these attributes are temporary.
0 | 4 | Your organisation uses projects, programs, and portfolios. Some project team members are confused about what a program is. Which one of the following is a program? | A very large, complex project | A collection of small projects with a common goal | A collection of projects with a common objective | A collection of subprojects with a typical customer | 3 | 1 | 2 |  | m1-2 | The correct answer is “a collection of projects with a common objective”, as a program is a collection of projects completed together to gain benefits by managing the projects as a group rather than individually. The other options are not attributes of programs because projects within a program are neither necessarily small nor are they subprojects.
0 | 5 | You are being interviewed by a functional manager who says, “We have this huge undertaking of launching an online education website that contains different components, such as designing the website, developing the content, developing the administrative system including registration and payment, marketing the courses on the website, integrating different components of the website, and finally going live. Each component is functionally complex and large enough to be better served under different management.” The manager is most likely describing a: | Project | Program | Operation | Portfolio | 2 | 1 | 2 |  | m1-2 | “Program” is the correct answer because it sounds like a group of interrelated projects, which would nicely fit into a program. “Project” is incorrect because a project usually has only one manager. “Operation” is wrong because the undertaking is temporary and has a set of unique products. “Portfolio” is incorrect because a portfolio may contain projects and programs, and this conversation is held at the program level, not at the portfolio level.
0 | 6 | Your organisation would like to create a new product based on market research. This new product will be created in a project. This is an example of which one of the following reasons to launch a new project? | Organisational need | Customer request | Market demand | Legal requirement | 3 | 1 | 2 |  | m1-2 | The answer is “market demand,” as projects can be created for several reasons. This example supports the choice of market demand. The other options are incorrect as “organisation need” is created to satisfy an internal need. “Customer request” is incorrect because no specific customer requested this new product. Lastly, “legal requirement” is wrong because there is no legal requirement to create a new product.
0 | 7 | Which of the following is not a project management knowledge area? | Project procurement management | Project risk management | Project quality management | Project team management | 4 | 1 | 2 |  | m1-2 | “Project team management” is the correct answer because it is not a knowledge area. This task is part of the human resource management knowledge area. The other options are incorrect because they are three of the ten project management knowledge areas.
0 | 8 | The risk register is not an input to which of the following processes? | Identify risks | Perform qualitative risk analysis | Perform quantitative risk analysis | Implement risk responses | 1 | 1 | 2 |  | m1-2 | “Identify risks” is the correct answer because the risk register is the output of the risk identification process. Still, it was not used as input because it did not exist before this process. The other options are incorrect because the risk register is an input item for performing qualitative risk analysis, quantitative risk analysis, planning risk responses, implementing risk responses, and monitoring risks.
0 | 9 | You are managing a project in biotechnology code-named Mitochondria Eve. You need work performance measurements or information to write the performance reports. Which process(es) will you run? | Monitor and control project work | Control scope, control schedule, and control cost | Develop project work performance report | Direct and manage project work | 2 | 1 | 2 |  | m1-2 | “Control scope, control schedule, and control cost” is the correct answer because controlling scope, schedule, and cost generates work performance information. “Monitor and control project work” is incorrect because the Monitor and Control Project Work process generates performance reports and uses work performance information as input. “Develop project work performance report” is wrong because there is no standard project work performance report development process. “Direct and manage project work” is wrong because the Direct and Manage Project Work process does not generate work performance information; it creates work performance data instead.
0 | 10 | A project is considered successful when ____________. | The product of the project has been manufactured | The project sponsor announces the completion of the project | The product of the project is turned over to the operations area to handle the ongoing aspects of the project | The project achieves its objectives and meets the expectations of the stakeholders | 4 | 1 | 2 |  | m1-2 | A project succeeds when it achieves its objectives and meets the expectations of stakeholders. Success is gauged by how well the project aligns with its original scope, schedule, cost, and quality while addressing stakeholder needs. The other options are incorrect as manufacturing the product, although important, is merely one phase of the project and does not guarantee success if objectives or expectations remain unmet. Similarly, the sponsor's announcement of project completion does not define success unless the outcomes meet the required standards. Moreover, transitioning the product to operations is a critical step in project closure, yet it does not alone signify overall success. True success is determined by the project's capacity to deliver intended results and satisfy stakeholders.
0 | 11 | Which of the following statements is true? | Programs are groups of related projects | Project life cycles are collections of sequential, iterative, and overlapping project phases | A project may or may not be part of a program | Portfolios are collections of interdependent projects or programs | 4 | 1 | 2 |  | m1-2 | The answer is "portfolios are collections of interdependent projects or programs". Portfolios are structured collections of projects, programs, or both, which are managed as a group to achieve strategic objectives. This makes the statement about portfolios true. Programs, on the other hand, consist of related projects that are managed together to achieve benefits not available if managed separately. Project life cycles, while involving sequential, iterative, or overlapping phases, describe the progression of a single project rather than a collection of projects. Lastly, a project may or may not belong to a program, but this is a contextual fact, not a defining truth about project management. Therefore, the statement about portfolios accurately captures their role in strategic alignment and management.
0 | 12 | Which of the following applies a set of tools and techniques used to describe, organise, and monitor the work of project activities to meet the project requirements? | Project managers | The PMBOK® Guide | Project management | Stakeholders | 3 | 1 | 2 |  | m1-2 | The correct answer is "project management". Project management applies a structured set of tools, techniques, and methodologies to define, organise, and monitor project activities. Its purpose is to ensure the project's objectives are achieved within the constraints of scope, time, cost, and quality while meeting stakeholder expectations. While project managers are responsible for implementing these practices, they are not the system or methodology itself. The PMBOK® Guide is a reference framework for project management, but it does not directly apply tools and techniques—it provides guidance. Stakeholders are impacted by or influence the project but are not responsible for organising or monitoring the work. Therefore, project management is the correct and encompassing term.
0 | 13 | Which of the following statements is true regarding the Project Management Knowledge Areas? | They include Initiation, Planning, Executing, Monitoring and Controlling, and Closing. | They consist of 10 areas that bring together processes with things in common. | They consist of five processes that bring together project phases with things in common. | They include Planning, Executing, Monitoring and Controlling processes because they are commonly interlinked. | 2 | 1 | 2 |  | m1-2 | Project Management Knowledge Areas are key components in project management, as outlined in the PMBOK® Guide. They include 10 distinct areas that group related processes based on common themes, such as integration, scope, time, cost, quality, resource, communications, risk, procurement, and stakeholder management. These knowledge areas define the specific expertise and focus needed to manage a project effectively. The other options are incorrect because the process groups (Initiating, Planning, Executing, Monitoring and Controlling, and Closing) are not the same as the knowledge areas. Furthermore, knowledge areas are not limited to five processes or phases, nor are they restricted to interlinked processes. The 10 knowledge areas provide a more comprehensive framework for project management.
0 | 14 | You are managing a software development project with a set of preplanned milestones. Your team has completed all milestones, and you are now verifying that the product meets the specifications outlined in the project management plan. What process group are you currently in? | Monitoring and controlling | Closing | Executing | Planning | 1 | 1 | 2 |  | m1-2 | The correct answer is “monitoring and controlling," as you verify that the product meets the specifications outlined in the project management plan, which is a key activity within the Monitoring and Controlling process group. This process group ensures that the project stays on track by measuring performance, monitoring compliance with the plan, and taking corrective actions as necessary. The other options are incorrect because closing involves finalising the project or phase, including formal acceptance and documentation; executing refers to performing the work defined in the project plan to achieve the objectives, while planning focuses on determining the scope, objectives, and course of action to accomplish the project's goals, rather than controlling and monitoring the results.
0 | 15 | Why is project tailoring necessary? | To ensure uniformity across all projects | To adapt methods to specific project environments | To reduce stakeholder input | To avoid risks | 2 | 1 | 3 |  | m1-3 | The answer is "to adapt methods to specific project environments" because every project is unique, with its own objectives, constraints, stakeholders, and environmental factors. Tailoring allows project managers to customise processes, tools, and techniques to suit the specific needs and conditions of a project. This ensures that the chosen methodologies are effective and relevant to the project's context. The other options are incorrect because ensuring uniformity across all projects contradicts the need for flexibility and adaptation. Reducing stakeholder input is not a purpose of tailoring, though stakeholder involvement is often critical in tailoring decisions. Lastly, avoiding risks is a goal of risk management, not the primary purpose of project tailoring.
0 | 16 | What is the primary objective of project integration management? | Minimising project costs | Coordinating all project elements for cohesion | Avoiding stakeholder conflicts | Limiting quality checks | 2 | 1 | 3 |  | m1-3 | The correct answer is “Coordinating all project elements for cohesion” because integration management ensures that all processes and knowledge areas work together to achieve project objectives. The other options are incorrect because “minimising project costs” is part of cost management, “avoiding stakeholder conflicts” is a focus of stakeholder management, and “limiting quality checks” is not relevant to integration management.
0 | 17 | What is the benefit of using Net Promoter Score (NPS) in project management? | Measures customer satisfaction and loyalty | Minimises project risks | Avoids stakeholder engagement | Ensures zero-cost project execution | 1 | 1 | 3 |  | m1-3 | The correct answer is “measures customer satisfaction and loyalty” because NPS assesses stakeholders’ willingness to recommend the project outcomes, which reflects satisfaction and loyalty. The other options are wrong as NPS does not address risk management, stakeholder avoidance, or cost execution.
0 | 18 | Which phase in the construction life cycle focuses on feasibility? | Design phase | Conception phase | Commissioning phase | Close-out phase | 2 | 1 | 3 |  | m1-3 | The correct answer is “conception phase” because it evaluates the project's viability and develops preliminary plans. The other options represent subsequent phases of the life cycle.
0 | 19 | What drives the creation of business value in projects? | Reducing the number of stakeholders involved | Aligning project deliverables with strategic objectives | Minimising costs at all stages | Eliminating risks entirely | 2 | 1 | 3 |  | m1-3 | The correct answer is “Aligning project deliverables with strategic objectives” because projects deliver business value by aligning outputs with organisational goals.
0 | 20 | What does quality management in a project ensure? | Deliverables meet established standards | Costs are minimised regardless of quality | Risks are eliminated entirely | Only stakeholders’ financial goals are met | 1 | 1 | 3 |  | m1-3 | The correct answer is "Deliverables meet established standards" because quality management ensures that project outputs adhere to agreed-upon specifications, meeting the required standards. The other options are incorrect because minimising costs without considering quality compromises deliverables, eliminating risks entirely is unrealistic, and focusing solely on financial goals ignores broader quality objectives.
0 | 21 | Which knowledge area deals primarily with timelines and scheduling? | Project Scope Management | Project Resource Management | Project Time Management | Project Integration Management | 3 | 1 | 4 |  | m1-4 | The correct answer is "Project Time Management" because it involves planning, managing, and controlling the schedule to meet project deadlines. The other options are incorrect as they deal with other aspects like scope, resources, and integration, not specifically with time.
0 | 22 | Which phase focuses on transferring project deliverables to the client? | Close-out phase | Construction phase | Initiation phase | Planning phase | 1 | 1 | 4 |  | m1-4 | The correct answer is "Close-out phase" because this phase involves finalising all project activities and handing over deliverables to the client. The other options are incorrect as they focus on different project phases such as planning, construction, or initiation.
0 | 23 | How does project risk management differ from general risk management? | It focuses solely on financial risks | It eliminates the need for quality management | It includes all risks impacting project goals and deliverables | It ignores low-priority risks | 3 | 1 | 4 |  | m1-4 | The correct answer is "It includes all risks impacting project goals and deliverables" because project risk management considers any risks that might affect the project's success. The other options are incorrect as they mischaracterise the scope or purpose of risk management.
0 | 24 | Why is stakeholder management essential in project management? | It ensures that financial goals are prioritised | It identifies and manages stakeholder needs and expectations | It eliminates the need for quality control measures | It reduces project costs | 2 | 1 | 4 |  | m1-4 | The correct answer is "It identifies and manages stakeholder needs and expectations" because stakeholder management ensures that the project aligns with stakeholder requirements. The other options are incorrect as they focus solely on financial goals or cost reduction and disregard the broader purpose of stakeholder management.
0 | 25 | Which process ensures project phases transition smoothly? | Scope planning | Stakeholder mapping | Phase gate review | Scheduling | 3 | 1 | 4 |  | m1-4 | The correct answer is "Phase gate review" because it provides structured checkpoints to assess and ensure readiness before moving to the next phase. The other options, such as scope planning or scheduling, do not specifically address phase transitions.
0 | 26 | A local government initiates an urban redevelopment project to revitalise a declining city area. The project includes building a community centre, improving public transport, and introducing green spaces. Stakeholders include residents, business owners, city officials, and environmental groups. Which project management principle is most critical for ensuring diverse stakeholder satisfaction in this project? | Focusing on value | Tailoring project processes | Engaging stakeholders | Managing risk effectively | 3 | 1 | 5 |  | m1-5 | The correct answer is "Engaging stakeholders" because actively involving diverse stakeholders ensures their needs and expectations are addressed. The other options are secondary or broader principles that do not focus specifically on stakeholder satisfaction.
0 | 27 | A pharmaceutical company is launching a new drug to treat chronic conditions. The project requires compliance with strict regulations, high stakeholder involvement, and coordination across R&D, manufacturing, and marketing teams. The marketing team proposes a last-minute change to the product’s branding, which could delay regulatory approval. How should the project manager respond? | Approve the change if it aligns with strategic goals | Reject the change outright to avoid delays | Escalate the decision to the project sponsor for resolution | Conduct a risk assessment to determine the impact of the change | 4 | 1 | 5 |  | m1-5 | The correct answer is "Conduct a risk assessment to determine the impact of the change" because assessing the risk allows the project manager to evaluate how the branding change might affect timelines and regulatory compliance. The other options either overlook the potential impact or shift responsibility unnecessarily.
0 | 28 | A construction firm manages a mega bridge project involving multiple contractors, suppliers, and government agencies. The project aims to improve connectivity between two cities, with an expected completion time of 7 years. What project life cycle model should the team follow for optimal stakeholder coordination in such a complex project? | Agile approach | Integrated project delivery (IPD) | Waterfall approach | Incremental approach | 2 | 1 | 5 |  | m1-5 | The correct answer is "Integrated project delivery (IPD)" because it fosters collaboration among contractors, suppliers, and government agencies, which is crucial for complex, long-term projects. The other options are less suitable for managing such extensive stakeholder coordination.
0 | 29 | A company is upgrading its IT infrastructure to improve data security and support remote work capabilities. The project has a tight deadline and is met with resistance from employees. Halfway through the project, new security threats emerge, requiring additional upgrades. How should the project manager respond? | Ignore the threat to meet deadlines | Escalate the issue to senior management | Update the risk register and adjust project plans | Postpone the project until threats are fully resolved | 3 | 1 | 5 |  | m1-5 | The correct answer is "Update the risk register and adjust project plans" because documenting and addressing new security threats ensures the project remains aligned with organisational objectives. The other options either ignore the threat or delay the project unnecessarily.
0 | 30 | A non-profit organisation is launching a project to install solar panels in rural communities. The project faces logistical challenges and budget constraints, but stakeholders strongly support it. The project’s funding is delayed, halting procurement activities. What should the project manager do? | Identify alternative funding sources and reassess priorities | Pause the project until funds are secured | Scale down the project to reduce financial dependency | Shift resources to other ongoing projects temporarily | 1 | 1 | 5 |  | m1-5 | The correct answer is "Identify alternative funding sources and reassess priorities" because exploring additional funding options and prioritising activities ensures progress despite budget constraints. The other options are less proactive and do not address the underlying issue effectively.
0 | 31 | You have been assigned to a project to expand three miles of the north-to-south highway through your city by two lanes in each direction. You are in charge of this project's demolition phase and report to the project manager. This project is producing deliverables in short periods. You work with the product owner. Your project team holds daily standup meetings and retrospective meetings at the end of the working period. What methodology does this describe? | Iterative | Adaptive | Agile | Incremental | 3 | 1 | 5 |  | m1-5 | This question describes the Agile methodology, which uses daily standups, sprint planning meetings, and retrospectives and works with a Scrum master and product owner.
0 | 32 | Your project was just completed. Because of some unfortunate circumstances, the project was delayed, causing cost overruns at the end of the project. Which of the following statements is true? | You should pay particular attention to archiving the financial records for this project. | You should document the circumstances as lessons learned. | Your project ended because of starvation because of the cost overruns. | You should document the circumstances surrounding the project completion during the scope verification process. | 2 | 1 | 5 |  | m1-5 | Lessons learned document the experiences, successes, and failures that occurred during this project for future reference. There is not enough information in the question to determine whether the other options are correct. "Your project ended because of starvation because of the cost overruns" is not correct because the project was completed.
1 | 33 | Which of the following processes is typically not part of the pre-initiating phase in project management? | Defining the project’s objectives and success criteria | Involve stakeholders to create a shared understanding of the success criteria | Developing the project charter | Establishing the project team and assigning roles and responsibilities | 3 | 2 | 6 |  | m1-6 | The project charter is usually developed during the initiating phase. It formally authorises the project and gives the project manager the authority to apply organisational resources to project activities.
1 | 34 | A business case is a document that outlines the justification for undertaking a project and includes various components. Which of the following is typically not included in a business case? | Business objectives | Potential risks | Budget estimate and financial analysis | Project execution plan and timeline | 4 | 2 | 6 |  | m1-6 | The correct answer is “project execution plan and timeline”, as a business case primarily focuses on justifying the need for a project. It outlines business objectives and potential risks and includes a budget estimate and financial analysis to determine if the project is feasible and beneficial. However, a detailed project execution plan and timeline are usually part of the project management plan (developed after the project is approved), not the initial business case.
1 | 35 | Which of the following describes one of the roles of a project sponsor? | Leading the project team | Documenting project evaluation | Setting project objectives | Advocating for the project and team | 4 | 2 | 6 |  | m1-6 | “Advocating for the project and team” is the correct answer. A project sponsor plays a key leadership role by championing the project within the organisation, securing resources, and ensuring alignment with strategic goals. While the project sponsor may influence objectives and monitor progress, the project manager typically handles the tasks of leading the project team and documenting project evaluation.
1 | 36 | What does a cost-benefit analysis include? | Project risk mitigation | Financial viability | Project schedule | Stakeholder engagement | 2 | 2 | 6 |  | m1-6 | The correct answer is “financial viability.” A cost-benefit analysis (CBA) evaluates whether a project's benefits outweigh its costs, helping to determine its financial viability. It includes tangible and intangible costs and benefits to assess the project’s profitability. Risk mitigation, project schedules, and stakeholder engagement are essential aspects of project management but are not directly part of the CBA.
1 | 37 | Which of the following is not true regarding the purpose of a business case? | It is an economic feasibility study that helps determine whether the investment in the project is worthwhile. | It describes the need or demand that brought about the project. | It describes how the benefits of the project will be measured and obtained. | It contains the results of the benefit measurement methods that will assist in project selection. | 3 | 2 | 6 |  | m1-6 | The purpose of the business case is to understand the business need for the project and to determine whether investing in the project is worthwhile. This may involve analysis through benefit measurement methods. The benefits, including how they are measured and realised, are outlined in the benefits management plan.
1 | 38 | You are a project manager recently assigned to a construction project. The sponsor has just communicated the high-level expectations of the project to you. However, the remote project site and environmental regulations are highly stringent. What is your next logical step in the pre-initiation process to ensure the project’s success? | Start developing a detailed project schedule | Begin assessing the potential risks associated with the project site | Begin construction-related tasks to avoid delays | Request the sponsor to prepare the business case for review | 2 | 2 | 6 |  | m1-6 | The correct answer is “begin assessing the potential risks associated with the project site”, as during the pre-initiation process, it is essential to assess any project site-related risks, especially when environmental regulations are strict. These risks can significantly impact project planning and execution, making it vital to address them early on. The other options are incorrect because developing a detailed schedule is premature without understanding the risks. Starting construction without adequate risk analysis can lead to costly issues later, and requesting the sponsor to prepare the business case ignores the fact that the business case should already be ready before your involvement.
1 | 39 | You are involved in the pre-initiation phase of a large construction project. The sponsor presents you with a business case, including financial benefits, regulatory requirements, and preliminary project requirements. However, the document lacks a detailed analysis of site safety and environmental factors, which are crucial for this project. What should you do next? | Proceed with the available business case and begin project planning | Request the sponsor to revise the business case to include the missing information | Begin the cost-benefit analysis independently to assess the financial impact of missing elements | Ignore the omissions since the sponsor’s approval of the business case indicates readiness to proceed | 2 | 2 | 6 |  | m1-6 | The correct answer is “request the sponsor to revise the business case to include the missing information” because a comprehensive business case is critical for project success. Missing key components such as site safety and environmental factors can jeopardise the project. The other options are incorrect because proceeding without this information could lead to unaddressed risks, independently starting a cost-benefit analysis does not solve the issue of missing crucial project aspects, and ignoring the omissions could lead to significant problems later in project execution.
1 | 40 | The project sponsor has tasked you, the senior project manager, with selecting a suitable project manager for a high-profile construction project. The project is complex, involving multiple stakeholders and various regulatory bodies. What should be your primary consideration when selecting the project manager? | The project manager’s technical knowledge of construction methods | The project manager’s ability to meet strict deadlines | The project manager’s experience with managing stakeholder relationships and regulatory compliance | The project manager’s ability to negotiate lower costs with vendors | 3 | 2 | 6 |  | m1-6 | The correct answer is “the project manager’s experience managing stakeholder relationships and regulatory compliance”. Managing these relationships and ensuring compliance is vital to success in a complex construction project with multiple stakeholders and regulatory requirements. While technical knowledge, meeting deadlines, and cost negotiations are essential, the other options are wrong because focusing solely on technical skills may overlook critical managerial aspects, and prioritising deadlines without considering regulatory and stakeholder factors can cause issues. While cost negotiation is beneficial, it is not the most crucial factor in this scenario.
1 | 41 | What is the output of the “develop project charter” process? | Stakeholder register | Assumption log | Change request register | Project schedule | 2 | 2 | 6 |  | m1-6 | The correct answer is “assumption log.” The “develop project charter” process results in key outputs that establish the project's foundation. One such output is the assumption log, which captures key assumptions and constraints identified early in the project. Other options, like the stakeholder register and change request register, are developed later in the project lifecycle. The project schedule is part of project planning, not the charter development phase.
1 | 42 | Why might the initiating process change the project management plan and project documents? | Due to the completion of the project charter | Due to stakeholder resistance | Due to new stakeholders and their requirements | As a result of completed deliverables | 3 | 2 | 6 |  | m1-6 | The correct answer is “Due to new stakeholders and their requirements”. New stakeholders may be identified during the initiating process, or existing stakeholders might provide additional input. Their requirements or expectations can lead to necessary adjustments in the project management plan and other project documents to ensure alignment with stakeholder needs. The other options are not directly related to the changes typically made during the initiating process.
1 | 43 | As a project manager for a large-scale construction project, you have identified a key stakeholder group whose requirements were not initially considered during the project initiation. This new group has raised concerns about environmental sustainability. What action should you take first to address their concerns effectively? | Revise the project charter immediately to incorporate the new stakeholder requirements | Hold an urgent meeting with the new stakeholders to discuss their concerns and propose a solution | Update the stakeholder register and prepare a communication strategy to engage them further | Submit a change request to revise the project scope to address the new concerns | 3 | 2 | 6 |  | m1-6 | The correct answer is “update the stakeholder register and prepare a communication strategy to engage them further”. Other options, like the change request register, are developed later in the project lifecycle, and the project schedule is part of project planning, not the charter development phase.
1 | 44 | During the initiation phase of a bridge construction project, several assumptions were made regarding material availability and labour costs. As the project progresses, these assumptions show signs of being inaccurate, potentially impacting the budget. How should you address these emerging risks? | Continue with the project as planned since assumptions were already included in the project charter | Revise the assumption log to reflect the updated understanding and initiate a risk management process | Reduce project activities until a thorough investigation of the assumptions is completed | Update the project management plan and re-issue the project charter to include contingency plans | 2 | 2 | 6 |  | m1-6 | Revising the assumption log and initiating risk management is the correct approach because it acknowledges and integrates the changes into risk processes. The other options are incorrect because continuing the project without addressing risks can lead to cost overruns or delays. Reducing project activities could cause unnecessary disruption. Updating the project charter is inappropriate as it is not meant to capture assumptions in such detail.
1 | 45 | You are leading the initiation phase for a residential construction project. The kick-off meeting with key stakeholders has been scheduled. What is the primary purpose of this meeting? | To finalise the project budget and resources | To ensure stakeholder buy-in and clarify the project’s goals and key processes | To identify risks and update the project risk register | To establish the detailed project schedule and timelines | 2 | 2 | 7 |  | m1-7 | The main objective of a kick-off meeting is to ensure stakeholder buy-in and clarify the project’s goals and key processes. This fosters engagement and alignment early in the project.
1 | 46 | Which of the following is not an enterprise environmental factor (EEF)? | Organisational culture | Employee capability | Legal restrictions | Project structure | 4 | 2 | 7 |  | m1-7 | The correct answer is “project structure.” Enterprise Environmental Factors (EEFs) refer to external and internal factors influencing a project’s success. Organisational culture, employee capability, and legal restrictions are examples of EEFs, as they shape how projects are managed. However, the project structure is part of the organisational process assets (OPAs), not EEFs, as it relates to how a specific project is organised and managed within the company.
27 | 47 | For a construction project, which of the following is most likely an external stakeholder? | Safety auditor | Reinforcement concrete sub-contractor | Client project sponsor | Quantity surveyor | 1 | 2 | 7 |  | m1-7 | The correct answer is “safety auditor”. An external stakeholder is someone outside the project organisation but still impacted by or involved in the project. A safety auditor typically represents a regulatory body or an independent entity, making them an external stakeholder. The other roles, sub-contractor, client project sponsor, and quantity surveyor, are considered internal stakeholders as they are directly engaged in the project’s execution or management.
27 | 48 | Which of the following is most likely an internal stakeholder for a construction project? | Government inspector | Change control board members | Concrete supplier | Residents near site | 2 | 2 | 7 |  | m1-7 | The correct answer is “Change control board members”. Internal stakeholders are individuals or groups actively involved in the project’s planning, execution, or oversight. Change control board members participate in decision-making processes within the project, making them internal stakeholders. The other options are external stakeholders, who are outside the project organisation but still influence or are affected by the project.
27 | 49 | Which of the following need not be included in a stakeholder register during initiation? | Internal or external stakeholder | Role in project | Level of influence of stakeholder | Position | 4 | 2 | 7 |  | m1-7 | The correct answer is “position”. A stakeholder register focuses on information that helps manage stakeholder engagement, such as whether the stakeholder is internal or external, their role in the project, and their level of influence. While knowing a stakeholder’s position may be helpful, it is not essential to be included in a stakeholder register during the initiation phase.
27 | 50 | Stakeholder analysis belongs to which process group? | Initiation | Planning | Execution | Monitoring and controlling | 1 | 2 | 7 |  | m1-7 | The correct answer is “initiation”. Stakeholder analysis is performed during the initiation phase to identify stakeholders, assess their influence and interests, and plan appropriate engagement strategies. This early analysis ensures that stakeholder needs are considered, setting the foundation for effective project management.
27 | 51 | Which statement about the kick-off meeting is true? | It must be face-to-face | Not all key stakeholders need to be present | If well-conducted, it can ensure better buy-in | It can be conducted during the execution stage | 3 | 2 | 7 |  | m1-7 | The correct answer is, “If well-conducted, it can ensure better buy-in.” A kick-off meeting helps align the team and stakeholders with project goals, fostering commitment and engagement. It ensures everyone is on the same page from the start, enhancing buy-in for the project’s success. On the other hand, meetings do not have to be face-to-face; virtual meetings are now common. Key stakeholders should be present to align expectations. The kick-off meeting is typically conducted in the initiation or planning stage, not during execution.
27 | 52 | Who cannot be absent from a kick-off meeting for a construction project? | Project sponsor | Labour supplier | Regulator | Drywall sub-contractor | 1 | 2 | 2 |  | m2-2 | The correct answer is “project sponsor.” The project sponsor is a critical participant in the kick-off meeting, providing vision, authority, and alignment with strategic objectives. Their presence ensures the project team understands its importance and has the necessary support. In contrast, depending on the meeting's scope and phase, the labour supplier, regulator, and subcontractors may not always need to attend the kick-off meeting. Their involvement can be addressed later during detailed planning or execution.
27 | 53 | Which of the following agenda items is not essential for a kick-off meeting? | Introduction of attendees | Discuss project organisational structure | Identify potential risks | Discuss project scope | 3 | 2 | 2 |  | m2-2 | The correct answer is “identify potential risks.” While risk identification is important, it is typically addressed in detailed planning sessions rather than the kick-off meeting. The primary purpose of the kick-off meeting is to align everyone on the project scope, objectives, roles, and responsibilities. Essential agenda items for a kick-off meeting include an “Introduction of attendees” to build rapport, a discussion of the project scope to ensure a shared understanding, and clarifying the project organisational structure to clarify roles and reporting lines.
2 | 54 | Multiple changes to the model have been proposed to address important client requests in a construction project using Building Information Modelling (BIM). What is the best way to manage these changes? | Approve all changes directly within the BIM system without formal review since it is still in the start stage of the project | Implement the changes gradually without disrupting ongoing work to save time | Evaluate each change request in line with the project’s configuration and change management plans before approval | Reject some BIM changes but accept some to maintain the project’s original schedule and budget | 3 | 3A | 2 |  | m2-2 | The correct answer is “evaluate each change request by the project’s configuration and change management plans before approval.” Evaluating BIM changes according to these plans ensures that all proposed modifications are controlled and approved by project objectives. The other options are incorrect because approving all changes without review, implementing them gradually, or rejecting some changes outright could lead to mismanagement, inefficiency, or missed project improvement opportunities.
2 | 55 | You manage a large construction project with multiple teams handling different aspects, including structural design and electrical work. Coordination between the teams has become challenging, and the project is falling behind. What is the most effective strategy to manage integration? | Let each team manage their tasks independently to avoid further delays | Update the scope management plan to reduce the number of interdependent tasks | Meet with each team individually and adjust the project plan based on their needs | Use the PM plan to coordinate and integrate the efforts of all teams, ensuring consistency across the project | 4 | 3A | 2 |  | m2-2 | The correct answer is “use the PM plan to coordinate and integrate the efforts of all teams, ensuring consistency across the project”. The PM plan integrates all management areas, ensuring team consistency and coordination, which is essential for project success. The other options are wrong because allowing independent work, adjusting scope without proper coordination, or individual adjustments can lead to further disorganisation.
2 | 56 | The main purpose of project planning is to guide project ____. | Initiation | Execution | Review | Evaluation | 2 | 3A | 2 |  | m2-2 | The correct answer is “execution”. The primary purpose of project planning is to create a detailed roadmap that guides the execution of the project. It ensures that tasks are well-defined, resources are allocated, timelines are established, and risks are managed, helping the team execute the project smoothly and efficiently. In contrast, initiation involves defining the project’s purpose, and review and evaluation occur after execution, during the monitoring and closing phases.
2 | 57 | Why is project integration management crucial for project managers? | It coordinates all the project management knowledge areas. | It focuses on individual staff duties and KPIs. | It facilitates communication among stakeholders. | It ensures consistency across scope, schedule, and budget. | 1 | 3A | 2 |  | m2-2 | The correct answer is “it coordinates all the project management knowledge areas”. Project integration management is essential because it ensures that all aspects of a project, such as scope, schedule, cost, quality, resources, and risks, are aligned and work together seamlessly. It helps the project manager coordinate efforts across different areas to achieve the project’s objectives. While it involves communication and consistency, those are managed within specific knowledge areas. It does not focus on individual staff duties or KPIs and falls under human resource management.
2 | 58 | You are managing a large construction project to build a commercial office complex. Midway through the project, the client requests significant design changes to the interior layout. After identifying the need for the change, you must assess its impact on the project’s scope, schedule, and budget. Based on best practices for change management, what would be your next step? | Incorporate the change and inform the client about any delays afterwards | Pause the work and call for a meeting with the Change Control Board (CCB) to approve the change | Conduct a detailed impact assessment, then submit the findings to the Change Control Board for approval | Submit a change request to the sponsor for direct approval without an impact assessment | 3 | 3A | 2 |  | m2-2 | The correct answer is “Conduct a detailed impact assessment, then submit the findings to the Change Control Board for approval”. The next logical step after identifying a change is conducting an impact assessment to analyse its effect on scope, budget, and schedule. This ensures that decisions are data-driven and the project stays on track, preventing scope creep. The other options are wrong because skipping the impact assessment could result in unforeseen budget overruns or missed deadlines. Pausing all work without prior assessment and context could unnecessarily delay progress.
2 | 59 | Due to evolving client requirements, multiple versions of the structural blueprints have been issued during the construction of a residential tower. The contractor is confused about which version to follow, which has led to a delay. Under configuration management, what is the best approach to resolve this issue and prevent future occurrences? | Issue all versions of the blueprints and allow the contractor to choose the most recent one | Implement strict version control and ensure the contractor works only with the approved baseline blueprint | Allow changes to be made as they arise to avoid bottlenecks | Assign the contractor responsibility for managing their version control process | 2 | 3A | 2 |  | m2-2 | The correct answer is “Implement strict version control and ensure the contractor works only with the approved baseline blueprint”. Proper version control is key to effective configuration management, ensuring that only the approved and baseline blueprints are followed. This reduces confusion and helps maintain consistency in project deliverables.
2 | 60 | You are overseeing the construction of a healthcare facility. The client requests several enhancements early in the project, including additional rooms and a different façade design. This would significantly increase costs and extend the project timeline. You are concerned about the project’s scope creeping beyond control. What action should you take as the project manager to maintain control over the project? | Assess the feasibility of the enhancements through a scope baseline change request | Approve the changes and revise the project plan based on client preferences | Reject the changes to avoid scope creep and maintain the original project schedule | Apply the requested changes progressively to prevent antagonising the client | 1 | 3A | 3 |  | m2-3 | The correct answer is “Assess the feasibility of the enhancements through a scope baseline change request”. Evaluating the changes against the scope baseline is critical before committing to any enhancements. This helps ensure the project remains feasible while controlling scope creep. The other options are wrong because simply approving or applying the changes without assessment could overrun the budget and schedule while rejecting them outright could damage client relationships.
2 | 61 | During the construction of a high-rise apartment complex, a site supervisor makes several unapproved modifications to the material specifications, thinking they will improve structural integrity. Upon discovering this, you, as the project manager, need to act. What is the correct course of action according to configuration and change management principles? | Continue with the modifications since they improve the project outcomes | Accept the changes and adjust the project baseline accordingly | Halt further work, conduct a configuration audit, and submit a change request for approval | Revert to the original specifications immediately and discipline the supervisor | 3 | 3A | 3 |  | m2-3 | The correct answer is “Halt further work, conduct a configuration audit, and submit a change request for approval”. A configuration audit followed by a formal change request ensures that all modifications are documented, assessed, and approved within the project’s change management process. The other options are wrong because making changes without formal review could lead to inconsistencies and scope creep. Immediate reversion might ignore the potential benefits of the changes and bypass the necessary evaluation of the modifications.
2 | 62 | As a construction project manager, you face resistance from your structural engineer and the procurement team when integrating scope and budget management. They are focused on their KPIs and resist coordination. How should you use the project management plan (PM plan) to address this issue? | Reassign the teams to focus solely on their respective areas of expertise to avoid further resistance | Adjust the PM plan to exclude detailed budget management to keep the team motivated | Allow the teams to operate independently while you monitor their progress closely | Use the PM plan to facilitate communication and highlight the overall project objectives to align team efforts | 4 | 3A | 3 |  | m2-3 | The correct answer is “Use the PM plan to facilitate communication and highlight the overall project objectives to align team efforts”. The PM plan provides a roadmap for communication and ensures all stakeholders understand the project goals, reducing resistance by aligning efforts with the overall objectives. The other options are wrong because isolating teams increase fragmentation, and excluding key details like budget can cause misalignment and project failure.
2 | 63 | Midway through a residential construction project, the client requests additional modifications to the exterior façade. You identify the need for the change, but before proceeding, what is the next critical step in managing this change? | Conduct an impact assessment of the change on scope, budget, and schedule before submitting it to the Change Control Board (CCB) | Implement the change and assess the cost overruns later | Reject the change due to potential delays and cost increases | Inform the client that all changes might be postponed until project completion | 1 | 3A | 3 |  | m2-3 | The correct answer is “Conduct an impact assessment of the change on scope, budget, and schedule before submitting it to the Change Control Board (CCB)”. An impact assessment is crucial in determining how the change will affect the project and whether it aligns with project goals before it goes to the CCB for approval. The other options are wrong because implementing changes without analysis, rejecting the change outright, or postponing all changes may lead to client dissatisfaction or unforeseen consequences.
2 | 64 | In your construction project, multiple changes to the architectural drawings have been requested and approved. However, the contractor is struggling to keep track of the correct versions. What action should you take to prevent future confusion? | Ensure that the contractor uses the latest but unapproved versions of the drawings for faster progress | Create separate baselines for each version and allow the contractor to choose | Eliminate baselines to avoid complexity and rely on communication for updates | Maintain a strict baseline management process to track and control approved versions of the drawings | 4 | 3A | 3 |  | m2-3 | The correct answer is “Maintain a strict baseline management process to track and control approved versions of the drawings”. Baseline management ensures only approved versions are used, preventing errors and confusion. The other options are wrong because using unapproved versions, allowing contractors to choose from multiple baselines, or eliminating baselines would lead to project inconsistencies and lack of control.
2 | 65 | A new member of your team made unapproved changes to the material specifications. How should you address this issue under configuration management principles? | Accept the changes since they might improve project outcomes | Ignore the changes if the project remains on schedule | Perform a configuration audit and revert to the approved specifications if necessary | Allow the team to continue with their changes and update the configuration items later | 3 | 3A | 3 |  | m2-3 | The correct answer is “Perform a configuration audit and revert to the approved specifications if necessary”. A configuration audit ensures unapproved changes are identified and rectified, maintaining control over project deliverables. The other options are wrong because accepting changes without evaluation or ignoring them could compromise quality and project consistency.
2 | 66 | A client in a commercial building project requests several aesthetic changes that will significantly alter the project scope. How should you manage this without allowing scope creep as a project manager? | Approve the changes to keep the client satisfied and adjust the timeline later | Incorporate the changes immediately and request an additional budget afterwards | Refuse all client-requested changes to avoid delays | Follow the change management process, assessing the impact on scope, schedule, and budget before approval | 4 | 3A | 3 |  | m2-3 | The correct answer is “Follow the change management process, assessing the impact on scope, schedule, and budget before approval”. Following the change management process ensures that changes are evaluated for impact before approval, preventing uncontrolled scope expansion. The other options are wrong because incorporating changes without assessment or refusing all changes could lead to either scope creep or client dissatisfaction.
2 | 67 | In a construction project, the structural engineer frequently updates the blueprints, leading to confusion about which version to follow. As the project manager, how should you enforce version control? | Allow the team to use their most recent version and follow up | Postpone all updates until the final design is approved | Implement version control through a configuration management plan, ensuring all team members can access the latest version | Allow individual teams to manage their versions based on their best understanding | 3 | 3A | 4 |  | m2-4 | The correct answer is “Implement version control through a configuration management plan, ensuring all team members can access the latest version”. A configuration management plan ensures proper version control, allowing the team to work with the approved versions of documents. The other options are wrong because allowing teams to use different versions or postponing updates leads to project inconsistencies and confusion.
2 | 68 | You are managing a large-scale construction project, and the client has provided new feedback regarding safety features they want to incorporate. How should you handle this request? | Approve the safety changes immediately to avoid delays since they are our primary customer | Assess the impact of the safety changes on the project’s scope, cost, and schedule before seeking approval | Reject the changes as the safety features were not within the original scope, and it would take up more time | Implement the changes before informing other stakeholders to keep the project moving quickly | 2 | 3A | 4 |  | m2-4 | The correct answer is “Assess the impact of the safety changes on the project’s scope, cost, and schedule before seeking approval”. Assessing the impact of the safety changes ensures that the request is aligned with the project’s objectives and available resources before implementation. The other options are wrong because immediate approval, rejection, or implementation without consultation could lead to risks, misalignment, or budget and schedule overruns.
2 | 69 | Each option describes an element of the Develop Project Management Plan process, except for which one? | Project charter | Outputs from other planning processes | Configuration management system | Organisational process assets | 3 | 3A | 4 |  | m2-4 | The inputs for Developing a Project Management Plan include the project charter, outputs from other processes, enterprise environmental factors (EEF), and organisational process assets (OPA). The tools and techniques used in this process are expert judgment, data gathering, interpersonal and team skills, and meetings.
2 | 70 | Which of the following makes up the scope baseline when using a predictive life-cycle approach? | The approved project scope statement | The approved scope management plan and WBS | The WBS, the approved project scope statement, work packages, planning packages, and the WBS dictionary | The approved scope management plan, the WBS, work packages, planning packages, and the WBS dictionary | 3 | 3A | 4 |  | m2-4 | The scope baseline consists of the approved project scope statement, the WBS, work packages, planning packages, and the WBS dictionary.
6 | 71 | Henry is the project manager for his organisation, and management has asked him to create a project management plan to define the scope statement. Which project management plan guides the creation of the detailed project scope statement? | The project charter | The project management plan | The project scope plan | The project scope management plan | 4 | 3A | 4 |  | m2-4 | The correct answer is “the project scope management plan,” which defines the detailed creation of the project scope statement.
6 | 72 | You are the project manager of the ABC Project. This project will create a walking bridge across the Singapore River. You’ve been asked to start creating the project scope statement, and you must gather the elements for this process. Which one of the following is not required to define the project scope? | A project charter | Organisational process assets | A risk management plan | Requirements documentation | 3 | 3A | 4 |  | m2-4 | The answer is “risk management plan”. You would not need, or likely have, the risk management plan to define the project scope. The other options are incorrect because you will need the project charter, organisational process assets, and the requirements documentation to define the project scope.
6 | 73 | The project's milestones are scheduled at the end of each phase. Tied to these milestones is a project management requirement of scope validation. Scope validation leads to what? | Defect repair | Formal acceptance of the complete project scope | Rework | Inspection | 2 | 3A | 4 |  | m2-4 | The answer is “formal acceptance of the complete project scope”. Scope validation leads to formal acceptance of the complete project scope. The other options are incorrect because defect repair, rework, and inspection are not outputs of scope validation.
6 | 74 | One of the project stakeholders you manage asks why you regard the project scope statement as vital to your project management methodology. How do you respond to her question? | It is mandatory to consult the plan before authorising any change. | Project managers must document any changes before approving or declining them. | The project scope helps the project manager determine whether a change is within or outside of scope. | The project plan and earned value management (EVM) collaborate to assess the risks associated with proposed changes. | 3 | 3A | 4 |  | m2-4 | The project scope statement can help the project management team determine whether a proposed change is within or outside the project boundaries. The other options are factual statements, but they do not answer the question about the importance of the project scope statement.
6 | 75 | Marty, the project manager, is working with his team members to create the WBS. He shows the team how to divide the project scope into the WBS components, but the team does not understand how far down the breakdown should occur. What is the lowest-level item in a WBS? | A work package | A deliverable | An activity | A leaf object | 1 | 3A | 5 |  | m2-5 | The smallest item in the WBS is called the work package. A “deliverable” may be accurate, but a “work package” is a more precise answer. An “activity” is incorrect because activities are in the activity list, and a “leaf object” is an invalid WBS term.
6 | 76 | You will use the scope management plan to define the project scope statement. You will also use this plan to build the scope baseline. Which two items are parts of the scope baseline for the project? | Time and cost baselines | The project scope management plan and project charter | The project scope management plan and the WBS | The WBS and WBS dictionary | 4 | 3A | 5 |  | m2-5 | The WBS and WBS dictionary are two of the three components of the scope baseline. The approved detailed project scope statement is the third portion of the scope baseline. The other options are all incorrect because they do not accurately define the scope baseline.
6 | 77 | Which of the following is a false statement about the WBS? | A control account can have many account identifier codes. | You should keep composing WBS components at lower levels until necessary and sufficient decomposition has been achieved. | Each work component appears in the WBS once and only once. | The work packages should appear from left to right in the order in which the work will be performed. | 4 | 3A | 5 |  | m2-5 | The correct answer is “The work packages should appear from left to right in the order in which the work will be performed” because work packages do not have to appear in the order in which the work will be performed. This sequencing will be done later. The other options are incorrect answers because these are the characteristics of the WBS.
6 | 78 | What components are collectively called at the lowest level of the WBS hierarchy? | Work package | Control accounts | Phase | Milestones | 1 | 3A | 5 |  | m2-5 | “Work package” is correct because the components in the lowest level of the WBS hierarchy are called work packages. “Control accounts” is incorrect because a control account might contain multiple work packages. “Phase” is incorrect because if a phase is represented in the WBS, it will be represented at a much higher level. “Milestones” is incorrect because a milestone might consist of multiple work packages.
6 | 79 | Which of the following is a false statement about the Plan Scope Management process output that creates the project scope management plan? | It describes how to verify the project scope. | It describes how to control the project scope. | It does not describe how to manage the requirements. | It describes how to define the product scope. | 3 | 3A | 5 |  | m2-5 | The correct answer is “It does not describe how to manage the requirements,” as the scope management process generates the requirement management plan. The other options are incorrect because they are factual statements about the project scope management plan.
6 | 80 | Who creates the WBS? | The project manager alone | The upper management in the performing organisation | The customer | The project manager and with the help from the project team | 4 | 3A | 6 |  | m2-6 | The correct answer is “The project manager and with the help from the project team”. The project manager does not work alone to create the WBS as they might not have all necessary information to create the WBS. The other options, “The upper management in the performing organisation” and “The customer”, are wrong because they do not create the WBS.
6 | 81 | You have been assigned as a project manager on a research and development project for a new dental procedure. You are working in the Project Scope Management Knowledge Area. What is the purpose of the scope management plan? | The scope management plan describes and documents a scope baseline to help make future project decisions. | The scope management plan decomposes project deliverables into smaller units of work. | The scope management plan describes how project scope will be developed and how scope changes will be managed. | The scope management plan describes how cost and time estimates will be developed for project scope changes. | 3 | 3A | 6 |  | m2-6 | The correct answer is "The scope management plan describes how project scope will be developed and how scope changes will be managed" because the primary purpose of the scope management plan is to define the processes for creating, managing, and controlling the project scope, including handling any changes to it. The other options are incorrect because the scope baseline is a separate deliverable, not the purpose of the scope management plan; decomposing deliverables into smaller units is the purpose of the Work Breakdown Structure (WBS); and addressing cost and time estimates is handled in separate management plans, not the scope management plan.
6 | 82 | You are a project manager for an agricultural supply company. You have interviewed stakeholders and gathered requirements. Which of the following statements is true regarding the process to which this question refers? | The requirements document lists the requirements and describes how they will be analysed, documented, and managed throughout the project. | The requirements documentation consists of formal, complex documents that include elements such as the project's business need, functional and nonfunctional requirements, impacts on others inside and outside the organisation, and requirements assumptions and constraints. | The requirements documentation details the work required to create the project’s deliverables, including a description of the deliverables, product acceptance criteria, exclusions from requirements, and requirements assumptions and constraints. | The requirements traceability matrix ties requirements to project objectives, business needs, WBS deliverables, product design, test strategies, and high-level requirements and traces them to project completion. | 4 | 3A | 6 |  | m2-6 | The answer is “The requirements traceability matrix ties requirements to project objectives, business needs, WBS deliverables, product design, test strategies, and high-level requirements and traces them to project completion”. The traceability matrix links requirements to their origin and traces them throughout the project. The other options are incorrect as “The requirements document lists the requirements and describes how they will be analysed, documented, and managed throughout the project” describes the requirements management plan, not the requirements document. “The requirements documentation consists of formal, complex documents that include elements such as the project's business need, functional and non-functional requirements, impacts on others inside and outside the organisation, and requirements assumptions and constraints” is partially true except for the first statement. Requirements documents do not have to be formal or complex. Lastly, “The requirements documentation details the work required to create the project’s deliverables, including a description of the deliverables, product acceptance criteria, exclusions from requirements, and requirements assumptions and constraints” refers to the project scope statement, not the requirements.
6 | 83 | Which of the following is true regarding the project scope statement? | The project scope statement includes a change control system describing how to change the scope. | The project scope statement further elaborates the details of the Initiating and Planning processes and serves as a basis for future project decisions. | The project scope statement describes how the team defines and develops the work breakdown structure. | The project scope statement assesses the reliability of the project scope and describes the process for verifying and accepting completed deliverables. | 2 | 3A | 6 |  | m2-6 | The project scope statement further elaborates on the project deliverables and documents the product scope description, acceptance criteria, and project exclusions. It serves as a basis for future project decisions.
6 | 84 | Mary has created an activity list with her project team, including attributes for each activity. Which of the following is not an example of an activity attribute that Mary likely included? | Scope validation | Predecessor activities | Leads and lags | The geographic area where the work must take place | 1 | 3A | 6 |  | m2-6 | The correct answer is "scope validation" as it leads to acceptance decisions with the project customer, but it is not part of the activity attributes. The other options are wrong because they are all part of the activity attributes that Mary may include.
6 | 85 | You and the project team have created the work breakdown structure based on the project scope and requirements. Your next step is to generate the project’s activity list. Which one of the following will not be included in the activity list created with the project management team? | Activities that are not part of the project scope | Quality control activities | Activities to create the work packages | Physical terms, such as linear feet of pipe to be installed | 1 | 3A | 2 |  | m3A-2 | The answer is “activities that are not part of the project scope,” as the list must not include activities outside the scope. The other options are incorrect because these activities and terms are included in the activity list.
6 | 86 | What is the function of the WBS Dictionary? | It is used as a glossary to define the acronyms in the project scope statement. | It is used to plan the project resources. | It is used as a glossary to define the acronyms used in the project WBS. | It describes the details of each component in the project WBS. | 4 | 3A | 2 |  | m3A-2 | The WBS Dictionary describes work packages and their attributes, including any technical documentation for each WBS element. Therefore, the answer is "It describes the details of each component in the project WBS".
6 | 87 | Why is it important to document exclusions in the Project Scope Statement? | To simplify change management processes | To ensure clients are aware of project constraints | To prevent unnecessary work outside the project scope | To establish a baseline for resource allocation | 3 | 3A | 2 |  | m3A-2 | The correct answer is “To prevent unnecessary work outside the project scope” because documenting exclusions avoids ambiguity and ensures no work beyond the defined scope is undertaken. The other options are incorrect because change management and resource allocation are secondary to defining explicit exclusions, and project constraints are addressed elsewhere in project planning.
6 | 88 | What is a significant risk of unclear scope definition during the planning phase? | Accelerated project timelines | Increased likelihood of scope creep | Ineffective communication among stakeholders | Reduced resource utilisation | 2 | 3A | 2 |  | m3A-2 | The correct answer is “increased likelihood of scope creep” because unclear scope definition can lead to uncontrolled changes and added work, resulting in scope creep. The other options are incorrect because accelerated timelines and reduced resource utilisation are unlikely outcomes. Communication challenges may arise but it is not the primary risk.
6 | 89 | What is the primary purpose of a Requirements Traceability Matrix (RTM)? | To track stakeholder engagement during the project lifecycle | To document and trace the progress of each project requirement | To monitor changes in the project scope baseline | To evaluate alternative project management approaches | 2 | 3A | 2 |  | m3A-2 | “To document and trace the progress of each project requirement” is the correct answer because the RTM tracks requirements from origin to implementation, ensuring none are missed. The other options are incorrect because stakeholder engagement and scope baseline monitoring are unrelated to RTM, and evaluating management approaches is outside RTM’s scope.
6 | 90 | What is a key advantage of using a top-down approach to develop a WBS? | It simplifies cost estimation for work packages. | It leverages detailed knowledge of project components. | It ensures a logical breakdown of significant deliverables. | It reduces the need for stakeholder involvement. | 3 | 3A | 2 |  | m3A-2 | The correct answer is “It ensures a logical breakdown of significant deliverables” because the top-down approach starts with the most considerable deliverables and systematically breaks them into smaller components.​ The other options are incorrect because simplifying cost estimation and leveraging detailed knowledge are benefits of other WBS approaches, and reducing stakeholder involvement is neither a goal nor an advantage.
6 | 91 | While developing a Work Breakdown Structure (WBS) for a hospital kiosk project, the project team realised that one deliverable—touchscreen software—requires integration with biometric scanners. This dependency was not identified in earlier scope planning. How should the project manager address this situation? | Revise the requirements documentation to reflect the new dependency | Add a new activity in the schedule to address the integration | Update the scope baseline to include the integration requirements | Conduct a risk analysis and delay integration until a later phase | 1 | 3A | 2 |  | m3A-2 | The correct answer is “Revise the requirements documentation to reflect the new dependency” because dependencies must first be documented and reflected in the requirements before cascading changes to other elements like scope or schedule. The other options are incorrect because updating the scope baseline prematurely without adjusting requirements would lead to inconsistencies, adding a new activity without revisiting requirements disrupts the process hierarchy, delaying integration without a clear plan could create further complications later.
6 | 92 | A project manager is tasked with defining the scope of a highly innovative, iterative project where many requirements are unknown at the outset. What approach should the manager adopt to ensure effective scope definition? | Finalise the scope based on the initial project charter | Develop a comprehensive scope statement and strictly control changes | Focus on creating a detailed Work Breakdown Structure immediately | Use an adaptive approach to update the scope incrementally in each iteration | 4 | 3A | 2 |  | m3A-2 | The correct answer is “Use an adaptive approach to update the scope incrementally in each iteration.” Iterative or adaptive approaches are ideal for projects with evolving requirements, enabling scope updates during each iteration. The other options are incorrect because finalising the scope too early limits flexibility in an uncertain project, and strict change control contradicts the nature of iterative projects. While a detailed WBS is desirable but secondary to a flexible, evolving scope.
6 | 93 | Conflicting requirements emerge during a project's "Collect Requirements" phase with multiple stakeholders. Stakeholder A insists on a faster delivery timeline, while Stakeholder B prioritises cost control. What is the most effective tool or technique for resolving this conflict? | Use multi-criteria decision analysis to weigh priorities | Conduct a brainstorming session to gather alternative ideas | Escalate the issue to senior management for resolution | Perform a context diagram analysis to visualise stakeholder needs | 1 | 3A | 2 |  | m3A-2 | The correct answer is “Use multi-criteria decision analysis to weigh priorities” because multi-criteria decision analysis evaluates and prioritises conflicting requirements based on pre-defined criteria, leading to an informed resolution. The other options are incorrect because while brainstorming generates ideas, it may not resolve conflicts effectively. Escalating the issue prematurely undermines the project manager’s authority which can cause further disputes, and context diagrams only clarify relationships and do not address priority conflicts.
8 | 94 | You have created a cost estimate for a new project you will manage in your organisation. The following should be included in your cost estimate, except for which one? | Description of the scheduled activity’s project scope of work | Assumptions made | Constraints | Team members the project will utilise | 4 | 3B | 2 |  | m3A-2 | The team members that the project manager will utilise are not included in the cost estimate. The project manager will consist of the project scope of work, the assumptions made, and the constraints considered when creating a cost estimate, so the other options are incorrect.
8 | 95 | You are working with your project team to schedule activities for your construction project. You have scheduled the painting activity to be completed before the carpet installation activity may begin. Which one of the following can best describe the relationship between the painting activity and carpet installation activity? | Lag | Lead | Finish-to-start (FS) | Start-to-finish (SF) | 3 | 3B | 3 | a | m3A-3a | The painting activity must finish first, and then the carpet installation activity can begin. Therefore, the correct answer is “Finish-to-start”. Lag is incorrect because it describes the waiting time between project activities. Lead is incorrect because it describes a schedule compression technique that moves project activities closer together. Start-to-finish is a relationship between activities typically used in just-in-time scheduling, but that is not what is described in this scenario.
8 | 96 | You are the project manager of ABC Project. This project is similar to a project you completed a few months ago, and you would like to reference the older project for information. Which estimating technique uses a similar project to predict how long the current project will take to complete? | Analogous estimating | Parametric estimating | Organisational process assets | Bottom-up estimating | 1 | 3B | 3 | a | m3A-3a | The answer is “analogous estimating” as it uses an analogy between similar projects to determine the current project’s duration. Parametric estimating, use a parameter—such as 10 hours per unit installed—to predict the project duration. Organisational process assets is not a valid answer. Bottom-up estimating, accounts for every work package in the WBS and the total time for each deliverable. It is the most reliable time-estimating technique but also takes the longest to create.
8 | 97 | You are the project manager for a new technology implementation project. The management has requested that your estimates be as exact as possible. Which of the following methods of estimating will provide the most accurate estimate? | Top-down estimating | Top-down budgeting | Bottom-up estimating | Parametric estimating | 3 | 3B | 3 | a | m3A-3a | Bottom-up estimating takes the longest to complete all the estimating approaches, but it is also the most reliable approach. Thus, making it the correct answer. The other options are wrong. Top-down estimating is also known as analogous estimating, and it is not trustworthy. Top-down budgeting is not a valid term. Parametric estimating is an approach that predicts project costs based on a parameter, such as cost per hour, cost per unit, or cost per usage.
8 | 98 | You and your project team are about to enter a meeting to determine project costs. You have elected to use bottom-up estimating and will base your estimate on the WBS. Which one of the following is not an attribute of bottom-up estimating? | People doing the work create the estimates. | It creates a more accurate estimate. | It is more expensive to do than other methods. | It is less expensive to do than other methods. | 4 | 3B | 3 | a | m3A-3a | Bottom-up estimating is typically more expensive than other estimating approaches because of the time required to create this type of estimate. Therefore, the answer is “It is less expensive to do than other methods”. The other options are wrong as they are all accurate attributes of a bottom-up estimate.
8 | 99 | You can purchase gravel for your project at $437 per kilogram. You need four (4) kilograms of the gravel, so you predict your costs will be $1,748. Which cost-estimating approach is this an example of? | Parametric | Analogous | Bottom-up | Top-down | 1 | 3B | 3 | a | m3A-3a | This is a parametric approach. Analogous is incorrect because no other project cost estimate is being referenced. Bottom-up is not described in this instance because the WBS and each work package are not estimated for cost. Top-down estimating is another name for analogous so this option is wrong.
8 | 100 | You are the project manager of the Data Warehouse Project. You recently created the project network diagram and want to identify the critical path. Which one of the following best describes the critical path? | It is always one path with no float. | It determines the earliest the project can be finished. | It has the most activities. | It has the most essential project activities. | 2 | 3B | 3 | a | m3A-3a | The critical path reveals the earliest that a project may finish. This question tricks many project managers as they often think the critical path shows only the latest a project may finish. Remember that the forward pass shows a project's early and late finish. “It is always one path with no float” is incorrect because the project may have more than one critical path if two or more paths have the same duration, so it is not always just one path. “It has the most activities” is incorrect because the critical path may have fewer activities than other paths in the project but may still take longer to complete. “It has the most essential project activities” is incorrect because the critical path does not reflect the importance of its activities, just their duration.
8 | 101 | Mike, a project manager in your company, is falling behind on the project schedule. He has elected to crash the project. What is crashing? | Adding lag time between all project activities | Adding lead time between all project activities | Adding additional project resources to the project work | Removing all unneeded project deliverables | 3 | 3B | 3 | a | m3A-3a | Crashing occurs when a project manager adds resources to the work to compress the project schedule, which increases the project’s costs. Adding lag time between all project activities is incorrect because it would increase the project duration. Adding lead time between all project activities is wrong, as it is an example of fast-tracking. Removing all unneeded project deliverables is not a valid choice.
8 | 102 | Which of the following is not an output of the schedule control process? | Recommended corrective actions | Updates to the schedule baseline | Schedule variations | Work performance data | 4 | 3B | 3 | a | m3A-3a | Work performance data is the correct answer because it is an input to this process, not an output. The other options are incorrect because all these items could be part of the schedule control process's output.
8 | 103 | The project charter is an input to which schedule management process? | Define activities | Sequence activities | Plan schedule management | Schedule development | 3 | 3B | 3 | a | m3A-3a | Plan schedule management is the correct answer as it is an input to only one schedule management process. The other options are the incorrect answers because the project charter is an input to only one schedule management process, which is Plan Schedule Management.
8 | 104 | You know from a network diagram that Activity B cannot start until Activity A is finished. Which of the following is true? | Activities A and B have a start-to-finish dependency | Activities A and B have a finish-to-start dependency | Activity B has a mandatory dependency on Activity A | Activities A and B are on a critical path | 2 | 3B | 3 | b | m3A-3b | “Activities A and B have a finish-to-start dependency” is the correct answer because finish-to-start dependency means that the successor (B) activity cannot start until the predecessor (A) activity is finished. “Activities A and B have a start-to-finish dependency” is incorrect because the start-to-finish relationship means the successor activity cannot finish until the predecessor activity is started. “Activity B has a mandatory dependency on Activity A” is incorrect because we lack the information to say this dependency is mandatory. “Activities A and B are on a critical path” is incorrect because although there is a dependency between two activities, it does not mean they are on the critical path.
8 | 105 | All of the following statements describe the activity list except for which one? | The activity list is an output of the Define Activities process. | The activity list includes all project activities. | The activity list is an extension of and a component of the WBS. | The activity list includes an identifier and description of the activity. | 3 | 3B | 3 | b | m3A-3b | The activity list is an output of the Define Activities process and a component of the project schedule, not the WBS. It includes all the project activities, an identifier, and a description of each activity.
8 | 106 | You are the project manager for a video game. You have created a project schedule network diagram and updated the project documents, including the activity list, activity attributes, assumptions log, and milestone list. Which process have you just completed? | Define Activities process, which identifies all specific activities of the project | Sequence Activities process, which identifies all activity dependencies | Develop Schedule process, which illustrates project network time estimates | Estimate Activity Durations, which process calculates the duration of activities | 2 | 3B | 3 | b | m3A-3b | The Sequence Activities process produces project schedule network diagrams and project document updates, which include updating the activity list, activity attributes, assumption log, and milestone list. The purpose of this process is to identify all activity dependencies.
8 | 107 | You are the project manager for Design Your Web Site, Inc. Your company is designing the website for a national grocery store chain. You have your activity list and are ready to diagram the activity dependencies using the PDM technique. Which of the following statements is true? | PDM is also the AON diagramming method, and it uses a one-time estimate | PDM is also the AOA diagramming method and uses logical relationships. | PDM is also the ADM diagramming method, and its most common logical relationship is finish-to-start. | PDM is also the GERT method, allowing conditions, branches, and loops. | 1 | 3B | 3 | b | m3A-3b | The precedence diagramming method is also known as the activity on node (AON) diagramming method.
8 | 108 | Which logical relationship does the PDM use most often? | Start-to-finish | Start-to-start | Finish-to-finish | Finish-to-start | 4 | 3B | 3 | b | m3A-3b | The finish-to-start (FS) logical relationship is the most commonly used in PDM and the default relationship in most project management software packages.
8 | 109 | You are the project manager for Xylophone Phonics, a company that produces children’s software programs aimed at teaching essential reading and math skills. As you are currently performing cost estimates for your project and lack many details, which of the following techniques should you employ? | Analogous estimating techniques | Bottom-up estimating techniques | Monte Carlo analysis | Parametric modelling | 1 | 3B | 3 | c | m3A-3c | Analogous estimating is a form of expert judgment. Analogous estimating can be used to estimate cost or time and considers historical information from previous and similar projects.
8 | 110 | You are the project manager for Heartthrobs by the Numbers Dating Services. You are working on an updated website to showcase pictures and short bios of potential heartbreakers. You have your activity list and resource requirements ready and plan to use parametric estimates and reserve analysis to determine activity durations. Which of the following statements is true? | You are using inputs from the Estimate Activity Duration process. | You are using tools and techniques of the Estimate Cost process. | You are using tools and techniques of the Estimate Activity Durations process. | You are using inputs of the Estimate Costs process. | 3 | 3B | 3 | c | m3A-3c | The correct answer is "You are using tools and techniques of the Estimate Activity Durations process" because parametric estimates and reserve analysis are specific tools and techniques used in the Estimate Activity Durations process to determine how long project activities will take based on available data and assumptions. The other options are incorrect because inputs from the Estimate Activity Duration process refer to elements like activity lists and resource requirements but do not include tools and techniques; the Estimate Cost process involves cost estimations rather than activity durations; and inputs of the Estimate Costs process focus on cost data, not duration calculations.
8 | 111 | You have been hired as a contract project manager for Grapevine Vineyards. Grapevine wants you to design an internet wine club for its customers. One of the activities of this project is installing and testing several new servers. Based on experience, it takes approximately 16 hours per server to complete this task. Given that you are installing ten new servers, you estimate this activity will take a total of 160 hours. Which estimating techniques have you employed? | Parametric estimating | Analogous estimating | Bottom-up estimating | Reserve analysis | 1 | 3B | 3 | c | m3A-3c | Parametric estimating is the correct answer as it uses an algorithm or formula that multiplies a known element— such as the quantity of materials needed—by the time it takes to install or complete one unit. The result is a total estimate for the activity. In this case, 10 servers multiplied by 16 hours per server gives you a 160-hour total duration estimate.
8 | 112 | You want to improve your cost estimates by considering estimation uncertainty and risk. Which of the following tools and techniques will you use? | Analogous estimates | Three-point estimates | Parametric estimates | Bottom-up estimates | 2 | 3B | 3 | c | m3A-3c | Three-point estimating can improve activity cost estimates because they factor in estimation uncertainty and risk.
8 | 113 | You are a project manager for a trucking company. Your company specialises in moving household goods across the city or the country. Your project involves upgrading the company's nationwide computer network. Your lead engineer has given you the following estimates for a critical path activity: 60 days most likely, 72 days pessimistic, and 48 days optimistic. What is the weighted average or expected value? | 54 | 66 | 60 | 30 | 3 | 3B | 3 | c | m3A-3c | The calculation for PERT is the sum of optimistic time, pessimistic time, and four times the most likely time divided by 6. For this example, the calculation is as follows: [48 + 72 + (4 × 60)] / 6 = 60.
8 | 114 | Your project sponsor has requested a cost estimate for the project. She would like this estimate to be as accurate as possible, as this may be her only opportunity to secure the budget due to recent cuts in special projects. You decide to use _____________. | Analogous estimating techniques | Bottom-up estimating techniques | Top-down estimating techniques | Expert judgment techniques | 2 | 3B | 3 | c | m3A-3c | Bottom-up techniques are the most time-consuming and generally the most accurate estimates. With bottom-up estimating, each work item is estimated and rolled up to a project total.
8 | 115 | Amy, your project sponsor, has requested a cost estimate for the project you are currently working on. This project is similar in scope to the one you completed last year. She would like to receive the cost estimates as soon as possible. Accuracy is not her main concern now; she needs a rough estimate by tomorrow. You decide to use __________. | Analogous estimating techniques | Bottom-up estimating techniques | Parametric estimating techniques | Three-point estimating techniques | 1 | 3B | 3 | d | m3A-3d | Analogous—or top-down—estimating techniques are a form of expert judgment. Because this project is similar to another recent project, you can use the cost estimates from the previous project to help you quickly determine estimates for the current project.
8 | 116 | You are a project manager at a trucking company responsible for calculating the anticipated time to implement a new GPS tracking system across your fleet. The lead engineer provides the following estimates: 15 days optimistically, 21 days most likely, and 30 days pessimistically. What is the expected duration based on PERT? | 20 | 22 | 18 | 21 | 1 | 3B | 3 | d | m3A-3d | The correct answer is 20 days. [(15 + 4 x 21 + 30) / 6 = 20]
8 | 117 | Your project involves replacing your trucking company’s communication software. The task of configuring user accounts has the following time estimates: 3 days optimistic, 8 days pessimistic, and 5 days most likely. What is the PERT estimate for completing this task? | 5.3 | 5.2 | 2.7 | 5 | 2 | 3B | 3 | d | m3A-3d | The correct answer is 5.2 days. [(3 + 4 x 5 + 8) / 6 = 5.166667 = 5.2 (round off)]
8 | 118 | A key task in your project involves upgrading the servers at your regional hubs. Your IT team estimates that this task will take 10 days at best (optimistic), 20 days at worst (pessimistic), and 14 days under normal conditions (most likely). Calculate the PERT expected duration. | 7.3 | 14.7 | 14.3 | 14 | 3 | 3B | 3 | d | m3A-3d | The correct answer is 15 days. [(10 + 4 x 14 + 20) / 6 = 14.333 = 14.3 (round off)]
8 | 119 | Which of the following compression techniques increases risk? | Crashing | Resource levelling | Fast-tracking | Lead and lag | 3 | 3B | 3 | d | m3A-3d | Fast-tracking is a compression technique that increases risk and potentially causes rework. It involves performing two activities previously scheduled to start simultaneously.
8 | 120 | In an industrial project, the installation of equipment can start 15 days after the foundation is completed. What type of dependency is this? | Start-to-finish with a 15-day lead | Finish-to-start with a 15-day lag | Finish-to-start with a 15-day lead | Finish-to-finish with a 15-day lag | 2 | 3B | 3 | d | m3A-3d | The dependency between the two activities is a Finish-to-Start (FS) type because the second activity can start only after completing the first activity. There is also a 15-day time lag before the second activity can start.
8 | 121 | In a construction project, painting of the walls must finish 5 days before the final inspection can begin. What type of dependency is this? | Start-to-finish with a 5-day lead | Finish-to-start with a 5-day lead | Finish-to-finish with a 5-day lead | Start-to-start with a 5-day lag | 3 | 3B | 3 | d | m3A-3d | The dependency between the two activities is a Finish-to-Finish (FF) type because the painting must finish before the final inspection can start. The 5-day lead allows the final inspection to start sooner, relative to the painting completion.
8 | 122 | In a software development project, the final testing phase can only start 10 days after the coding phase is completed. What type of dependency is this? | Finish-to-start with a 10-day lag | Finish-to-finish with a 10-day lag | Start-to-start with a 10-day lag | Finish-to-start with a 10-day lead | 1 | 3B | 2 | a | m3B-2a | The dependency between the two activities is a Finish-to-Start (FS) type because the testing phase can only begin after the coding phase is completed. The 10-day lag specifies the waiting period before the second activity can start.
8 | 123 | Most project management software applications use the _______ method to build the project schedule network diagram. | Leads and Lags | Critical Diagramming | Activity-On-Arrows Diagramming | Precedence Diagramming | 4 | 3B | 2 | a | m3B-2a | Most project management and project planning software uses the Precedence Diagramming Method (PDM), also known as Activity-On-Node (AON).
8 | 124 | You have recently been assigned as the manager of a highly critical national project that should be completed in a very short period compared to similar projects. After developing the first draft of the project network diagram, you see that the project cannot be completed on time. What would be the best approach if the network diagram could not be changed anymore and you had extra human resources? | Fast-tracking | Crashing | Risk analysis | Levelling the resources | 2 | 3B | 2 | a | m3B-2a | Levelling the resources will generally increase the duration. Since the network diagram cannot be changed, the fast-tracking option is also not feasible. So crashing remains the best option in this situation to decrease the duration.
8 | 125 | A project manager has increased the project costs by $200,000, but he completed the project 4 weeks earlier than planned. What activity is best described in this situation? | Critical path method | Resource levelling | Budgeting | Schedule compression | 4 | 3B | 2 | a | m3B-2a | Schedule compression shortens the project's duration by assigning more budget or resources.
8 | 126 | In a manufacturing project, the assembly of components can only start 7 days after the parts procurement is completed. What type of dependency is this? | Finish-to-start with a 7-day lag | Start-to-start with a 7-day lag | Finish-to-finish with a 7-day lead | Finish-to-start with a 7-day lead | 1 | 3B | 2 | a | m3B-2a | The dependency between the two activities is a Finish-to-Start (FS) type because the assembly cannot begin until the parts procurement is finished. The 7-day lag indicates a delay before the second activity can start.
8 | 127 | You are managing a warehouse relocation project. One critical path activity, the setup of automated shelving, has the following time estimates: 20 days optimistic, 25 days most likely, and 40 days pessimistic. What is the expected duration of this activity? | 30 | 28 | 25 | 35 | 2 | 3B | 2 | a | m3B-2a | The correct answer is 28 days. [(20 + 4 x 25 + 40) / 6 = 28]
8 | 128 | You are supervising the construction of a logistics hub. A task on the critical path involves laying concrete for the main foundation. The time estimates are as follows: 8 days optimistic, 12 days most likely, and 16 days pessimistic. What is the PERT estimate for this activity? | 10 | 14 | 12 | 8 | 3 | 3B | 2 | a | m3B-2a | The correct answer is 28 days. [8 + 4 x 12 + 16) / 6 = 12]
10 | 129 | A project team is planning cost management. They want to ensure consistency in rounding numbers and setting acceptable percentage deviations. Which section of the cost management plan would address this requirement? | Units of measure | Level of precision | Level of accuracy | Organisational procedure links | 2 | 3B | 2 | b | m3B-2b | The correct answer is "Level of precision" because it focuses on guidelines for rounding numbers. The other options are incorrect because "Units of measure" deals with defining measurement units, "Level of accuracy" sets the acceptable percentage deviation, and "Organisational procedure links" focuses on aligning cost management with broader organisational procedures.
10 | 130 | During cost estimation, a project team utilises historical data from similar projects to estimate the costs for their current project. Which estimation method are they using? | Bottom-up estimating | Analogous estimating | Parametric estimating | Expert judgment | 2 | 3B | 2 | b | m3B-2b | The correct answer is "Analogous estimating" because it relies on historical data from similar projects. The other options are incorrect: "Bottom-up estimating" involves detailed aggregation, "Parametric estimating" employs mathematical models, and "Expert judgment" utilises practitioners' insights without directly referencing historical data.
10 | 131 | A construction project faces unexpected subsurface conditions and regulatory delays, leading to increased costs. Which budget component would assist in managing such unforeseen risks? | Cost baseline | Work package cost estimates | Management reserve | Contingency reserve | 4 | 3B | 2 | b | m3B-2b | The correct answer is "Contingency reserve" because it is allocated for identified risks or known unknowns. The other options are wrong because "Cost baseline" excludes reserves, "Management reserve" is for unforeseen changes outside the contingency scope, and "Work package cost estimates" are detailed costs for specific WBS components.
10 | 132 | What is the primary purpose of a cost baseline in project management? | To measure and monitor cost performance | To allocate resources | To document funding requirements | To manage changes to the budget | 1 | 3B | 2 | b | m3B-2b | The correct answer is "To measure and monitor cost performance" because the cost baseline tracks deviations and controls costs. The other options are wrong because "To allocate resources" relates to resource management, "To document funding requirements" focuses on financial flow, and "To manage changes to the budget" refers to change control processes.
10 | 133 | A project team must balance the cost estimation process of a small project while utilising limited activities. Which approach would be most suitable? | Bottom-up estimating | Analogous estimating | Parametric estimating | Three-point estimating | 1 | 3B | 2 | b | m3B-2b | The correct answer is "Bottom-up estimating" because it is feasible and detailed for small projects. The other options are wrong because "Analogous estimating" is less precise, "Parametric estimating" requires extensive databases, and "Three-point estimating" involves probability scenarios that might not fit the small project's simplicity.
10 | 134 | During cost management planning, which tool ensures that cost reporting is consistent and timely? | Control thresholds | Reporting formats and frequency | Rules of performance measurement | Additional cost activities | 2 | 3B | 2 | b | m3B-2b | The correct answer is "Reporting formats and frequency" because it specifies how and when cost reports are shared. The other options are wrong because "Control thresholds" relate to deviations, "Rules of performance measurement" deal with progress tracking, and "Additional cost activities" include broader details that are not specific to reporting.
10 | 135 | What is the role of reserve analysis in the determined budget process? | To estimate activity costs | To set aside buffers for potential cost overruns | To reconcile funding limits | To aggregate cost estimates | 2 | 3B | 2 | c | m3B-2c | The correct answer is "To set aside buffers for potential cost overruns" because reserve analysis focuses on establishing contingencies. The other options are incorrect because "To estimate activity costs" involves cost estimation, "To reconcile funding limits" is part of funding limit reconciliation, and "To aggregate cost estimates" sums costs but does not set reserves.
10 | 136 | A cost management plan specifies the use of staff hours as the measurement unit and accounts for inflation in currency calculations. Which section of the plan does this relate to? | Level of precision | Cost budgeting | Units of measure | Rules of performance measurement | 3 | 3B | 2 | c | m3B-2c | The correct answer is "Units of measure" because it defines staff hours and currency details. The other options are wrong because "Level of precision" relates to rounding, "Cost budgeting" outlines allocation, and "Rules of performance measurement" relate to earned value management.
10 | 137 | A project manager uses an S-curve to monitor the relationship between expenditure and the approved budget. What does the curve primarily signify? | Funding requirements | Expenditure tracking | Cost baseline | Management reserves | 3 | 3B | 2 | c | m3B-2c | The correct answer is "Cost baseline" because it visualises the approved project costs over time. The other options are wrong because "Funding requirements" reflect financial flow, "Expenditure tracking" relates to actual cost monitoring, and "Management reserves" are discretionary funds outside the baseline.
10 | 138 | Which key input to the determined budget process ensures that risks are considered when establishing the budget? | Project schedule baseline | Scope baseline | Cost management plan | Risk register | 4 | 3B | 2 | c | m3B-2c | The correct answer is "Risk register" as it assists in evaluating and incorporating risks into the budget. The other options are incorrect because "Project schedule baseline" focuses on timing, "Scope baseline" provides deliverables, and "Cost management plan" delineates overall cost guidelines.
10 | 139 | This document establishes the criteria for planning, estimating, budgeting, and controlling costs. What is this document called? | The cost baseline is an output of the Determine Budget process. The cost baseline is based on the approved project charter, scope, schedule, resources, and human resource management plan to manage project costs. | The performance management baseline is an output of the Plan Cost Management process. It is based on the project scope, schedule, resources, and human resource management plan to manage project costs. | The project funding requirements are an output of the Determine Budget process. Funding is based on the project scope, schedule, resources, and other information used to manage project costs. | The cost management plan is an output of the Plan Cost Management process. The cost management plan is based on the approved project charter, schedule, and risk management plan to manage project costs. | 4 | 3B | 2 | c | m3B-2c | The correct answer is the cost management plan, which is an output of the Plan Cost Management process and establishes the criteria for planning, estimating, budgeting, and controlling costs. It is based on the approved project charter, project schedule, risk management plan, and other information required to manage project costs.
10 | 140 | You are working on a project to upgrade the phone system in your customer service centre. You have considered using analogous, parametric, bottom-up, and three-point estimating to determine activity costs. Which process does this describe? | Estimating activity resources | Estimate costs | Determine budget | Estimating activity costs | 2 | 3B | 2 | c | m3B-2c | Estimate costs involve estimating activity costs using some of the tools and techniques listed in the question. The remaining tools and techniques are expert judgment, data analysis, project management information systems, and group decision-making.
10 | 141 | You are the project manager for a custom home-building construction company. You are working on the model home project for the upcoming Show Homes Tour. The model home includes smart home connections, talking appliances, and wiring for home theatres. You are working on the cost baseline for this project. All of the following statements are true except for which one? | This process aggregates the estimated costs of project activities. | The cost baseline will be used to measure variances and future project performance. | This process assigns cost estimates for expected future period operating costs. | The cost baseline is the time-phased budget at completion of the project. | 3 | 3B | 2 | d | m3B-2d | Future period operating costs are considered ongoing costs and are not part of project costs.
10 | 142 | Which estimation technique is most suitable when a detailed project design is unavailable but statistical data is accessible? | Bottom-up estimating | Analogous estimating | Parametric estimating | Three-point estimating | 3 | 3B | 2 | d | m3B-2d | The correct answer is "Parametric estimating" because it uses statistical data and mathematical models when detailed design is not available. The other options are incorrect as they either require detailed designs or rely on different methods of approximation.
10 | 143 | What is the purpose of a contingency reserve in a project budget? | To manage unforeseen changes | To adjust funding requirements | To handle identified risks | To fund discretionary activities | 3 | 3B | 2 | d | m3B-2d | The correct answer is "To handle identified risks" because contingency reserves are specifically for known unknowns. Other options are incorrect as they address different aspects of budgeting and funding.
10 | 144 | A project team aims to compare current cost performance with planned costs. Which tool should they utilise? | S-curve | Earned value analysis | Reserve analysis | Funding reconciliation | 2 | 3B | 2 | d | m3B-2d | The correct answer is "Earned value analysis" as it helps compare planned costs with actual performance. Other options either focus on visualisation, reserves, or funding alignment.
10 | 145 | Which of the following is not part of a cost baseline? | Activity cost estimates | Contingency reserves | Management reserves | Work package costs | 3 | 3B | 2 | d | m3B-2d | The correct answer is "Management reserves" because they are excluded from the cost baseline. Other options are components of the baseline.
10 | 146 | During budget determination, which activity involves reconciling expenditure with funding limits? | Funding limit reconciliation | Cost aggregation | Reserve analysis | Historical information analysis | 1 | 3B | 2 | d | m3B-2d | The correct answer is "Funding limit reconciliation" because it aligns expenditures with funding constraints. Other options address different aspects of cost determination.
10 | 147 | What role does the "cost of quality" play in cost estimation? | Ensures quality compliance in resource allocation | Estimates costs for rework and quality standards | Calculates costs for duration estimation | Manages vendor and supplier costs | 2 | 3B | 2 | d | m3B-2d | The correct answer is "Estimates costs for rework and quality standards" as it accounts for maintaining quality. Other options address different objectives.
10 | 148 | A project team uses expert judgment for cost estimation. Which of the following describes this technique? | Estimates based on statistical models | Identifying risks and buffers | Cost aggregation at work package level | Predictions from experienced professionals | 4 | 3B | 2 | d | m3B-2d | The correct answer is "Predictions from experienced professionals" because expert judgment involves insights from qualified individuals. Other options are unrelated.
10 | 149 | Which cost estimation approach aggregates costs from the lowest-level components of the WBS? | Analogous estimating | Parametric estimating | Bottom-up estimating | Data analysis | 3 | 3B | 2 | d | m3B-2d | The correct answer is "Bottom-up estimating" because it starts at the lowest WBS level and aggregates costs upwards. Other options use different methodologies.
10 | 150 | What is a primary difference between contingency reserves and management reserves? | Contingency reserves are for known unknowns, while management reserves are for unknown unknowns. | Management reserves are part of the cost baseline. | Contingency reserves are discretionary. | Management reserves address identified risks. | 3 | 3B | 2 | e | m3B-2e | The correct answer is "Contingency reserves are for known unknowns, while management reserves are for unknown unknowns." Other options incorrectly describe their roles.
12 | 151 | Management has requested that you define the correlation between quality and the project scope. Which of the following is the most appropriate answer? | The project scope includes metrics for quality. | Quality metrics are applied to the project scope. | Quality is the process of completing the scope to meet stated or implied needs. | Quality is the process of evaluating the project scope to ensure that quality exists. | 3 | 3C | 2 | e | m3B-2e | Quality, about the project scope, is about completing the work to provide the stated or implied needs, as promised. “The project scope includes metrics for quality” is incorrect because, although the project scope will have requirements for acceptance, it may not have metrics for quality defined. The other options are incorrect statements.
12 | 152 | The quality management plan outlines how the project team will implement the quality policy. It should cover at least all of the following, except for which one? | The resources needed to carry out the quality plan | The quality metrics and tolerances and what will be measured | The responsibilities the project team has in implementing quality | The processes to use to satisfy quality requirements | 2 | 3C | 2 | e | m3B-2e | Quality metrics are an output of the Plan Quality Management process and not part of the quality management plan.
12 | 153 | During the execution of the project, as the project manager, you realise that a new quality standard has been adopted by your company. Your project team will meet with the company quality department to discuss how the new standard will impact your project. Which quality process is this a part of? | Plan Quality Management | Manage Quality | Control Quality | Quality Update | 1 | 3C | 2 | e | m3B-2e | Even though it is occurring during the execution of the project, determining what standards to use is part of quality planning. Sometimes during the project execution or other phases we need to refer back to planning because planning is an iterative process. In planning, we determine what quality standards are applicable to the project and how to implement and control them. ‘Quality Update’ is a made-up term and does not represent any of the quality management processes.
12 | 154 | What is the primary focus of a quality metric like "on-time completion percentage"? | Resource optimisation | Timely project delivery | Stakeholder satisfaction | Process efficiency | 2 | 3C | 2 | e | m3B-2e | The correct answer is "Timely project delivery" because it measures adherence to schedules. The other options are wrong because "Resource optimisation" reduces waste, "Stakeholder satisfaction" assesses feedback, and "Process efficiency" focuses on workflows.
12 | 155 | Which principle of quality management focuses on making decisions using reliable project data and information? | Leadership | Process approach | Evidence-based decision making | Relationship management | 3 | 3C | 2 | e | m3B-2e | The correct answer is "Evidence-based decision making" because it emphasises decisions based on data. The other options are wrong because "Leadership" provides direction, "Process approach" manages interconnected processes, and "Relationship management" builds stakeholder trust.
12 | 156 | Which tool in quality management involves comparing a project's quality performance with best practices or standards? | Flowcharts | Benchmarking | Cost-benefit analysis | Logical data model | 2 | 3C | 2 | e | m3B-2e | The correct answer is "Benchmarking" because it compares performance against standards. The other options are wrong because "Flowcharts" illustrate processes, "Cost-benefit analysis" assesses costs versus benefits, and "Logical data model" structures data relationships.
12 | 157 | A construction company wants to reduce unused materials on-site. Which quality metric should they monitor? | Material waste percentage | Change order rate | Subcontractor quality performance | On-time completion percentage | 1 | 3C | 2 | e | m3B-2e | The correct answer is "Material waste percentage" because it calculates unused materials. The other options are wrong because "Change order rate" tracks project changes, "Subcontractor quality performance" assesses subcontractors, and "On-time completion percentage" measures schedule adherence.
12 | 158 | A project deliverable does not meet its intended purpose despite adhering to the specifications. Which quality management principle has likely not been fully addressed? | Leadership | Customer focus | Engagement of people | Process approach | 2 | 3C | 2 | f | m3B-2f | The correct answer is "Customer focus" because meeting the customer's intended use is crucial. The other options are wrong because "Leadership" guides the project, "Engagement of people" involves team participation, and "Process approach" focuses on process interconnections.
12 | 159 | In quality planning, what is the key difference between quality assurance and quality control? | Quality assurance is reactive, and quality control is proactive. | Quality assurance ensures customer satisfaction, and quality control prevents defects. | Quality assurance is proactive, and quality control is reactive. | Quality assurance addresses processes, and quality control focuses on deliverables. | 3 | 3C | 2 | f | m3B-2f | The correct answer is "Quality assurance is proactive, and quality control is reactive" because quality assurance prevents issues, while quality control addresses them after detection. The other options are wrong because they misrepresent the nature or focus of assurance and control.
12 | 160 | A client evaluates a project deliverable based on its usability rather than its specifications. Which concept does this illustrate? | Process approach | Continuous improvement | Quality assurance | Fitness for use | 4 | 3C | 2 | f | m3B-2f | The correct answer is "Fitness for use" because it refers to suitability for its intended purpose. The other options are wrong because "Process approach" involves managing processes, "Quality assurance" ensures adherence to standards, and "Continuous improvement" enhances performance.
12 | 161 | A project team is planning quality management. Which document defines the roles and responsibilities concerning quality management in a project? | Quality management plan | Scope baseline | Requirements traceability matrix | Risk management plan | 1 | 3C | 2 | f | m3B-2f | The correct answer is "Quality management plan" because it includes roles and responsibilities for quality management. The other options are wrong because "Scope baseline" defines deliverables, "Requirements traceability matrix" tracks requirements, and "Risk management plan" addresses risks.
15 | 162 | In a RACI chart, each task may have multiple ____ entries. | R, C, or I | A, R, or I | A, C, or R | A, C, or I | 1 | 3C | 2 | f | m3B-2f | In a RACI chart, each task may have multiple roles marked as Responsible (R), Consulted (C), or Informed (I), but only one role marked as Accountable (A). This ensures clear accountability while allowing collaboration and communication. The other options are incorrect because they suggest that the accountable role can be one of multiple roles for a task. This contradicts the principle that only one person can be accountable to avoid confusion and ensure clear responsibility.
15 | 163 | Why is it important to regularly update resource estimates throughout a project? | To ensure project resource needs are not too complex | To ensure resource availability aligns with project needs | To ensure the resource availability is within the project scope | To ensure project schedule is on track with the resource acquiring plan | 2 | 3C | 2 | f | m3B-2f | Regularly updating resource allocation ensures that resource availability aligns with project needs. This helps manage workloads, avoid resource overuse or underuse, and ensure the project progresses smoothly. Complexity is managed through proper planning, not just updating estimates. Scope defines the work; resource availability must align with needs, not just scope. While ensuring the project schedule is on track with the resource-acquiring plan is essential, this is a secondary benefit; the main goal is aligning resource availability with needs.
15 | 164 | You are managing a commercial building project, and during a team meeting, you need to determine the most suitable method to estimate the resources required for the project activities. The project includes tasks that are similar to previous projects your organisation has completed successfully. Which estimation method would be most effective in this situation? | Analogous estimating | Parametric estimating | Bottom-up estimating | Three-point estimating | 1 | 3C | 2 | f | m3B-2f | Analogous estimating is most effective in this situation because it involves using historical data from similar previous projects to estimate the resources required. This method is particularly useful when detailed information is not yet available. Parametric estimating uses statistical relationships and is more suitable when there is quantitative data. Bottom-up estimating involves detailed estimation at the task level, which can be time-consuming, and three-point estimating, while useful for uncertainty, is not specifically about leveraging historical data from similar projects.
15 | 165 | Which resource management tool provides insights into resource demand over time for each resource type? | Responsibility assignment matrix | RACI chart | Resource histogram | Organisational chart | 3 | 3C | 2 | f | m3B-2f | A resource histogram is a tool that provides insight into the availability and allocation of resources over time. It visually represents when resources are scheduled to work on a project, helping to identify periods of resource overuse or underuse. The responsibility assignment matrix is incorrect because it assigns project roles and responsibilities, not to track resource availability over time. The RACI chart is incorrect because it outlines roles and responsibilities but does not provide a timeline for resource allocation. An organisational chart is incorrect because it shows the structure of an organisation but does not provide information on resource allocation or availability over time.
15 | 166 | What is the primary purpose of resource levelling in project management? | To extend the project schedule | To ensure resource overloads are minimised | To prioritise project activities | To increase the number of available resources | 2 | 3C | 2 | f | m3B-2f | The primary purpose of resource levelling in project management is to ensure resource overloads are minimised. This involves adjusting the project schedule or resource assignments to prevent over-allocation and ensuring that no resource is overburdened. Extending the project schedule is incorrect because while resource levelling may extend the schedule, its primary goal is to balance resource allocation. To prioritise project activities is incorrect because prioritising activities is a part of scope and time management, not specifically resource levelling. Increasing the number of available resources is incorrect because resource levelling optimises existing resources rather than increasing them.
15 | 167 | A ______ describes when and how people will be added to and taken off a project. | project organisational chart | resource histogram | responsibility assignment matrix | staffing management plan | 4 | 3C | 2 | f | m3B-2f | A staffing management plan describes when and how people will be added to and removed from a project. It includes details on staff acquisition, resource calendars, staff release plans, and training needs. The project organisational chart is incorrect because an organisational chart shows team structure and hierarchy, not staffing timelines. Resource histogram is incorrect because it displays resource allocation over time but does not specify staffing processes. The responsibility assignment matrix is incorrect because it outlines roles and responsibilities for tasks, not the staffing schedule.
15 | 168 | What does the resource smoothing technique aim to achieve? | Minimise resource overloads while extending the schedule | Balance resource allocation without affecting the project timeline | Focus on assigning tasks directly to individuals | Prioritise tasks and resources based on project dependencies | 2 | 3C | 2 | g | m3B-2g | The resource smoothing technique balances resource allocation without affecting the project schedule. It involves adjusting activities within their float to ensure a consistent workload without changing the project’s duration. Minimising resource overloads while extending the project schedule is incorrect because extending the project schedule is related to resource levelling, not smoothing. Focus on assigning tasks directly to individuals is incorrect because resource smoothing deals with overall resource allocation, not individual task assignments. Prioritising tasks and resources based on project criticality is incorrect because this pertains to project prioritisation and critical path analysis, not specifically to resource smoothing.
15 | 169 | A project ____ chart is a graphic representation of how authority and responsibility are distributed within the project. | organisational | planning | stakeholder | management | 1 | 3C | 2 | g | m3B-2g | A project organisational chart is a graphic representation of the hierarchy within an organisation or project. It outlines the roles and relationships between the team members. Planning is incorrect because a planning chart would focus on project timelines and schedules. Stakeholder is incorrect because a stakeholder chart typically lists stakeholders and their influence or interest in the project. Management is incorrect because management charts generally refer to management processes or workflows.
15 | 170 | You are the project manager for AA Tops, a nationwide toy store chain. Your new project involves creating a prototype display at several stores nationwide. You will use a RACI chart to display individuals and activities. What does RACI stand for? | Responsible, accountable, consult, inform | Responsible, assignment, control, inform | Resource, activity, control, identify | Resource, accountable, consult, identify | 1 | 3C | 2 | g | m3B-2g | RACI is a commonly used acronym in resource management to describe responsibilities. It stands for Responsible, Accountable, Consulted, and Informed, which are the key roles assigned to tasks in a project.
15 | 171 | Which of the following is not an input for the estimated activity resources process? | Project schedule | Resource management plan | Cost estimates | Activity attributes | 1 | 3C | 2 | g | m3B-2g | The project schedule is not an input for the Plan Resource Management process. Instead, it is developed after planning resource management to align resources with the project timeline.
15 | 172 | You are managing a construction project for a new corporate headquarters. The electrical and plumbing teams are needed simultaneously, but not enough workers are available to meet the demand. As a project manager, which strategy is the most suitable for the situation? | Delay both activities and accept the project delay | Implement resource smoothing | Hire additional temporary workers to fill the gap | Reduce the scope of work for both teams | 2 | 3C | 2 | g | m3B-2g | Resource smoothing is the best strategy to address overallocation without extending the project timeline. Resource smoothing involves adjusting non-critical tasks to ensure a balanced workload, allowing the project to continue on schedule without overburdening team members. This approach is crucial in maintaining efficiency and preventing delays. The other options are incorrect, as delaying both activities and accepting the project delay have undesirable effects on the project. Hiring additional temporary workers increases the project budget, and reducing the scope of work could compromise the quality of the project.
15 | 173 | As your construction project progresses, you observe that some team members are underutilised while others are overburdened. How would you address this imbalance and improve resource allocation? | Create a new project schedule | Analyse the resource histogram | Hire additional staff to support overburdened team members | Adjust the project budget to accommodate changes | 2 | 3C | 2 | g | m3B-2g | Analysing the resource histogram to identify peaks and valleys in resource allocation is the best strategy to address the imbalance and improve resource utilisation. By examining the histogram, the project manager can pinpoint periods of overuse and underuse of resources and reassign tasks accordingly to balance the workload. This method ensures that all team members are effectively utilised and prevents burnout. The other options are incorrect, as creating a new project schedule does not directly address the issue of workload imbalance, hiring additional staff does not solve the underlying allocation issue, and adjusting the budget does not address the imbalance in resource distribution.
15 | 174 | As a project manager for a large construction project involving the development of a new commercial complex, you have encountered significant delays due to confusion about team responsibilities. Multiple teams, including architects, engineers, and construction workers, are involved, and there is a need to clearly define each team member’s responsibilities to improve coordination and efficiency. Which project management tool should you implement to address the issue of responsibility confusion and improve team coordination? | Project charter | Resource histogram | Responsibility assignment matrix (RAM) | Work breakdown structure (WBS) | 3 | 3C | 2 | g | m3B-2g | The Responsibility Assignment Matrix (RAM) is the best tool to use because it clearly defines the roles and responsibilities of each team member concerning specific project tasks. Unlike the project charter, which provides a high-level overview of the project, or the resource histogram, which shows resource allocation over time, the RAM ensures that everyone knows their duties, reducing confusion and improving coordination. The Work Breakdown Structure (WBS) breaks the project into manageable sections. Still, it does not assign responsibilities, making the RAM the most suitable choice for addressing the issue of unclear responsibilities among team members.
15 | 175 | You are overseeing the construction of a new hospital. The project is experiencing frequent team reassignments, leading to inefficiencies and delays. To minimise these issues, you need a detailed plan that addresses the acquisition, management, and reassignment of team members. Which component of the resource management plan can help address the issue of frequent team member reassignments? | Project charter | Staffing management plan | Communications management plan | Quality management plan | 2 | 3C | 2 | h | m3B-2h | The Staffing Management Plan is essential because it provides detailed information on how team members will be acquired, developed, managed, and reassigned throughout the project. Unlike the project charter, which outlines the project’s objectives, or the communications and quality management plans, which focus on communication strategies and maintaining quality standards, the staffing management plan ensures that team members are effectively managed and utilised. This helps minimise disruptions caused by frequent reassignments, ensuring smooth transitions and the project progresses efficiently.
15 | 176 | While planning a bridge construction project, you must decide how to acquire necessary resources such as skilled labour and specialised equipment. You are considering various options, including outsourcing some of the work to external contractors. Which aspect of the resource management process should you focus on to make an informed decision about outsourcing? | Develop project charter | Identify risks | Perform alternative analysis | Create quality management plan | 3 | 3C | 2 | h | m3B-2h | Performing alternative analysis is crucial because it involves evaluating different resource acquisition options, such as outsourcing versus internal hiring. This analysis helps make informed decisions about the most cost-effective and efficient method of obtaining the necessary resources. Developing the project charter, identifying risks, and creating a quality management plan are also essential, but they do not specifically address the decision-making process for resource acquisition.
15 | 177 | You are tasked with managing a high-rise construction project and must create a comprehensive resource breakdown structure (RBS) that includes human resources, equipment, materials, and subcontractors. This will help you organise and manage resources effectively throughout the project. What should be the primary purpose of the resource breakdown structure in your project? | To define the project scope | To identify the project deliverables | To organise resources hierarchically | To establish communication protocols | 3 | 3C | 2 | h | m3B-2h | The primary purpose of the resource breakdown structure (RBS) is to organise the project’s resources hierarchically, providing a structured framework for identifying and managing the necessary resources, including human resources, equipment, materials, and subcontractors. This helps ensure that all resources are accounted for and allocated efficiently. The other options are incorrect as defining the project scope, identifying project deliverables, and establishing communication protocols are essential aspects of project management but are not the primary purposes of the RBS.
15 | 178 | You are the project manager of the PLN Project. You use a RACI chart to organise roles and responsibilities for project assignments. In a RACI chart, what is the maximum number of people accountable for an assignment? | One | Two | Two, if one of the two people is also responsible | As many people that are on the project team | 1 | 3C | 2 | h | m3B-2h | In a RACI chart, “responsible, accountable, consulted, and informed" means only one person is accountable. The other options are incorrect, as they enable more than one person to be accountable.
15 | 179 | Which of the following processes will you perform first? | Estimate Activity Resources | Determine Budget | Estimate Costs | Develop Schedule | 1 | 3C | 2 | h | m3B-2h | “Estimate Activity Resources” is the correct answer, and the other answers are incorrect because the activity source needs to be known before you can estimate the activity duration to schedule. Resources and schedules need to be known for estimating costs and determining the budget.
15 | 180 | You are the project manager for Hello There, a company that produces software programs for children designed to teach essential reading skills. You are now prepared to assign project roles, responsibilities, and reporting relationships. Which project planning process are you currently engaged in? | Estimate Activity Resources | Plan Resource Management | Acquire Resources | Plan organisational Resources | 2 | 3C | 2 | h | m3B-2h | The Plan Resource Management process identifies project resources, documents roles and responsibilities of project team members, and documents reporting relationships.
15 | 181 | All of the following statements about the Plan Resource Management process are true, except for which one? | The Plan Resource Management process involves determining roles and responsibilities. | The Plan Resource Management output includes project organisation charts showing the project’s reporting relationships. | The resource management plan created in this process describes how and when resources will be acquired and released. | The RACI chart is an output of this process that allows you to see all the people assigned to an activity. | 4 | 3C | 2 | h | m3B-2h | The RACI chart is part of the data representation tool and technique used in this process.
18 | 182 | Achieving an average course evaluation of at least 3.0 on a 5.0 scale is an example of a ________. | requirement | dashboard | Key Performance Indicator | outcome | 3 | 3C | 2 | h | m3B-2h | The correct answer is “Key Performance Indicator (KPI)”. A KPI is a measurable value that indicates how effectively a goal or objective is being achieved. In this case, the average course evaluation of at least 3.0 on a 5.0 scale serves as a KPI to track the performance and quality of the course. Requirements, dashboards, and outcomes are related to project management but do not specifically refer to performance measurement in this context.
18 | 183 | Many projects ______ use red, yellow, and green to indicate the status of each metric. | control charts | dashboards | control panels | risk register | 2 | 3C | 2 | h | m3B-2h | The correct answer is “dashboards”. Dashboards visually display the status of various project metrics, often using red, yellow, and green indicators to represent performance: Green = On track Yellow = At risk Red = Off track. This helps stakeholders quickly assess progress. Control charts, control panels, and risk registers do not typically use colour coding in this way for project status monitoring.
18 | 184 | You are the project manager for the JHG Project. Management has requested that you create a document detailing what information stakeholders will be expected to provide and to whom that information will be disseminated. Management is asking for which of the following? | The roles and responsibilities matrix | The scope management plan | The communications management plan | The communications worksheet | 3 | 3C | 2 | i | m3B-2i | Management is requesting a communications management plan, which details the requirements and expectations for communicating information among the project stakeholders. The other options are incorrect because a roles and responsibilities matrix depicts who does what and who makes which decisions, the scope management plan, this plan explains how changes to the scope may be allowed, depending on the circumstances. Communication worksheet is not a valid choice for the question.
18 | 185 | A construction project is nearing completion, but several stakeholders have raised concerns about inconsistent updates and miscommunication regarding project progress. The project manager has not yet developed a formal communications management plan. To rectify this issue, which of the following should the project manager prioritise? | Increasing the frequency of team meetings | Implementing a comprehensive communications management plan | Appointing a dedicated communication officer | Using more informal communication tools such as messaging apps | 2 | 3C | 2 | i | m3B-2i | Implementing a communications management plan is the correct choice because it provides a structured approach to defining communication methods, stakeholder requirements, and escalation processes. This ensures clear, consistent, and tailored communication across the project. The other options are wrong because while they may address parts of the problem, they do not provide a long-term, structured solution. Increasing the frequency of meetings or appointing a communication officer may help but would not address underlying communication planning issues. Similarly, relying on informal tools could lead to more confusion in a complex, multi-disciplinary project.
18 | 186 | In a construction project, multiple stakeholders from diverse professional backgrounds (architects, engineers, subcontractors) struggle to understand each other’s terminology, leading to delays. To mitigate this issue, what should the project manager include in the communications management plan? | Establish a strict chain of command for communication | Schedule more frequent cross-functional meetings | Create a glossary of common terminology for project communication | Utilise separate communication channels for each stakeholder group | 3 | 3C | 2 | i | m3B-2i | Creating a glossary of common terminology is the correct option because it standardises the language used in the project, reducing misunderstandings due to technical jargon and improving cross-functional communication. The other options are wrong because a strict chain of command may limit necessary communication flow, more frequent meetings would not necessarily solve communication barriers caused by jargon, and separate communication channels could further isolate teams instead of promoting understanding.
18 | 187 | A construction project team relies heavily on subcontractors for progress updates. However, the subcontractors have been inconsistent in providing accurate information, leading to delays. What should the project manager implement to ensure timely and accurate updates? | Increase the number of subcontractor progress meetings | Require subcontractors to submit weekly progress reports via a centralised project dashboard | Implement penalties for late submissions of progress updates | Request more detailed progress reports from subcontractors | 2 | 3C | 2 | i | m3B-2i | Using a centralised project dashboard for progress updates ensures that all information is easily accessible in one location, allows real-time tracking, and promotes transparency. The other options are wrong because more meetings and requesting more detailed reports do not solve the issue of inconsistency, while penalties may create adversarial relationships without addressing the root communication problem.
18 | 188 | During a construction project, a project manager notices that crucial project information is not reaching key stakeholders promptly. Upon review, the communication methods employed are emails and face-to-face meetings. What is the most effective communication method the project manager should implement to address this? | A shared project website with access-controlled sections for stakeholders | Increase the frequency of emails to keep stakeholders updated | Use a messaging platform for real-time updates | Schedule more face-to-face meetings with stakeholders | 1 | 3C | 2 | i | m3B-2i | A shared project website with access-controlled sections ensures that stakeholders can access relevant information at their convenience, fostering transparency and improving information flow. This also allows for real-time access to updated project documents and schedules. The other options are wrong because increasing emails may overwhelm stakeholders without ensuring timely access, real-time messaging may not suit all professional contexts, and more face-to-face meetings are time-consuming and may not be practical for all stakeholders.
18 | 189 | A construction project team is using various communication tools, including emails, instant messaging, and weekly meetings. However, stakeholders are reporting feelings of being overwhelmed and missing critical updates. How can the project manager enhance the communication process to alleviate this issue? | Switch to using only emails for formal communication | Create a formal communication matrix detailing communication responsibilities and methods | Reduce the use of instant messaging to avoid informal updates | Schedule fewer meetings to reduce information overload | 2 | 3C | 2 | j | m3B-2j | A formal communication matrix helps by clearly defining what information needs to be communicated, who is responsible for it, and through what channels. This streamlines communication and ensures stakeholders receive the information they need without being overwhelmed. The other options are wrong because using only one tool, like emails or reducing informal communication, does not address the need for a structured approach. Reducing meetings might exacerbate the lack of timely communication rather than resolving the issue of information overload.
18 | 190 | You are the project manager for a large-scale construction project that involves multiple stakeholders, including architects, engineers, contractors, and subcontractors. Throughout the project, you have noticed communication breakdowns among the different teams, primarily due to the complex jargon specific to each discipline. These miscommunications have caused delays and rework. The stakeholders also possess varying interests and goals, which further complicates communication. As the project manager, it is essential to ensure that communication flows smoothly across all parties. What is the best strategy for managing communication complexities in this scenario? | Establish a rigid communication hierarchy to streamline message dissemination through key points of contact | Develop a tailored communications management plan, including a glossary of terms and guidelines for communication methods across teams | Increase the frequency of formal project meetings to ensure alignment and understanding between stakeholders | Assign a communication liaison from each team to handle all cross-team communications, preventing direct contact between disciplines | 2 | 3C | 2 | j | m3B-2j | The correct answer is “Develop a tailored communications management plan, including a glossary of terms and guidelines for communication methods across teams” because developing a tailored communications management plan ensures that all stakeholders understand the communication process, the jargon used, and how to interact effectively across disciplines. The glossary will bridge knowledge gaps caused by different technical languages and help ensure that each stakeholder interprets project terms correctly. The other options are wrong because establishing a rigid hierarchy may slow communication and lead to bottlenecks, increasing the chance of misinterpretation. Increasing meeting frequency does not address the root cause of miscommunication, while assigning communication liaisons might create further barriers and delay problem-solving, as it restricts direct dialogue between experts from different teams.
18 | 191 | What is a primary communications management challenge in the construction industry? | Lack of skilled workers | Complex regulatory environment | Short-term collaboration with multiple stakeholders | Lack of project funding | 3 | 3C | 2 | j | m3B-2j | The correct answer is “Short-term collaboration with multiple stakeholders”. In the construction industry, projects often involve numerous stakeholders, such as contractors, subcontractors, suppliers, and clients, who collaborate for a limited time. Managing communication between these diverse parties can be challenging, especially with changing teams and temporary relationships. While lack of skilled workers, regulatory complexities, and funding issues are relevant to construction, they are not primarily communications management challenges.
18 | 192 | Which of the following will help you, the project manager in an adaptive project, complete the needed communications management plan by identifying the stakeholders’ communication needs? | Identification of all communication channels | Formal documentation of all communication channels | Formal documentation of all stakeholders | Lessons learned from previous similar projects | 4 | 3C | 2 | j | m3B-2j | Lessons learnt and historical information from a previous project are ideal inputs to communications planning, even for adaptive projects. While adaptive projects do not plan heavily, they will still need to identify the stakeholders and prepare communications to some extent. The other options are incorrect because they do not fully answer the question. Lessons learnt from similar projects are the best tool for identifying stakeholders' communication requirements.
18 | 193 | All of the following regarding Plan Communications Management are true except for which one? | The communications management plan is a component plan of the project management plan. | This process should be completed as early in the project as possible. It is used to define and manage the flow of project information. | It is tightly linked with enterprise environmental factors, and all organisational process assets are used as inputs for this process. | Data gathering, communication technology, communication methods, and expert judgment are some of the tools and techniques of this process. | 4 | 3C | 2 | j | m3B-2j | Expert judgement, communications requirements analysis, communication technology, communication models, communication methods, interpersonal and team skills (communication styles assessment, political awareness, cultural awareness), data representation (stakeholder engagement assessment matrix), and meetings are the tools and techniques of the Plan Communications Management process.
28 | 194 | How should stakeholder engagement strategies be adapted to effectively address varying stakeholder attitudes towards a project? | By increasing the budget and resources allocated to stakeholder-related activities. | By evaluating and aligning with stakeholder-specific regulatory and compliance requirements. | By customising communication and involvement tactics to either mobilise support or mitigate opposition from stakeholders. | By modifying the project’s timelines to accommodate the preferences and expectations of different stakeholders. | 3 | 3C | 2 | j | m3B-2j | The correct answer is “By customising communication and involvement tactics to either mobilise support or mitigate opposition from stakeholders”. Different stakeholders may have varying attitudes, interests, and levels of influence. Tailoring communication and engagement strategies ensures that supportive stakeholders are mobilised effectively while potential opposition is managed proactively. Increasing budgets, focusing solely on compliance, or modifying timelines are less effective or practical than customised engagement to address varying stakeholder needs.
28 | 195 | You are in the process of analysing and visually representing your stakeholders. Which of the following is false? | The salience model is especially useful for displaying stakeholder analysis for small projects or straightforward stakeholder interactions. | Data analysis includes stakeholder analysis and document analysis techniques. | A power/interest grid displays stakeholder information in a quadrant format to display whether the stakeholder is a key player or is one who needs only periodic updates. | Salience models are displayed as Venn diagrams. | 1 | 3C | 3 | a | m3B-3a | The correct answer is “The salience model is especially useful for displaying stakeholder analysis for small projects or straightforward stakeholder interactions”. The salience model is used for complex projects with multiple stakeholders, as it helps prioritise them based on power, legitimacy, and urgency. It is not typically needed for small or simple projects. The other statements are true. Data analysis includes techniques like stakeholder and document analysis. The power/interest grid uses quadrants to classify stakeholders based on their influence and interest levels. Salience models are often represented using Venn diagrams to show overlapping stakeholder attributes.
28 | 196 | Terry is the project manager of his company's ARB project. He approaches Scott for insight into the schedule for releasing the product the project will create. Scott knows nothing about the project Terry is working on and is surprised to learn about the product. What type of stakeholder is Scott? | Unaware | Uninformed | Neutral | Sensitive | 1 | 3C | 3 | a | m3B-3a | Scott is an unaware stakeholder. He does not know about the project or its possible effects on him. Incorrect choices include no stakeholder classification, which is known as uninformed or sensitive. This other option is also incorrect because neutral describes a stakeholder who neither opposed nor favoured the project.
28 | 197 | You are managing a large construction project with multiple stakeholders, including local authorities, environmental groups, and investors. The environmental group possesses significant power but exhibits low interest in your project. It is essential to ensure that their influence on your project is effectively managed. What is the best strategy for engaging this stakeholder? | Ensure continuous, detailed updates and arrange weekly meetings with the group | Provide periodic updates and consult them only when necessary | Minimise communication as they are not directly involved in the project | Engage them actively and involve them in decision-making processes regularly | 2 | 3C | 3 | a | m3B-3a | The correct answer is “Provide periodic updates and consult them only when necessary”, as stakeholders with high power and low interest (such as regulatory authorities), their level of engagement is not as high as their power. The other options are wrong because “Ensure continuous, detailed updates and arrange weekly meetings with the group” suggests over-engagement, which wastes time, “Minimise communication as they are not directly involved in the project” would risk missing out on key input, and “Engage them actively and involve them in decision-making processes regularly” would overly involve them, leading to unnecessary interference.
28 | 198 | You are leading a construction project that involves several high-risk activities. During a recent project risk review, it became evident that a few key stakeholders were not adequately informed about the project’s risks. To align the stakeholder engagement plan with the risk management plan, what should be your next step? | Update the resource management plan to allocate more resources to risk management | Modify the communications management plan to reflect the risks for these stakeholders | Include the risks directly in the stakeholder engagement plan for these stakeholders | Ignore the misalignment as the stakeholders do not have direct decision-making authority | 3 | 3C | 3 | a | m3B-3a | Integrating risks into the stakeholder engagement plan ensures stakeholders are aware of and can respond to relevant project risks. The other options are wrong because “Update the resource management plan to allocate more resources to risk management” does not directly address stakeholder awareness of risks. “Modify the communications management plan to reflect the risks for these stakeholders” focuses too much on communication without proper integration. “Ignore the misalignment as the stakeholders do not have direct decision-making authority” neglects the importance of managing stakeholders’ expectations and risk awareness.
28 | 199 | You are the project manager of a large infrastructure project. The client has considerable power and is highly interested in the project. However, your team has been focusing most of its engagement efforts on the local community, which has low power but high interest. What is the best course of action? | Continue focusing on the local community to maintain good public relations | Shift focus to engaging the client more actively through regular updates and involvement | Engage the client only when issues arise but keep the local community informed daily | Maintain a balanced approach by engaging both the client and local community equally | 2 | 3C | 3 | a | m3B-3a | The client, having both high power and high interest, should be the primary focus of your engagement strategy, as their influence is critical to project success. The other options are wrong because “Continue focusing on the local community to maintain good public relations” over-prioritises the community with lower power, “Engage the client only when issues arise but keep the local community informed daily” neglects the client’s needs, and “Maintain a balanced approach by engaging both the client and local community equally” does not appropriately reflect the client’s priority status.
28 | 200 | In your construction project, a key stakeholder has become resistant to the project due to insufficient communication about its impact on their operations. To rectify this, which approach should you take according to stakeholder management principles? | Increase the frequency of all project communications to ensure no information is missed | Use assumption analysis to determine why the stakeholder became resistant | Arrange a meeting with the stakeholder to discuss concerns and adjust the communication plan accordingly | Reduce communication with this stakeholder as they are already resistant to the project | 3 | 3C | 3 | a | m3B-3a | Direct engagement and adjusting communication strategies based on stakeholder concerns help address resistance effectively. The other options are wrong because “Increase the frequency of all project communications to ensure no information is missed” does not focus on the specific stakeholder’s concerns, “Use assumption analysis to determine why the stakeholder became resistant” is passive and does not involve immediate action, and “Reduce communication with this stakeholder as they are already resistant to the project” could further alienate the stakeholder.
28 | 201 | A regulatory agency in your construction project is unaware of the project but will eventually need to approve several key phases. What action should you take to ensure they become supportive of the project? | Maintain the current strategy as their awareness will increase naturally over time | Proactively engage the regulatory agency by sharing detailed project information and aligning their expectations | Include them in routine communications but do not focus heavily on engagement | Only engage them when their approval is required to avoid unnecessary effort | 2 | 3C | 3 | a | m3B-3a | Proactively engaging unaware stakeholders, especially regulatory agencies, ensures their support when critical approvals are needed. The other options are wrong because “Maintain the current strategy as their awareness will increase naturally over time” is too passive, “Include them in routine communications but do not focus heavily on engagement” risks under-engagement, and “Only engage them when their approval is required to avoid unnecessary effort” delays action until it could be too late.
28 | 202 | During the midpoint of your construction project, you notice that a previously supportive stakeholder has become neutral and less engaged. What is the best way to adjust your stakeholder engagement plan? | Continue with the existing plan and let the stakeholder re-engage at their own pace | Reassess the stakeholder’s needs and concerns and adjust your communication strategy accordingly | Reduce the level of communication as the stakeholder is less supportive | Replace the stakeholder with another that may have more interest in the project | 2 | 3C | 3 | b | m3B-3b | Reassessing the stakeholders' concerns and adapting the engagement strategy can help re-engage previously supportive stakeholders. The other options are wrong because “Continue with the existing plan and let the stakeholders re-engage at their own pace” does not address the shift. “Reduce the level of communication as the stakeholder is less supportive” risks further disengagement. “Replace the stakeholder with another that may have more interest in the project” is impractical and ignores the stakeholder’s value.
28 | 203 | You are responsible for monitoring the effectiveness of stakeholder engagement in your construction project. Several stakeholders have reported dissatisfaction with the current communication level. How should you respond? | Increase the frequency of communication across all stakeholder groups to avoid further dissatisfaction | Conduct an evaluation of the current communication methods and stakeholder needs and adjust accordingly | Take time to understand the problem, if project timelines are not affected | Engage a third-party consultant to manage stakeholder communications for you | 2 | 3C | 3 | b | m3B-3b | Evaluating the effectiveness of current communication strategies based on stakeholder feedback allows for tailored improvements. The other options are wrong because “Increase the frequency of communication across all stakeholder groups to avoid further dissatisfaction” may overwhelm stakeholders unnecessarily, “Take time to understand the problem, as long as project timelines are not affected” risks further dissatisfaction, and “Engage a third-party consultant to manage stakeholder communications for you” passes off critical management responsibility.
28 | 204 | In the power-interest grid, which stakeholders require frequent and close engagement? | Low power, low interest | High power, low interest | Low power, high interest | High power, high interest | 4 | 3C | 3 | b | m3B-3b | The correct answer is "High power, high interest" because these stakeholders hold significant influence and are actively involved in the project. Other options represent stakeholders with different levels of power and interest.
21 | 205 | Tom is a project manager overseeing a bridge construction project for the first time. He has arranged a series of interviews with various stakeholders to gather experiential and historical information on certain risks. Which process is Tom most likely involved in? | Perform Quantitative Risk Analysis | Plan Risk Responses | Identify Risks | Perform Qualitative Risk Analysis | 4 | 3D | 3 | b | m3B-3b | Such meetings or interviews are usually conducted as part of Qualitative Risk Analysis. This method draws on experiential learning and historical data to evaluate the impact of risks on project objectives. Read the question carefully. It mentions that the purpose of the interviews is to gather information about some risks, not to discover some risks.
21 | 206 | Which technique visualises the decision-making process and its potential outcomes in quantitative risk analysis? | Sensitivity analysis | Monte Carlo analysis | Decision tree analysis | Simulation analysis | 3 | 3D | 3 | b | m3B-3b | Decision tree analysis visualises the decision-making process by showing different paths and their potential outcomes. It helps evaluate the consequences of various decisions and select the best course of action based on expected outcomes. Sensitivity analysis assesses how different variables affect outcomes but does not visualise decision paths. Monte Carlo analysis uses random sampling to simulate the effects of risk but does not visualise decision paths. Simulation analysis involves creating models to simulate project scenarios but does not specifically visualise decision paths like decision tree analysis.
21 | 207 | In the context of quantitative risk analysis, what is the primary focus of sensitivity analysis? | Evaluating the constraints and limitations inherent in the project | Determining how variations in different project variables can influence the overall project outcomes | Assessing the likelihood of occurrence of individual risks within the project | Analysing past project data to predict future project performance | 2 | 3D | 3 | b | m3B-3b | Sensitivity analysis involves determining how variations in different project variables impact project objectives. It helps identify which variables influence project outcomes most and where to focus risk management efforts.
21 | 208 | Which risk response strategy involves transferring the responsibility of managing a risk to another party? | Escalate | Share | Exploit | Mitigate | 2 | 3D | 3 | c | m3B-3c | The “Transfer” risk response strategy involves transferring the risk to a third party through insurance or outsourcing.
21 | 209 | You decide to take out an insurance policy if a risky event occurs. What risk response strategy are you using? | Risk transference | Risk mitigation | Risk avoidance | Escalation of the risk | 1 | 3D | 3 | c | m3B-3c | Transferring risk means shifting the impact of a risk to a third party, often through insurance. By taking out an insurance policy, you are transferring the potential financial burden of the loss to the insurance company. Mitigation involves reducing the likelihood or impact of a risk. While insurance helps manage the impact, it does not reduce the likelihood of the event occurring. Avoidance means changing plans to completely prevent the risk from happening. Taking out insurance does not prevent the risk but manages its consequences. Escalation involves passing the risk to a higher authority within the organisation when it cannot be handled at the current level. This is not relevant to the scenario of taking out insurance.
21 | 210 | Which statement best describe a project risk? | An unknown outcome that affects project objectives positively | Uncertainty that can have either a negative or positive effect on meeting project objectives | A random outcome that affects project objectives negatively | An unexpected event that always leads to project failure | 2 | 3D | 3 | c | m3B-3c | According to PMI, project risk is an uncertainty that can negatively or positively affect project objectives. This includes potential opportunities (positive risks) and threats (negative risks).
21 | 211 | Who is responsible for managing specific risks within a project? | Project Manager | Stakeholders | Risk Owners | Project Management Office (PMO) | 3 | 3D | 3 | c | m3B-3c | Risk owners are responsible for managing specific risks in a project. They are designated individuals who monitor risks, implement response strategies, and report on their status.
21 | 212 | In most projects, how are risk probability and impact initially estimated in the risk management plan? | Using mathematical models | Based on expert judgment | By analysing historical project data | By conducting surveys with stakeholders | 2 | 3D | 3 | c | m3B-3c | Risk probability and impact are assessed in most projects based on expert judgement. This involves leveraging the experience and knowledge of experts to evaluate the likelihood and potential impact of risks. Using mathematical models is incorrect because while models can be used, expert judgment is more common and practical. Analysing historical project data is incorrect because historical data is used as a reference but not the primary method for assessing current project risks. Conducting surveys with stakeholders is incorrect because surveys may gather opinions but are not the primary method for assessing risk probability and impact.
21 | 213 | Each of the following statements is true regarding the risk management plan, except for which one? | The risk management plan is an output of the Plan Risk Management process. | The risk management plan describes the selected responses to risks and triggers. | The risk management plan includes thresholds, scoring and interpretation methods, responsible parties, and budgets. | The risk management plan is an input to all the remaining risk-planning processes. | 2 | 3D | 2 |  | m3C-2 | The risk management plan does not describe specific risk responses and triggers. Instead, it outlines the methodology and framework for risk management. The risk register, an output of the Identify Risks process, details specific risk responses and triggers.
21 | 214 | Complete this sentence: A project risk is a(n) ______ occurrence that can impact the project positively or negatively. | Known | Planned | Uncertain | Known unknown | 3 | 3D | 2 |  | m3C-2 | Risks are not planned or known; they are uncertain. The other options are incorrect because these terms do not accurately complete the sentence.
21 | 215 | You are a software development project manager, and you are currently developing the project risk management plan. Which of the following is not part of such a plan? | Risk probability | Methodology | Risk categories | Impact Matrix | 1 | 3D | 2 |  | m3C-2 | The risk management plan contains the following: methodology, roles and responsibilities, budgeting, risk categories, definition of risk probabilities and impacts, probability and impact matrix, revised stakeholders’ tolerances, reporting formats, and tracking. It describes how risk management will be structured and performed on the project. However, it does not identify individual risks or the probability of their occurrence.
21 | 216 | Which analysis technique comprehensively evaluates four internal and external categories that could impact the project? | Brainstorming | Checklists | SWOT analysis | Document analysis | 3 | 3D | 2 |  | m3C-2 | SWOT analysis comprehensively evaluates all potential risks to a project by examining internal factors (Strengths and Weaknesses) and external factors (Opportunities and Threats) that could impact project success. Brainstorming is not suitable because it is a technique for generating ideas. Checklists are not appropriate as checklists help ensure that all known risks are considered but do not provide a thorough evaluation. Document analysis is not applicable because it involves reviewing documents to identify risks but does not offer a comprehensive evaluation.
21 | 217 | Which external factor category does the PESTLE acronym not cover? | Political | Economic | Social | Legacy | 4 | 3D | 2 |  | m3C-2 | The PESTLE analysis covers several external factor categories, including Political, economic, Social, Technological, Legal, and Environmental. These factors are not internal to the project but can influence its success.
21 | 218 | Jason is the project manager for his organisation. He and his project team are working to identify and analyse project risks. As part of this process, Jason creates a risk register, but his team doesn’t understand what a risk register is or its purpose. Which of the following best describes the risk register? | It documents all the outcomes of the other risk management processes. | It is a document that includes the initial risk identification entries. | It is a system that monitors all adverse risks associated with a project. | It is part of the project’s project management information system (PMIS) for integrated change control. | 1 | 3D | 2 |  | m3C-2 | The risk register documents all the outcomes of the other risk management processes. The other options are incorrect definitions of the risk register.
21 | 219 | You have identified a risk event in your current project that could save $100,000 in project costs if it occurs. Which of the following statements is true based on this? | This is a risky event that should be accepted because the rewards outweigh the threats to the project. |  | This risk event should be mitigated to take advantage of the savings. | This risk event should be avoided to maximise the potential savings. | 2 | 3D | 2 |  | m3C-2 | This risk event has the potential to save money on project costs, so it is an opportunity, and the appropriate strategy to use in this case is the exploit strategy.
21 | 220 | Which of the following statements is true regarding the RBS? | The RBS is contained in the risk management plan. | It describes risk categories, a systematic way to identify risks and provide a foundation for understanding for everyone involved in the project. | The lowest level of the RBS can be used as a prompt list, a tool and technique of the Identify Risks process. | The RBS is like the WBS in that the lowest levels are easily assigned to a responsible party or owner. | 4 | 3D | 2 |  | m3C-2 | The RBS describes risk categories; the lowest level can be used as a prompt list to help identify risks. The RBS does not assign risk owners but is typically assigned when a risk is identified.
21 | 221 | As a project manager, you use a fishbone diagram to identify potential risks in your project. Which process are you in? | Plan Risk Response | Control Quality | Perform Qualitative Risk Analysis | Identify Risk | 4 | 3D | 2 |  | m3C-2 | A fishbone diagram (also known as an Ishikawa or cause-and-effect diagram) can identify risks by visually displaying the potential causes of a problem. This helps pinpoint where risks might arise. It is also a quality management tool.
21 | 222 | You are a project manager about to complete the risk management processes. Which one of the following documents evolves throughout the risk management processes? | Risk Mitigation Plan | Contingency Plan | Risk Profile | Risk Register | 4 | 3D | 3 | a | m3C-3a | The risk register is a document that contains all identified risks and their status. It is continuously updated throughout the project to reflect each risk's current state.
21 | 223 | When are risk identification activities performed? | During the Plan Risk Management process | During the Perform Qualitative Risk Analysis process | During the Perform Quantitative Risk Analysis process | Ongoing throughout the project | 4 | 3D | 3 | a | m3C-3a | Identifying risks is initially a planning process. However, this process is iterative because unknown risks can be discovered throughout the project’s life cycle.
21 | 224 | Assessing the probability and consequences of identified risks to the project objectives, assigning a risk score to each risk, and creating a list of prioritised risks describe which of the following processes? | Perform Quantitative Risk Analysis | Identify Risks | Perform Qualitative Risk Analysis | Plan Risk Management | 3 | 3D | 3 | a | m3C-3a | Qualitative Risk Analysis involves assessing the probability and consequences of identified risks to prioritise them for further analysis or action. It helps to focus on the most significant risks.
21 | 225 | What is the primary goal of performing qualitative risk analysis in project management? | To eliminate all project risks | To assess the probability of risks occurring | To evaluate and prioritise individual project risks | To determine the project budget | 3 | 3D | 3 | a | m3C-3a | The primary goal of qualitative risk analysis is to evaluate and prioritise individual project risks based on their probability and impact. This helps in focusing resources on the most critical risks.
21 | 226 | What is the purpose of risk categorisation in qualitative risk analysis? | To group risks based on alphabetical order | To rank risks based on their urgency | To facilitate prioritisation and further analysis | To determine the likelihood of each risk occurring | 3 | 3D | 3 | a | m3C-3a | Risk categorisation aims to facilitate prioritisation and further analysis by grouping similar risks together. This helps identify patterns and focus on areas with higher risk concentrations.
21 | 227 | What are the outputs of the Perform Qualitative Risk Analysis process? | Risk management plan, stakeholder register, risk response strategies | Updates to risk register, issue log, risk report | Enterprise Environmental Factors, Organisational Process Assets, project documents | Data representation, risk report, data analysis | 2 | 3D | 3 | a | m3C-3a | The outputs of the Perform Qualitative Risk Analysis process include updates to the risk register, issue log, and risk report. These documents are updated with the results of the qualitative risk analysis.
21 | 228 | What is the primary purpose of a probability/impact matrix to assist in qualitative risk analysis? | It helps to eliminate risks with low probabilities | It helps to define risk categories | It complements expert judgment | It helps to prioritise risks | 4 | 3D | 3 | a | m3C-3a | A probability/impact matrix assists in prioritising risks by plotting the probability of each risk against its impact. This visual tool helps identify which risks need more attention based on their potential effect on the project. While the other options describe relevant functions and aspects of the risk management process, the primary purpose of a probability/impact matrix is to prioritise risks. This ensures that resources and attention are focused on the most critical risks to the project’s success.
21 | 229 | Which factor is not considered when categorising the impact of a risk? | Time | Cost | Probability | Quality | 3 | 3D | 3 | a | m3C-3a | Probability is not a factor considered when categorising project risks. Risk categorisation typically involves factors like time, cost, and quality to group similar risks for better analysis and management. The other options are all considered factors when categorising project risks, as they help group risks based on their potential impact on different project areas.
21 | 230 | What is one of the typical outcomes of conducting qualitative risk analysis? | Categorisation of risks into high, medium, or low | Elimination of all risks | Probability distributions of risks | Ignoring risks with low impact | 1 | 3D | 3 | a | m3C-3a | One of the typical outcomes of conducting a qualitative risk analysis is categorising risks into high, medium, or low. This helps prioritise risks and focus on those that have the most significant potential impact on the project.
21 | 231 | Alice is a project manager for her organisation. She is working with the project team to identify and rank risks by impact and probability. Which risk analysis technique provides the project manager with a risk ranking? | Quantifiable | Qualitative | The utility function | SWOT analysis | 2 | 3D | 3 | a | m3C-3a | The risk ranking is based on the identified risks’ very high, high, medium, low, and very low attributes. Quantifiable is incorrect because it is irrelevant to the question; quantitative could have been correct. The utility function is an organisation’s tolerance for risk. SWOT analysis is part of risk identification.
21 | 232 | Which of the following is not an output of qualitative risk analysis? | A prioritised list of risks for a given project objective based on the probability and impact matrix of the objective | A watch list of low-priority risks | A list of risks prioritised based on the total effect of each risk on the overall project objectives | A list of trends in the analysis results | 3 | 3D | 3 | a | m3C-3a | A list of risks prioritised based on the total risk score is typically an output of quantitative risk analysis, not qualitative. Qualitative risk analysis focuses on assessing risks based on their probability and impact but does not usually involve a detailed scoring system. The other options are incorrect because these are the possible output items from qualitative risk analysis.
21 | 233 | What is the main objective of using simulation techniques, like Monte Carlo, in quantitative risk analysis within project management? | To precisely predict the exact date and cost at which the project will be completed | To identify and eliminate all potential risks in the project | To assess the combined impact of various risks on project objectives, providing a range of possible outcomes and their probabilities | To develop a detailed project plan that outlines every step in the project execution | 3 | 3D | 3 | a | m3C-3a | The main objective of using simulation in quantitative risk analysis is to assess the combined impact of various risks on project objectives. Simulations like Monte Carlo analysis help project managers understand how different risks interact and affect project outcomes.
21 | 234 | The water sanitation project manager has determined that the risks associated with handling certain chemicals are too high. Therefore, he has decided to let someone else complete this portion of the project. He has outsourced the handling and installation of the chemicals and filter equipment to an experienced contractor. This is an example of which of the following? | Avoidance | Acceptance | Mitigation | Transference | 4 | 3D | 3 | a | m3C-3a | It is considered transference because the risk is not eliminated but transferred to someone else or another entity. Avoidance is incorrect because the risk is not being avoided—another entity is just handling it. Acceptance is incorrect because the project manager has not accepted the risk but decided to allow another entity to deal with it. Mitigation is incorrect because the risk has not been mitigated in the project.
21 | 235 | You are managing a project to set up data servers to support a website for an enterprise customer. The servers have been located close to the customer due to their requirements; however, this location is prone to natural disasters, such as hurricanes and flooding. To mitigate this risk, you have decided to install additional servers in another city that will serve as a backup in the event of a disaster. This serves as an example of which of the following? | Risk avoidance | Risk mitigation | Risk acceptance | Risk transfer | 2 | 3D | 3 | b | m3C-3b | Risk mitigation is correct because building redundancy into a system is an example of mitigating the risk. Risk avoidance is incorrect because the risk can still happen. After all, you have not changed the plan, such as moving the server centre to another city. Risk acceptance is incorrect because accepting a risk means no proactive action is taken; this is not the case here. Risk transfer is incorrect because you have not transferred the risk to a third party.
21 | 236 | The risk management team of a software project has decided that due to the lack of adequate talent in your company, the development of a specific part of the system is at high risk, so they have decided to outsource it. This is an example of which of the following? | Risk avoidance | Risk mitigation | Risk acceptance | Risk transfer | 4 | 3D | 3 | b | m3C-3b | Risk transfer is correct because the risk has been transferred to a third party. Risk avoidance is incorrect because the risk can still happen because you have not changed the plan, such as eliminating the need for that part of the system. Risk mitigation is incorrect because mitigating the risk does not involve transferring the risk to a third party. Risk acceptance is incorrect because accepting a risk means no proactive action is taken.
21 | 237 | Which of the following is not a valid risk response? | Risk acceptance | Risk sharing | Risk mitigation | Risk rejection | 4 | 3D | 3 | b | m3C-3b | Risk rejection is the correct answer because there is no standard risk response named risk rejection. The other options are incorrect because these are valid risk responses.
21 | 238 | Your hardware vendor left you a voicemail saying that a snowstorm in the Midwest will prevent your equipment from arriving on time. You identified a risk response strategy for this risk and have arranged for a local company to lease you the needed equipment until yours arrives. This is an example of which risk response strategy? | Transfer | Acceptance | Mitigate | Avoid | 3 | 3D | 3 | b | m3C-3b | Mitigation attempts to reduce the impact of a risk event should it occur. Making plans to arrange for the leased equipment reduces the consequences of the risk.
21 | 239 | You are the construction project manager of an important stadium that will be used for the Winter Olympics. The games start in a month, and your project has faced some weather delays in pouring the concrete for the landscaping. Although you know that bad weather might affect the quality of the concrete, you decide to proceed with the remaining concrete work since the deadline is approaching and you do not want to delay the project any further. What risk strategy are you adopting? | Transfer | Exploit | Mitigate | Accept | 4 | 3D | 3 | b | m3C-3b | In this situation, you are using the acceptance strategy. Acceptance is adopted when there is no possibility to eliminate all threats from a project. This means the project team has decided not to change the project management plan to deal with a risk or cannot identify a response strategy. This strategy can be active or passive acceptance. Passive Acceptance: No action except documenting the strategy and leaving the project team to deal with the risks as they occur. Active Acceptance: Establish a contingency reserve (time/money/resources).
21 | 240 | Tom is a construction project manager who recently approached an insurance company to insure the project against potential storm damage predicted for the winter. What risk response strategy is Tom undertaking? | Avoid | Accept | Mitigate | Transfer | 4 | 3D | 4 |  | m3C-4 | Risk Transference is a risk response strategy that shifts the impact of a threat to a third party, together with ownership of the response. Taking out insurance or a warranty transfers the risk from the owner to the other party.
21 | 241 | During the Sequence Activities process, your project team has identified several dependencies on a few related projects that will provide major and critical deliverables to your project. Some of these projects are very similar to your project concerning their scope and deliverables. In this situation, which of the following processes should you be most concerned about? | Sequence Activities | Validate Scope | Plan Risk Response | Control Scope | 3 | 3D | 4 |  | m3C-4 | Since there are dependencies on external projects and those projects should provide you with critical and significant deliverables, the main concern must be the risks that other projects may pose to yours. It is preferable to prevent these issues in the Plan Risk Response process rather than spend effort controlling or validating scope.
21 | 242 | As a project manager for a complex infrastructure project, you must create a centralised record of all identified risks that can be continuously updated throughout the project. Which of the following records will assist you in effectively monitoring and managing risks, ensuring that any changes in risk status or new risks are swiftly addressed? | Risk management plan | Risk register | Risk report | Project management plan | 2 | 3D | 4 |  | m3C-4 | The risk register is a document that centralises the record of all identified risks. It is continuously updated throughout the project to reflect new risks, changes to existing risks, and the status of risk responses. The other options are incorrect because the risk management plan outlines the overall approach to risk management, the risk report provides an overview of the project’s risk status, and the project management plan integrates all subsidiary plans, including the risk management plan.
21 | 243 | You are managing a construction project for a new bridge and must ensure that all potential risks are identified and categorised. At this initial stage, you focus on external factors that could affect the project. Which tool would you use to classify risks? | SWOT Analysis | Risk Breakdown Structure (RBS) | PESTLE Analysis | Root Cause Analysis | 3 | 3D | 4 |  | m3C-4 | PESTLE Analysis is a tool for categorising risks based on political, economic, sociological, technological, legal, and environmental factors. SWOT Analysis focuses on strengths, weaknesses, opportunities, and threats, while the Risk Breakdown Structure (RBS) organises risks into categories but does not specifically focus on external factors. Root Cause Analysis identifies the underlying causes of risks but does not categorise high-level external risk factors in the same way as PESTLE Analysis.
21 | 244 | You are leading a construction project and have developed a comprehensive risk register. During a review, a team member suggests employing System 1 thinking to identify and mitigate risks based on past experiences. Why is this approach not recommended for project risk management? | System 1 thinking is intuitive and rapid, making it prone to errors | System 1 thinking involves a structured and careful approach that takes a longer time to complete | System 1 thinking is more suitable for technical problem-solving | System 1 thinking is the basis for developing a risk register | 1 | 3D | 4 |  | m3C-4 | System 1 thinking is intuitive and rapid, relying on past experiences and inclinations to make quick decisions. This approach is prone to errors and is not recommended for project risk management, which requires a thorough and careful approach to ensure all potential risks are identified and appropriately managed. The other options are wrong because System 1 thinking does not involve a structured approach, is not necessarily suitable for technical problem-solving, and is not the basis for developing a risk register; instead, System 2 thinking, which is deliberate and systematic, is recommended for these tasks.
24 | 245 | Assume you can lease a machine for a project for $2,000/day. The cost of purchasing the machine is $26,000 plus a daily operational cost of $300/day. How long will the purchase cost be the same as the lease (round to the nearest day)? | 14 days | 153 days | 15 days | 29 days | 3 | 3D | 4 |  | m3C-4 | Cost of purchase and operational cost for X days = Lease machine for X days: 26000+300X=2000X, 26000=1700X, X=26000/1700, X = 15.29
24 | 246 | You are the project manager for an upcoming outdoor concert event. You are working on the procurement plan for the computer software program to control the lighting and screen projections during the concert. You compare the cost of purchasing a software product to the cost of your company programmers writing a custom software program. Which of the following are you engaged in? | Procurement planning | Using expert judgment | Creating the procurement management plan | Make-or-buy analysis | 4 | 3D | 4 |  | m3C-4 | The correct answer is “Make-or-buy analysis”. A make-or-buy analysis compares the costs and benefits of developing a product or service in-house versus purchasing it from an external supplier. In this case, you are determining whether to write custom software or buy a pre-existing software product, which is a typical make-or-buy decision. While procurement planning, expert judgment, and creating the procurement management plan are part of the procurement process, this specific activity is a make-or-buy analysis.
24 | 247 | You are conducting procurement management, and you are about to award a contract to a subcontractor for a portion of the project scope. The mentioned portion, described at a high level, will cost $4 million with a standard deviation of $500,000. What type of contract do you recommend in this situation? | Fixed Cost | Fixed price plus incentive fee | Cost-plus fixed fee | Cost-plus percentage of costs | 3 | 3D | 4 |  | m3C-4 | The cost of this project will vary, at one standard deviation, from $3.5M to $4.5M. Since this is not insignificant, there would appear to be some ambiguity with the project definition. Since the scope is uncertain and not described in detail, we would not pick either fixed price option (fixed cost or fixed price plus incentive fee). Of the two cost-plus options, you need to select the better one. A cost-plus percentage of costs is probably the worst contract type, as there is no incentive for the seller to control costs. The only choice left is a cost-plus-fixed-fee contract.
24 | 248 | The analysis to make a buy-or-make decision is performed during which of the following procurement processes? | Conduct Procurements | Administer Procurements | Plan Procurements | Control Procurements | 3 | 3D | 4 |  | m3C-4 | The correct answer is that the make-or-buy analysis is a technique used in the procurement planning process called Plan procurement. The other options are incorrect because make-or-buy decisions are already made in the Conduct Procurements process. There is no standard process called Administer Procurement and Control Procurement, which is not the process in which make-or-buy decisions are made.
24 | 249 | You are leading the procurement process for a construction project where you urgently need to train 200 employees on safety protocols to meet regulatory requirements. You have two options: use internal trainers or hire an external company. Internal trainers can take 25 participants per run, costing $480. However, due to other commitments, the internal trainer can only conduct 1.5 monthly courses. External trainers can take 30 participants per run, costing $800 per participant. The external trainers can conduct a total of 7 runs of the course per month. Which option would you choose and why? | Hire internal trainers because they offer more flexibility in scheduling and are easier to follow up on administrative matters. | Hire external trainers because they can complete the training quicker and they are not too expensive. | Use internal trainers because the total cost is lower, and the trainers are easier to manage. | Use external trainers because they can ensure training quality and are more recognised by the regulator. | 2 | 3D | 4 |  | m3C-4 | The internal trainer can train all 200 employees at a lower total cost of [(200/25 = 8 runs) x $480 per run = $3840]. Compared to the external trainers, the total cost is [(200/30 = 6.7 runs = 7 runs) x $800 per run = $5600]. Although the external trainers are more expensive, they can finish the training within one month compared to the 8 months by the internal trainer. Given that the regulatory requirements and the difference in total cost are not too great, one should select an external trainer.
24 | 250 | In procurement processes, which type of bidding document not only requests an offer from potential suppliers but also allows them to detail their methodology and strategy in meeting the buyer’s specific requirements, often involving complex or less-defined scopes of work? | Request for Information (RFI) | Request for Quotation (RFQ) | Request for Proposal (RFP) | Terms of Reference (TOR) | 3 | 3D | 5 |  | m3C-5 | The correct answer is “Request for Proposal (RFP).” An RFP is used when the buyer requires suppliers to submit detailed proposals that include pricing, methodology, strategy, and an approach to meeting specific requirements. It is suitable for complex or less-defined scopes of work where the buyer is looking for more than cost estimates. On the other hand, an RFI gathers preliminary information. An RFQ focuses on pricing for well-defined needs. A TOR outlines the scope of work but is not a bidding document itself.
24 | 251 | In which situation would an RFP be more suitable than an RFQ? | When purchasing standardised items | When seeking specific pricing details | When there are various solutions to meet a need | When requesting information about goods | 3 | 3D | 5 |  | m3C-5 | The correct answer is “When there are various solutions to meet a need”. A Request for Proposal (RFP) is more suitable when the project requires creative solutions or multiple approaches, and the buyer needs suppliers to detail their methodologies, strategies, and pricing. It is often used for complex projects with less-defined requirements. In contrast, a Request for Quotation (RFQ) is better suited for standardised items or when specific pricing details are needed. A Request for Information (RFI) gathers preliminary data about available goods or services.
24 | 252 | In a construction project, when the project manager needs to acquire specific building materials with well-defined specifications, such as concrete mix or steel beams, which type of document is typically used to obtain accurate price quotes from various suppliers? | Invitation to Tender (ITT) | Request for Information (RFI) | Request for Quotation (RFQ) | Request for Proposal (RFP) | 3 | 3D | 5 |  | m3C-5 | The correct answer is “Request for Quotation (RFQ).” An RFQ is used when the buyer needs accurate price quotes for specific, well-defined items in a construction project, such as concrete mix or steel beams. This document focuses on pricing and delivery details for standardised products or services. In contrast, an ITT is used for formal bids, often for large projects. An RFI gathers general information, not pricing. An RFP is for more complex needs where solutions and methodologies are also required.
24 | 253 | What key information is typically included in an RFI? | Detailed cost breakdown | Project timeline and deliverables | Background of potential suppliers | Compliance with health and safety regulations | 3 | 3D | 5 |  | m3C-5 | The correct answer is “Background of potential suppliers.” An RFI gathers preliminary data about potential suppliers, including their background, capabilities, and experience. It helps the buyer assess which vendors might be suitable for further engagement. In contrast, cost breakdowns are typically requested in an RFQ. Timelines and deliverables are included in RFPs. Compliance with health and safety regulations is often addressed later in the procurement or contracting stages.
24 | 254 | What type of information does an SOW provide prospective suppliers? | Project requirements and scope of work | Detailed pricing breakdown | Background of potential suppliers | Evaluation criteria for contractors | 1 | 3D | 5 |  | m3C-5 | The correct answer is “Project requirements and scope of work.” A Statement of Work (SOW) outlines a project's specific tasks, deliverables, timelines, and expectations. It provides prospective suppliers with a clear understanding of the buyer's requirements, helping them prepare appropriate proposals or bids. On the other hand, Pricing breakdowns are part of RFQs or RFPs. Supplier backgrounds are collected through RFIs. Evaluation criteria are typically included in RFPs or tender documents.
24 | 255 | In the context of a construction project, when a project manager prepares a procurement document to contract a vendor to supply and install custom windows, what role does the Statement of Work (SOW) play in this process? | It provides a general inquiry about potential vendors’ capabilities and experiences. | It acts as a legal contract between the project owner and the vendor, specifying payment terms only. | It defines the project-specific activities, deliverables, and timelines for supplying and installing the custom windows. | It serves as a preliminary budget estimate for the procurement of materials. | 3 | 3D | 5 |  | m3C-5 | The correct answer is “It clearly defines the project-specific activities, deliverables, and timelines for the supply and installation of the custom windows”. In a construction project, the Statement of Work (SOW) outlines the scope, tasks, deliverables, and deadlines related to the vendor’s responsibilities. It ensures that both parties understand the work required and helps guide the procurement and project execution process. On the other hand, inquiries about vendors’ capabilities are part of RFIs. Contracts cover more than just payment terms. Budget estimates are included in cost management, not in the SOW.
24 | 256 | What is the purpose of a supplier evaluation matrix in project procurement management? | To negotiate prices with potential suppliers | To select suppliers based on their competency | To objectively assess and compare potential suppliers against predetermined criteria | To eliminate all potential suppliers except one | 3 | 3D | 5 |  | m3C-5 | The correct answer is “To objectively assess and compare potential suppliers against predetermined criteria.” A supplier evaluation matrix helps project managers rank suppliers based on price, quality, delivery, and past performance. This ensures a fair and structured selection process. However, negotiating prices happens after the evaluation. Competency assessments are part of the matrix but are not its sole purpose. The matrix aims to compare suppliers, not eliminate all but one.
24 | 257 | How does the weighted scoring model help in supplier evaluation? | It allows for an objective comparison of potential suppliers based on predetermined criteria with different levels of importance. | It includes opportunities to work with new suppliers. Suppliers are randomly assigned scores, which are multiplied by the weights they assign. | It ensures fairness by assigning equal importance to all criteria, only assigning weights when complications arise. | It prevents cost overruns by focusing solely on the supplier’s cost factor. The weighted scores help restrict cost overruns. | 1 | 3D | 5 |  | m3C-5 | The correct answer is “It allows for an objective comparison of potential suppliers based on predetermined criteria with different levels of importance”. A weighted scoring model assigns weights to different criteria (e.g., cost, quality, delivery) based on their importance. Suppliers are then scored against these criteria, and the scores are multiplied by the assigned weights, providing a fair and structured comparison to support decision-making. In contrast, scores are not assigned randomly or by suppliers. The model allows for variable weights, not equal importance for all criteria. It considers multiple factors, not just cost, to avoid overemphasising one aspect.
24 | 258 | How are the weights assigned to criteria in a supplier evaluation matrix determined? | They are randomly assigned. | They are determined by the supplier. | They reflect the project’s specific needs and priorities. | They are the same for most projects. | 3 | 3D | 2 | a | m3D-2a | The correct answer is “They reflect the project’s specific needs and priorities.” The weights assigned to criteria (such as cost, quality, or delivery time) are tailored to align with the project's unique needs and priorities in a supplier evaluation matrix. This ensures that the most important factors for the project are given appropriate significance during supplier evaluation. In contrast, weights are not randomly assigned or set by suppliers. They vary across projects to meet specific requirements.
24 | 259 | How is the overall score for a supplier typically calculated in a supplier evaluation matrix? | By summing up the supplier’s past performance | By averaging the scores of all criteria | By multiplying the supplier’s score for each criterion by its weight and summing up the results | By comparing the supplier’s cost to its quality | 3 | 3D | 2 | a | m3D-2a | The correct answer is “By multiplying the supplier’s score for each criterion by its weight and summing up the results”. Each criterion is weighed in a supplier evaluation matrix based on its importance. The supplier’s score for each criterion is multiplied by the corresponding weight, and the results are summed to determine the supplier’s overall score. This approach ensures a fair and prioritised evaluation. Simply summing past performance or averaging scores do not reflect varying criterion importance. Comparing cost to quality alone ignores other critical factors.
24 | 260 | The PSSCOC is the standard form of contract used for public infrastructure projects in Singapore. The other options are wrong because FIDIC is typically used for international projects, JCT contracts are more common in the UK, and the Singapore Institute of Architects (SIA) contract applies more to building projects, not public infrastructure. | Supplier A because cost savings are always the priority. | Supplier B because past performance and quality outweigh other criteria. | Supplier C because innovation and technology will expedite the project timeline. | Conduct a full supplier evaluation, balancing cost, quality, technology, and past performance. | 4 | 3D | 2 | a | m3D-2a | The correct option is “To conduct a full supplier evaluation, balancing cost, quality, technology, and past performance” as the most balanced approach to supplier selection. The supplier evaluation matrix allows for assigning weights to these factors, ensuring a well-rounded decision. The other options are wrong because focusing solely on cost or quality might overlook other critical aspects like technology and long-term value. Similarly, prioritising technology without considering references and past performance could lead to potential risks in reliability and quality.
24 | 261 | What is the fundamental objective of employing competitive contracting methods in project management? | To foster long-standing, collaborative relationships with selected suppliers | To stimulate competitive bidding among suppliers, aiming to achieve the best value | To ensure the client maintains comprehensive control over the execution of project components | To streamline and simplify the overall procurement process for efficiency. | 2 | 3D | 2 | a | m3D-2a | The correct answer is “To stimulate competitive bidding among suppliers, aiming to achieve the best value”. The primary goal of competitive contracting methods is to encourage competition among suppliers to secure the best value in terms of cost, quality, and service. This approach ensures the buyer receives optimal solutions while maintaining fairness and transparency in the procurement process. In contrast, collaborative relationships and comprehensive control are more relevant to specific contract types. Streamlining the procurement process is a benefit but not the primary objective of competitive contracting.
24 | 262 | When might a termination clause be invoked in a contract? | When the project is behind schedule | When the contractor exceeds the budget | When the project scope changes | When the contractor fails to deliver the product | 4 | 3D | 2 | a | m3D-2a | The correct answer is “When the contractor fails to deliver the product.” A termination clause allows the buyer to end the contract if the contractor fails to meet essential obligations, such as delivering the product or service as agreed. It provides a legal remedy to protect the buyer from non-performance. In contrast, project delays, budget overruns, or scope changes may lead to renegotiations, but they do not typically justify invoking a termination clause unless they are tied to a critical breach of contract.
24 | 263 | Which contract type would be most appropriate for a public-sector entity seeking to retain a high degree of control and risk management while ensuring the successful construction and operation of a new infrastructure facility by the private sector? | Design-Build-Finance-Operate (DBFO) contract | Design-Build contract | Privatisation contract | Operation-Management contract | 1 | 3D | 2 | a | m3D-2a | The correct answer is “Design-Build-Finance-Operate (DBFO) contract.” A DBFO contract enables the public sector to delegate an infrastructure facility's design, construction, financing, and operation to a private entity while maintaining oversight and control over the project’s objectives and outcomes. This type of contract helps manage risk by shifting specific responsibilities to the private sector. In contrast, a Design-Build contract deals only with design and construction. Privatisation contracts transfer complete ownership and operation to the private sector. An Operation-Management contract focuses primarily on managing operations rather than construction or financing.
24 | 264 | What is one of the advantages of using PPP contracts for public infrastructure projects? | They guarantee project completion ahead of schedule. | They reduce the need for competitive bidding. | They eliminate the need for risk analysis. | They bring in new ideas and expertise from the private sector. | 4 | 3D | 2 | a | m3D-2a | The correct answer is “They bring in new ideas and expertise from the private sector”. Public-Private Partnership (PPP) contracts leverage the private sector's innovation, expertise, and efficiency in public infrastructure projects. This collaboration often results in improved design, construction, and operation solutions. In contrast, PPPs do not guarantee early completion. They still require competitive bidding to ensure transparency. Risk analysis remains essential in PPP projects to manage shared risks effectively.
24 | 265 | You are the project manager of the Adams Construction Project. Some of the work in the project contains pure risk that you are not willing to accept. You decide to mitigate the pure risks in this project. Which of the following may be used as a risk mitigation tool? | The vendor proposal | The contract | The quotation | Project requirements | 2 | 3D | 2 | b | m3D-2b | Contracts can be used as a risk mitigation tool. Procuring risky activities is known as transference. The risk does not disappear, but the responsibility is transferred to the vendor. The other options, such as vendor proposals, quotations, and project requirements, are incorrect and do nothing to serve as risk mitigation tools.
24 | 266 | You are managing a large construction project for a public infrastructure development. You have opted for a Public-Private Partnership (PPP) to share risk. Midway through the project, the private sector partner struggles with unforeseen financial difficulties. To manage the project’s financial risk, what action should you take, according to risk management best practices? | Terminate the contract with the private sector partner and retender the project to a new bidder. | Collaborate with the private sector partner to revise the risk allocation matrix and redefine responsibilities. | Insist on enforcing penalty clauses, regardless of the private sector’s financial issues. | Transfer the financial burden entirely to the public sector to prevent project delays. | 2 | 3D | 2 | b | m3D-2b | The best action is collaborating with the private sector to revise the risk allocation matrix. This allows both parties to reassess responsibilities and manage financial risk more effectively, aligning with project management principles of adaptive risk allocation. The other options are wrong because terminating the contract would cause unnecessary delays, enforcing penalties might worsen the situation, and transferring all risk to the public sector undermines the purpose of a PPP by centralising too much risk in one party.
24 | 267 | During the procurement phase of a major infrastructure project, you decide between a fixed-price contract and a cost-reimbursable one. Given the project's complexity and uncertainty, which procurement strategy would best mitigate financial risks? | Fixed-price contract to lock in costs | Cost-reimbursable contract to allow for flexibility in pricing | Competitive bidding to drive down costs | Time and materials contract to manage resource utilisation | 2 | 3D | 2 | b | m3D-2b | A cost-reimbursable contract is the most suitable choice in this case because it offers flexibility in pricing, which is crucial for a complex and uncertain project. This type of contract provides the adaptability needed to accommodate changes in project scope or unexpected challenges. The other options are less appropriate because a fixed-price contract could lead to higher costs if unforeseen challenges arise, competitive bidding emphasises cost reduction but does not address risk mitigation, and a time and materials contract may result in cost overruns.
24 | 268 | You are overseeing the procurement for a public sector infrastructure project in Singapore. The client insists on using standardized contracts. Which contract is the most suitable? | REDAS Design and Build Conditions of Contract | Singapore Institute of Architects (SIA) Contract | BCA Public Sector Standard Conditions of Contract (PSSCOC) | EPCM contract | 3 | 3D | 2 | b | m3D-2b | The PSSCOC is specifically designed for public-sector projects in Singapore, ensuring compliance with public-sector requirements. The other options are wrong because the REDAS and SIA contracts are more suited for private-sector or building projects, and EPCM does not align with standardised public-sector procurement.
24 | 269 | What distinguishes EPC (Engineering, Procurement, and Construction) contracts from EPCM (Engineering, Procurement, and Construction Management) contracts regarding project management and execution? | In an EPC contract, the project owner is responsible for the construction or installation, whereas in an EPCM contract, the EPCM contractor supervises the construction. | EPC contracts assign complete project responsibility to a single contractor, while EPCM contracts involve the project owner playing a more active role in overseeing various contractors through an EPCM contractor. | Under an EPC contract, a single contractor is responsible for the entire construction or installation. In contrast, in an EPCM contract, the EPCM contractor is responsible for selecting and supervising different contractors. | Different contractors are selected for engineering, procurement, and construction in EPC contracts, whereas in EPCM contracts, a single contractor manages all these phases. | 3 | 3D | 2 | b | m3D-2b | The correct answer is: “Under an EPC contract, a single contractor is responsible for the entire construction or installation, while in an EPCM contract, the EPCM contractor is responsible for selecting and supervising different contractors”. In an Engineering, Procurement, and Construction (EPC) contract, the contractor takes full responsibility for design, procurement, and construction, delivering a complete, ready-to-use facility. In contrast, in an Engineering, Procurement, and Construction Management (EPCM) contract, the EPCM contractor manages and oversees the selection and supervision of multiple contractors but does not perform the construction directly. The project owner is more active in managing the various contractors under EPCM arrangements.
24 | 270 | What is the primary purpose of the “Procurement Constraints” section in the procurement management plan? | To highlight any project constraints that must be considered part of the procurement management process | To define the number of available procurement staff, which may constrain the procurement management process | To highlight the procurement risks that may impact the procurement management process | To describe the availability of technical experts, which may constrain the procurement management process | 1 | 3D | 2 | b | m3D-2b | The correct answer is “To highlight any project constraints which must be considered part of the procurement management process”. The “Procurement Constraints” section identifies limitations or restrictions that could affect procurement activities. These could include time, budget, resources, legal requirements, or delivery schedules, ensuring the procurement strategy aligns with the overall project constraints. While staff availability, risks, and technical expertise are relevant considerations, this section focuses on broader project constraints that impact procurement.
24 | 271 | You want to lower the risk arising from a contract to purchase goods and services from a supplier. As the buyer, what type of contract should you use? | fixed price | unit price | cost reimbursable | time and materials | 1 | 3D | 2 | b | m3D-2b | The correct answer is “fixed price”. In a fixed-price contract, the buyer’s risk is minimised because the total cost is agreed upon upfront, regardless of any variations in the supplier’s expenses. This type of contract ensures that the supplier controls costs and meets deliverables within the agreed budget. Other types, like unit price, cost reimbursable, and time and materials contracts, involve more uncertainty and potential cost overruns, placing more risk on the buyer.
24 | 272 | In the procurement process, a Request for ______ is a formal document issued by a company to invite suppliers to submit detailed proposals or bids, often encompassing pricing, approaches, and methodologies. What term completes this phrase? | Proposal | Price | Quote | Information | 1 | 3D | 2 | c | m3D-2c | The correct answer is “Proposal.” A request for Proposal (RFP) is a formal document inviting suppliers to submit detailed bids beyond pricing. It typically requires suppliers to outline their approaches, methodologies, timelines, and qualifications to meet the project’s needs. A request for Price (RFP) or Request for Quote (RFQ) focuses mainly on pricing. A request for Information (RFI) gathers preliminary information but does not request detailed proposals.
24 | 273 | You are managing a bridge reconstruction project after a tragic collapse. The procurement process has been designed with a strong incentive for early completion. However, you must ensure that safety is not compromised. How would you structure the procurement contract to balance speed and safety effectively? | Use a cost-reimbursable contract with a penalty clause for delays | Implement a lump-sum contract with a strong financial incentive for early completion and safety standards | Choose a time-and-material contract with no incentive for early completion. | Opt for an FIDIQ contract with flexible delivery times and open safety inspections. | 2 | 3D | 2 | c | m3D-2c | The lump-sum contract incentivises early completion while ensuring the financial reward does not compromise safety. The other options are incorrect because a cost-reimbursable contract does not necessarily incentivise early completion. A time-and-material contract permits flexibility but does not encourage early delivery. FIDIQ contracts are typically utilised when delivery times are less fixed, which is unsuitable for a project with critical deadlines.
3 | 274 | You are the project manager for a pharmaceutical company. You are currently working on a project for a new drug your company is creating. A recent change in a law governing drug testing will impact your project and change your project scope. What is the first thing you should do as a project manager? | Create a documented change request. | Proceed as planned since the project will be grandfathered beyond the new change in the law. | Consult with the project stakeholders. | Stop all project work until the issue is resolved. | 1 | 4A | 2 | c | m3D-2c | Any change requests should be documented in the project’s change control system. The following options are incorrect because the new law will require changes to the project, and it may be inappropriate to consult with the project stakeholders, especially on a large project. Finally, it is because we do not know the impact of the change, and it may not justify halting the project work.
3 | 275 | Your team members have recently completed training on specialised equipment. This is one of the results you have gathered and documented. Which of the following outputs from the Direct and Manage Project Work process does this refer to? | Work performance data | Deliverable | Preventive action | Project documents updates | 2 | 4A | 2 | c | m3D-2c | The correct answer is "Deliverable" because the training completion represents a tangible output that contributes to achieving the project's objectives. In the context of the Direct and Manage Project Work process, deliverables are the primary outputs generated through project execution, including tangible or intangible items, such as training completions, that are delivered to fulfil project requirements. The other options are incorrect because work performance data refers to raw data about the project's progress, preventive action refers to measures taken to reduce potential risks, and project documents updates involve changes to project-related documentation, which does not apply in this context.
3 | 276 | You report on project elements such as schedule status, deliverables completion, lessons learned, and resource utilisation. Which of the following outputs of the Direct and Manage Project Work does this describe? | Project management plan updates | Project documents updates | Preventive action | Work performance data | 4 | 4A | 2 | c | m3D-2c | Work performance data includes elements such as schedule status, the status of deliverables completion, lessons learned, and resource utilisation.
3 | 277 | You are overseeing a construction project for a residential building. Your client has recently requested a change to the lighting system, which could elevate project risks and costs. What should be your initial course of action? | Raise the issue to the project sponsor | Issue a Change Request | Update the project risk register | Analyse the impacts of the change | 4 | 4A | 2 | c | m3D-2c | The first action after receiving any change request is to analyse the impacts. After comparing the effects to the plan, you may need to issue a change request to modify the project scope. Once you know the effects of the change, you can also raise the issue with the project sponsor.
3 | 278 | The new cloud computing project was progressing well when Tammy, the project manager, received a call from an irate stakeholder who claimed that several issues within the project were not being addressed or receiving sufficient visibility. Tammy knew there was an issue log containing status information on these problems, so she was unsure why the stakeholder was unaware of it. What would be the most appropriate action for Tammy? | Tammy should tell the stakeholders they need to review the issue log to see if they want to know the latest status on a given problem. | Tammy should forward the stakeholder a copy of the issue log. | Tammy should analyse whether an issue with the project management information system prevented people from effectively accessing and interpreting the issue log. | Tammy does not need to act since she has executed everything correctly. | 3 | 4A | 2 | c | m3D-2c | Just because a process exists for documenting and updating issues does not mean it is effective. Tammy should analyse whether there are problems with the process and make any needed updates. Forwarding a copy of the log and telling the stakeholder to review it may work in the short run, but if there is an issue with the process, it will not fix the problem. Taking no action will annoy the stakeholders further and will not solve the problem.
3 | 279 | You are managing a construction project. After you create the schedule performance baseline, your project customer, who is external to your company, approaches you about adding new items to the project scope. Which of the following documents will you ask the customer to issue? | Change request | Project scope baseline | Project charter | Project scope statement | 1 | 4A | 2 | c | m3D-2c | Since this is an external customer, the only document it can create is a change request. The project manager or sponsor is responsible for the rest of the options. Changes must be formally controlled using the change control system.
3 | 280 | Your organisation utilises Scrum for all software development projects. Susan is a project team member developing software applications for years. She knows her routine, her approach to software development, and the complex processes she has evolved over time to explain in planning meetings. What type of knowledge does Susan have? | Tacit knowledge | Explicit knowledge | Factual knowledge | Experiential knowledge | 1 | 4A | 2 | c | m3D-2c | Susan has tacit knowledge, which has been gained through experience and is not easy to communicate or explain quickly to others. The other options are incorrect. Explicit knowledge is factual and easy to explain to others. Factual and experiential knowledge are not project management terms used to describe the knowledge management process.
3 | 281 | As a project manager in a large construction firm, you oversee a project that includes technical and interpersonal complexities. During the project, a senior engineer with vast tacit knowledge retires. Which action would best mitigate the loss of this tacit knowledge? | Archive all project documents in the organisation’s project management system. | Interview the engineer and document their insights into a lesson-learnt register. | Assign the engineer’s responsibilities to another team member and move forward. | Rely solely on the formal reports and data the engineer submitted during the project. | 2 | 4A | 2 | d | m3D-2d | Conducting an interview with the engineer and documenting their insights helps capture valuable tacit knowledge that is not easily documented in formal reports. This proactive approach to knowledge management ensures that informal knowledge, like insights and experience, is preserved. The other options are wrong because simply archiving documents misses the personal insights, assigning tasks to others does not capture knowledge, and relying solely on formal reports disregards the richness of tacit knowledge that cannot be formalised easily.
3 | 282 | Due to a lack of structured communication channels, the team struggles to share tacit knowledge in their construction project. As the project manager, what is the best way to facilitate the transfer of tacit knowledge within the team? | Organise weekly team meetings to go over project documentation. | Establish a community of practice where team members can share their experiences and lessons informally. | Mandate that all team members submit detailed reports on their work weekly | Hire external consultants to document the team’s informal knowledge | 2 | 4A | 2 | d | m3D-2d | Establishing a community of practice encourages informal collaboration and knowledge sharing, which is critical for transferring tacit knowledge, such as experiences and insights. The other options are wrong because weekly meetings may focus more on explicit knowledge, reports are primarily used for explicit knowledge, and hiring external consultants is unnecessary when the team can share their knowledge through peer interactions.
3 | 283 | May, the project manager, realises that some of the subsidiary plans in her project management plan now have incorrect data due to a change within the project scope. What should May do with the subsidiary plans already approved by her project sponsor? | Create a risk response for the project plans that are now incorrect. | Notate the project plan as being incorrect and why. | Communicate with the project sponsor and stakeholders about the incorrect plan. | Create a change request to correct the project plan. | 4 | 4A | 2 | d | m3D-2d | “Create a change request to correct the project plan” is the best answer of all the choices presented because changes to project documents and plans require change requests. The other options are wrong because creating a risk response or notating the project plan is not viable. The plan contains erroneous information that should be corrected. Lastly, May can communicate the error to the project sponsor, but she is not likely to do so with the stakeholders. In addition, the communication does not update the mistake in the plan.
3 | 284 | You are managing a construction project. After you have created the schedule performance baseline, your project customer, external to your company, approaches you about adding some new items to the project scope. Which one of the following documents will you ask the customer to issue? | Change request | Project scope baseline | Project charter | Project scope statement | 1 | 4A | 2 | d | m3D-2d | Since this is an external customer, the only document it can create is a change request. The rest of the options are the project manager's or project sponsor's responsibility. Changes must be formally controlled using the change control system.
3 | 285 | You have just received approval from the change control board to implement a few change requests. What process are you going to execute for that to happen? | No process is needed | Direct and Manage Project Work | Perform Integrated Change Control | Monitor and Control Project Work | 2 | 4A | 2 | e | m3D-2e | “Direct and Manage Project Work” is correct because approved change requests are executed through the Direct and Manage Project Work process. The other options are incorrect because project management is conducted through processes: the Perform Integrated Change Control process is used to assess the change requests and not to execute them, and the Monitor and Control Project Work process generates changes but does not implement them requests.
3 | 286 | You are a project manager for a growing dairy farm business. It offers organic dairy products regionally and is expanding its operations to the West Coast. It is in the process of purchasing and leasing dairy farm businesses to get operations underway. The subproject manager in network operations has reported some hardware problems to you. You are also having problems coordinating and integrating other elements of the project. Which of the following statements is true? | You are in the Direct and Manage Project Work process. | Your project team does not have the skills and knowledge needed to perform this project. | You are in the norming stage of team development. | Your project team could benefit from some team-building exercises. | 1 | 4A | 2 | e | m3D-2e | The most challenging aspect of the Direct and Manage Project Work process is coordinating and integrating all the project elements.
3 | 287 | Your team members have just completed training on specialised equipment. This is one of the work results you have gathered and recorded. Which of the following outputs of the Direct and Manage Project Work process does this describe? | Work performance data | Deliverable | Preventive action | Project documents updates | 2 | 4A | 2 | e | m3D-2e | Deliverables can be intangibles, such as the completion of training.
3 | 288 | You report on project elements such as schedule status, deliverables completion, lessons learnt, and resource utilisation. Which of the following outputs of the Direct and Manage Project Work does this describe? | Project management plan updates | Project documents updates | Preventive action | Work performance data | 4 | 4A | 2 | e | m3D-2e | Work performance data includes elements such as schedule status, the status of deliverables completion, lessons learned, and resource utilization.
3 | 289 | ______ motivation causes people to do something for a reward or to avoid a penalty. | Derived | Intrinsic | Extrinsic | Primary | 3 | 4A | 2 | e | m3D-2e | The correct answer is “Extrinsic”. Extrinsic motivation drives people to act to gain a reward or avoid a penalty. This type of motivation comes from external sources, such as money, recognition, or avoiding negative consequences. Intrinsic motivation comes from internal satisfaction or personal interest in the task. Derived and primary are not commonly used terms in this context.
13 | 290 | What is the name of a quality planning technique that involves comparing the results of similar activities? | Brainstorming | Benchmarking | Cost-benefit analysis | Quality metrics | 2 | 4A | 2 | e | m3D-2e | Benchmarking is the correct answer because benchmarking is a quality planning technique that compares a project's practices, products, or services with those of some reference projects to learn, improve, and create the basis for measuring performance. Brainstorming is incorrect because you can always brainstorm, but it does not have to compare the results of similar activities. Cost-benefit analysis is incorrect because, although it is a quality planning technique, it involves striking a balance between cost and benefit (which are not similar). Quality metrics are incorrect because quality metrics are not quality planning techniques; these are output items of the quality planning process.
13 | 291 | What about flowcharts is not true? | They can be used to understand and estimate the cost of quality for a process. | They can help in improving processes. | They can be used to identify points where quality defects may occur. | They help determine the frequency of defects from different product attributes during inspection. | 4 | 4A | 2 | e | m3D-2e | “They help determine the frequency of defects from different product attributes during inspection” is the correct answer because flowcharts are not used to determine this frequency. The other options are incorrect because all three are factual statements about flowcharts.
13 | 292 | You are the project manager of the Sports School project. Your supervisor has asked you to make some self-checks and inspections before the stakeholders ask for a formal inspection. It is time to perform which process? | Plan Quality | Perform Quality Control | Perform Quality Assurance | Manage Quality | 4 | 4A | 2 | e | m3D-2e | The correct answer is "Manage Quality" because this process involves proactive quality management activities, such as self-checks, inspections, and process improvements, to ensure the project meets quality standards before formal stakeholder inspections. "Plan Quality" is incorrect because it focuses on defining quality requirements and standards, not performing checks. "Perform Quality Control" is incorrect because it involves monitoring and validating deliverables against quality standards after production, not during the preparation phase. "Perform Quality Assurance" is outdated terminology replaced by "Manage Quality" in current project management practices.
13 | 293 | You are managing a software project with limited development resources. The QA department has discovered many defects in the product, and the project sponsor is very concerned about this. You want the maximum number of defects repaired with minimal effort and cost. Which quality-control tool will you use before you direct the project team's efforts to fix specific problems? | Control chart | Cause and effect diagram | Inspection | Scatter diagram | 2 | 4A | 2 | e | m3D-2e | The cause-and-effect diagram is the correct answer because it can identify the potential effects of defects and start fixing them with the worst and most unacceptable effects. However, the cause-and-effect diagram is incorrect because it plots the results to determine whether they are within acceptable limits. Inspection is incorrect because it determines whether a product conforms to a standard. Similarly, the scatter diagram is wrong because it finds the relationship between two variables, such as cause and effect or two causes.
13 | 294 | Which of the following statements about Ishikawa diagrams in the Identify Risks process is false? | Ishikawa diagrams are also called cause-and-effect diagrams. | Ishikawa diagrams are also called fishbone diagrams. | Ishikawa diagrams are part of this process's diagramming tool and technique. | Ishikawa diagrams show the steps needed to identify the risk. | 4 | 4A | 2 | e | m3D-2e | Cause-and-effect diagrams, also known as Ishikawa or fishbone diagrams, show the relationship between problems' effects and their causes. Kaoru Ishikawa developed these diagrams.
13 | 295 | Which of the following best characterises Six Sigma? | Stipulates that quality must be managed in | Focuses on process improvement and variation reduction by using a measurement-based strategy | Asserts that quality must be a continuous way of doing business | Focuses on improving the quality of the people first, then improving the quality of the process or project | 2 | 4A | 2 | e | m3D-2e | Six Sigma is a measurement-based strategy focusing on process improvement and reducing variation by applying Six Sigma methodologies to projects.
13 | 296 | Which document summarises the current quality status of a project and provides recommendations for improvement? | Risk Register | Quality Report | Scope Baseline | Project charter | 2 | 4A | 2 | e | m3D-2e | The correct answer is "Quality Report" because it communicates the quality status, highlights issues, and provides actionable recommendations. The other options are incorrect as they serve different purposes in project management.
13 | 297 | Which quality management tool involves identifying the underlying causes of problems or defects? | Benchmarking | Flowcharts | Root Cause Analysis | Quality Audits | 3 | 4A | 2 | e | m3D-2e | The correct answer is "Root Cause Analysis" because it identifies the underlying causes of issues. The other options are incorrect as they focus on different aspects such as comparing processes, illustrating workflows, or assessing compliance.
13 | 298 | What is the primary purpose of a requirements traceability matrix in quality management? | Establish links between requirements and tests | Identify project quality risks | Define the impact of quality requirements on project schedule | Outline resource allocation according to quality requirements | 1 | 4A | 3 | a | m3D-3a | The correct answer is "Establish links between requirements and tests" because traceability matrices ensure comprehensive coverage of requirements in testing. The other options are unrelated to this purpose.
13 | 299 | Which quality management tool helps visually map out potential causes of a problem across different categories? | Matrix Diagram | Scatter Diagram | Histogram | Fishbone Diagram | 4 | 4A | 3 | a | m3D-3a | The correct answer is "Fishbone Diagram" because it visually maps potential causes of problems across categories. The other options represent different data analysis tools used in quality management.
22 | 300 | Which project management document helps in tracking and managing changes related to risk responses? | Risk register | Risk matrix | Risk map | Risk assessment form | 1 | 4A | 3 | a | m3D-3a | Risk register is the correct answer. The risk register is a project management document that records all identified risks, their status, and actions taken to manage them. It is a key tool for tracking risks throughout the project lifecycle. The other options are incorrect because the risk matrix is a tool used to assess the severity and likelihood of risks but does not track the status of risks. The risk map visually represents risks but also does not track their status. Lastly, the risk assessment form is used to evaluate risks but not to monitor their progress.
22 | 301 | What are some of the tools and techniques used in implementing risk responses? | Risk analysis and selection | Cost estimation techniques | Resource allocation methods | Expert judgment and influencing skills | 4 | 4A | 3 | a | m3D-3a | Expert judgment and influencing skills are the correct answer. These tools and techniques are crucial in project risk management as they help in identifying potential risks and determining the best ways to address them, based on the experience and insights of experts. Risk analysis and selection is part of the risk management process but not a set of tools and techniques for implementing risk responses. Cost estimation techniques are used in budgeting and financial planning rather than risk management and resource allocation methods is related to managing project resources and not directly to risk management.
22 | 302 | What is the most likely outcome when planned risk responses are not implemented during the execution phase? | Increased project budget | Improved project schedule | Identified risks become actual issues | Enhanced stakeholder communication | 3 | 4A | 3 | a | m3D-3a | Identified risks become actual issues. When planned risk responses are implemented effectively, the main outcome is that potential risks that were identified and planned for are managed and controlled, preventing them from becoming actual problems that affect the project. This means that the team is proactive in addressing issues before they escalate. Increased project budget is incorrect because effective risk management typically aims to control costs and prevent budget overruns. Improved project schedule is not the most direct outcome of risk response implementation, although it can be a secondary benefit. Enhanced stakeholder communication is not the primary outcome of risk response implementation.
22 | 303 | Which of the following statements best describes the implementation of risk responses? | It involves creating risk registers. | It translates decisions made during risk management planning into action. | It is limited to the planning phase of the project. | It focuses on avoiding all project risks. | 2 | 4A | 3 | a | m3D-3a | It translates decisions made during risk management into actionable steps. Risk management planning is about taking the decisions made during the risk assessment process and detailing them into specific, actionable steps that can be implemented throughout the project. Creating risk registers is incorrect because it is just one part of risk management planning, not the entire process. The other options are incorrect because risk management planning spans the entire project lifecycle, not just the planning phase, and it is unrealistic to avoid all project risks.
22 | 304 | Which outcome is most likely when risk responses are not monitored effectively? | Risks are escalated to opportunities | Risk mitigation plans are redundant | New risks emerge without control | Risk status remains unknown | 4 | 4A | 3 | b | m3D-3b | The correct answer is "Risk status remains unknown" because monitoring risk responses ensures that the status of risks is tracked, their responses are implemented, and adjustments are made as needed. Without effective monitoring, the project team would have no insight into whether risks are being managed, mitigated, or escalating, leaving their status uncertain. The other options are wrong because lack of monitoring would likely result in unmanaged risks, not escalation into positive opportunities. Furthermore, risk mitigation plans are not rendered redundant by poor monitoring; instead, they become ineffective because their implementation cannot be verified or adjusted based on real-time project conditions. Lastly, while poor risk monitoring might lead to the late identification of new risks, the emergence of new risks is not a direct outcome of failing to monitor risk responses. New risks can emerge in any project, but they require a separate identification and management process, which is unrelated to monitoring existing risk responses.
25 | 305 | You are a project manager for Dakota Software Consulting Services. You are working with a major retailer that offers its products through mail-order catalogues. The company is interested in knowing customer characteristics, the amounts of first-time orders, and similar information. As a potential bidder for this project, you worked on the RFP response and submitted the proposal. When the selection committee received the RFP responses from all the vendors bidding on this project, they used a weighted system to select. This is a part of which tool and technique? | A proposal evaluation technique in the Conduct Procurements process | A seller proposal technique in the Conduct Procurements process | A make-or-buy decision technique in the Conduct Procurements process | A procurement negotiations technique in the Conduct Procurements process | 1 | 4A | 3 | b | m3D-3b | Weighted systems are a type of proposal evaluation technique, which is part of the data analysis tool and technique used to evaluate vendors based on selection criteria defined by the organisation.
25 | 306 | You are a project manager overseeing a large-scale infrastructure project. You have chosen to use the “advertising to many potential suppliers” approach for procurement. What is the primary advantage of using this method in your procurement process? | Reduces the need for extensive evaluation processes. | Increases competition, leading to better pricing and quality. | Establishes strong relationships with preferred suppliers. | Guarantees the use of established, reliable suppliers. | 2 | 4A | 3 | b | m3D-3b | Advertising to many potential suppliers increases competition, which can result in better pricing, quality, and more innovative solutions. The other options are wrong because the evaluation process may become more complex with more bids; establishing strong relationships is more aligned with the “preferred supplier” approach, and this approach does not guarantee that only reliable suppliers will be chosen.
25 | 307 | During a construction project, you are tasked with selecting a supplier. You decide to approach several qualified suppliers. What is the leading risk associated with this approach? | Potential delays in procurement due to a complex selection process. | Over-reliance on one preferred supplier. | Limited options for competitive pricing. | Lack of transparency in the bidding process. | 1 | 4A | 3 | b | m3D-3b | Approaching several qualified suppliers can increase the complexity of the selection process, potentially leading to delays. The other options are wrong because over-reliance is associated with the “preferred supplier” approach; multiple suppliers encourage competition, and this approach promotes transparency and fairness.
25 | 308 | In a high-stakes construction project, you conduct a bidder conference to ensure fairness in procurement. What is the key benefit of this conference? | Ensures all bidders provide the same price. | Guarantees that the most qualified bidder is selected. | Provides a platform to address ambiguities and ensure all bidders have equal access to project information. | Prevents the need for contract renegotiations later in the project. | 3 | 4A | 3 | b | m3D-3b | The primary purpose of a bidder conference is to clarify project details and ensure all potential bidders have equal access to information, promoting fairness. The other options are wrong pricing varies among bidders, the conference itself does not guarantee qualification, and it does not necessarily prevent future renegotiations.
25 | 309 | Your team is managing a public infrastructure project. Which of the following standard form contracts most likely apply to your project in Singapore? | FIDIC Conditions of Contract for Plant and Design-Build. | JCT Design and Build Contract. | Singapore Institute of Architects Lump Sum Contract. | Public Sector Standard Conditions of Contract (PSSCOC). | 4 | 4A | 3 | b | m3D-3b | The PSSCOC is the standard form of contract used for public infrastructure projects in Singapore. The other options are wrong because FIDIC is typically used for international projects, JCT contracts are more common in the UK, and the Singapore Institute of Architects (SIA) contract applies more to building projects, not public infrastructure.
25 | 310 | As a project manager, you must ensure the procurement process aligns with project management principles. Which principle is most critical when selecting suppliers through a competitive bidding process? | Simplicity | Transparency | Cost-saving | Speed | 2 | 4A | 3 | b | m3D-3b | Transparency is critical to ensure fairness in a competitive bidding process, giving all suppliers equal opportunity. The other options are wrong because procurement processes can be complex, cost-saving is important but secondary to fairness and transparency, and speed should not compromise the integrity of the process.
25 | 311 | You are managing a design-and-build construction project with multiple stakeholders. You use the FIDIC Conditions of Contract for Design-Build and Operate Projects. Why is this contract particularly suitable for your project? | It simplifies the procurement process for local suppliers. | It is designed for projects requiring the contractor to operate the completed facility. | It provides a framework specific to large public infrastructure projects. | It is commonly used for domestic residential projects. | 2 | 4A | 3 | c | m3D-3c | FIDIC Conditions of Contract for Design-Build and Operate Projects are tailored for scenarios where the contractor designs, builds, and operates the facility. The other options are wrong because FIDIC contracts are more suited for international use, the PSSCOC is better for public infrastructure in Singapore, and domestic residential projects often use different contracts.
25 | 312 | During a procurement review, you find that the project team did not adequately document lessons learned from the procurement process. What is the primary risk associated with this omission in future projects? | Difficulty in selecting appropriate suppliers, knowing that some suppliers have poor quality. | Inability to identify successful negotiation strategies without previous knowledge. | Increased likelihood of cost overruns without cost understanding. | Repetition of past procurement mistakes. | 4 | 4A | 3 | c | m3D-3c | Failing to document lessons learned increases the risk of repeating mistakes in future procurement processes. The other options are wrong because supplier selection issues are not directly related to lessons learned, negotiation strategies are only part of what is captured, and while cost overruns are possible, they are not the primary risk here.
25 | 313 | The seller proposals, an input item for Conduct Procurement, are created during which process? | Conduct Procurement | Plan Procurements | Control Procurement | Close Procurement | 1 | 4A | 3 | c | m3D-3c | Conduct Procurement is the correct answer. The other options are incorrect because sellers send proposals in response to buyers looking for sellers during the Conduct Procurements process. There is no standard process called Close Procurements, as procurements are closed in the Control Procurements process.
25 | 314 | In a competitive procurement process, why is advertising to a large number of suppliers considered beneficial? | It guarantees reliable suppliers will be chosen. | It reduces the need for evaluations. | It increases competition, leading to better pricing and innovation. | It ensures all suppliers are treated equally. | 3 | 4A | 3 | c | m3D-3c | The correct answer is "It increases competition, leading to better pricing and innovation" because a larger pool of suppliers promotes competitive offers. The other options are incorrect because reliability is not guaranteed, evaluations are still required, and equal treatment depends on the procurement process.
25 | 315 | What is the key risk if lessons learned from procurement are not documented? | Repetition of past mistakes | Higher project costs | Difficulty in identifying reliable suppliers | Increased negotiation failures | 1 | 4A | 3 | c | m3D-3c | The correct answer is "Repetition of past mistakes" because failing to document lessons learned makes it likely that errors will recur. The other options are incorrect because negotiation strategies and supplier reliability depend on other aspects of procurement planning, and while higher costs are possible, they are not the primary risk.
16 | 316 | You are the project manager for Heartthrobs by the Numbers Dating Services. You are working on an updated Internet site that will display pictures as well as short bios of prospective heartbreakers. You have just completed your project team assignments including the project team directory, and you published the resource calendar. Which process are you in? | Plan Resource Management | Manage Team | Develop Team | Acquire Resources | 4 | 4B | 3 | c | m3D-3c | Resource calendars and project team assignments (which includes the project team directory are outputs of the Acquire Resources process.
16 | 317 | Which of these is an output from the Acquire Resources process? | Organisational chart | Project team assignments | RAM | Staffing Management Plan | 2 | 4B | 3 | d | m3D-3d | After determining elements such as the roles and responsibilities, reviewing recruitment practices, and negotiating for staff, project team members are assigned to project activities as part of the Acquire Resources process.
16 | 318 | Harrold is the project manager for his organisation, and he has seven people on his project team. Who is responsible for executing the project plan and creating the project deliverables? | Project lead | Project manager and the project team | Project manager | Project team | 4 | 4B | 3 | d | m3D-3d | The project team members are responsible for executing the project plan and creating the project deliverables. Project lead is incorrect because the project lead isn’t the only role responsible for executing the plan. Project manager and the project team is tempting, but it is incorrect, because the project team is responsible for executing the plan—that is, doing the work to create the project.
16 | 319 | Your website development project is newly underway. The team appears to be in the “storming” stage, with several members insisting that the process occurs in a certain way and others unwilling to participate after their views were overruled. You recognise that cooperation and collaboration are imperative for the team to achieve the sponsor’s goal of a working prototype within the next few weeks. What is the most helpful action for you to take? | Enrol the team in a course on emotional intelligence so that they will learn to be sensitive to each other’s feelings. | Hold a team meeting and facilitate the creation of a team charter that includes ground rules. | Advise the sponsor that there may be a delay in the prototype delivery. | Hold a networking event so that team members can get to know each other better. | 2 | 4B | 3 | d | m3D-3d | The key to this question is that a deliverable is due soon, and the team conflict is putting that goal in jeopardy. The most efficient action for you to take is to have the team agree on ground rules that they can then hold themselves to. A team charter typically includes operating guidelines, decision-making criteria, and communication expectations. Enrolling a team in training may be of use long-term, along with a networking event but will not help the immediate situation. It is never a good idea to inform the sponsor there may be a delay due to a situation that you, as the project manager, are ultimately accountable for.
16 | 320 | What is the generally preferred approach for resolving conflicts involving differing opinions? | Avoiding | Competing | Accommodating | Collaborating | 4 | 4B | 3 | d | m3D-3d | Collaborating is the preferred approach for resolving conflicts as it involves working together to find a mutually beneficial solution. This fosters team cohesion and ensures all perspectives are considered. Avoiding ignores the conflict, competing creates tension, and accommodating may lead to one party feeling unheard or unvalued.
16 | 321 | What is the main function of a team charter in the dynamics of project management? | To serve as a legal document binding team members to the project. | To outline the individual tasks and deadlines for each team member. | To define the team’s vision, objectives, norms, roles, and responsibilities. | To document the financial compensation for each team member. | 3 | 4B | 3 | d | m3D-3d | A team charter defines the team’s vision, objectives, norms, and roles. It serves as a foundational document that guides the team’s behaviour and helps ensure everyone is aligned with the project goals.
16 | 322 | In situational leadership, when is the visionary style most suitable? | When the team needs guidance and support. | When high performance standards need to be set and achieved. | When a new direction and shared vision are required. | When building strong relationships is a priority. | 3 | 4B | 3 | d | m3D-3d | The visionary leadership style is most effective when a new direction and shared vision are required. It involves inspiring and guiding the team towards a new future with a compelling vision. “When the team needs guidance and support” aligns more with coaching leadership. “When building strong relationships is a priority” aligns with affiliative leadership. “When tasks are clearly defined and need monitoring” aligns with directive leadership.
16 | 323 | Which leadership style relies on rewards and punishments to motivate team members? | Charismatic | Transformational | Transactional | Laissez-Faire | 3 | 4B | 3 | e | m3D-3e | The transactional leadership style relies on rewards and punishments to motivate team members. This style focuses on structured tasks and clear expectations with contingent rewards. The other options are incorrect as charismatic leaders inspire and energise followers through their personality and vision, laissez-faire leaders provide minimal supervision and allow team members to make decisions, and transformational leaders inspire and motivate.
16 | 324 | According to Ouchi’s Theory Z, what does a supportive work environment emphasise? | Financial incentives | Employee well-being and job security | Coercion and strict oversight | Intrinsic motivation | 2 | 4B | 3 | e | m3D-3e | Theory Z emphasises a strong company philosophy, long-term employment, and a supportive work environment focusing on employee well-being and job security. This approach fosters loyalty and enhances job satisfaction.
16 | 325 | What does McClelland’s Acquired-Needs Theory highlight as significant motivators? | Basic physiological and survival needs. | Security and safety in the workplace. | Desires for achievement, social belonging, and influence over others. | Personal satisfaction and self-fulfilment from work. | 3 | 4B | 3 | e | m3D-3e | McClelland’s Acquired-Needs Theory highlights that individuals are driven by three primary needs which are the need for achievement, the need for affiliation, and the need for power. These needs influence their motivation and behaviour at work. The other options are incorrect as they are part of Maslow’s Hierarchy of Needs.
16 | 326 | In project resource acquisition, what is the primary purpose of collaborating with functional managers within the organisation? | To ensure the right personnel are assigned | To better estimate project costs | To create a collaborative culture | To ensure resource availability to the departments | 1 | 4B | 3 | e | m3D-3e | The primary goal of resource acquisition is to obtain the necessary personnel and resources needed to complete the project tasks effectively.
16 | 327 | You are the project manager for GHB Project. You have served as a project manager for your organisation for the past ten years. Most of your projects come in on time and on budget. Part of your planning is to consider when project team members are available for doing the project work. Which one of the following will detail team members’ availability for your project? | Resource management plan | Project calendar | Resource calendar | Gantt chart | 3 | 4B | 3 | e | m3D-3e | The resource calendar defines when resources, both people and physical resources, are available for utilisation in the project. Resource management plan is incorrect as the resource management plan defines how resources will be managed, not when resources are available. Project calendar is incorrect as the project calendar defines when the project work may take place. Gantt chart is incorrect as the Gantt chart is a scheduling tool of when activities will take place in the project.
16 | 328 | During the “Performing” stage in the Tuckman Model, what characterises the team’s behaviour? | High collaboration and constructive interaction | Introduction of team members | Conflict resolution | Reflection on achievements | 1 | 4B | 3 | e | m3D-3e | During the “Performing” stage, team members exhibit high collaboration and constructive interaction. The team operates at a high level of efficiency and productivity, with members working well together and making progress towards their goals.
16 | 329 | How does understanding diverse personality types contribute to team effectiveness? | It encourages uniformity in thinking and problem-solving. | It promotes a balanced and complementary team dynamic. | It is an essential input for the development of the team charter | It reduces the need for effective communication. | 2 | 4B | 3 | e | m3D-3e | Understanding diverse personality types helps in creating a balanced and complementary team environment. It allows project managers to leverage the strengths of each personality type, leading to a more effective and harmonious team.
16 | 330 | To overcome potential clashes between different social styles, what should team members develop? | Conflict avoidance strategies | Uniform communication styles | A single leadership style | Self-awareness and adaptability | 4 | 4B | 3 | e | m3D-3e | Self-awareness and adaptability are recommended strategies to overcome potential clashes between different social styles. Understanding one’s own social style and being adaptable to others’ styles can improve communication and collaboration within the team. The other options are incorrect because avoiding conflicts does not address the underlying issues and can lead to unresolved tensions. Similarly, enforcing a single communication style can be restrictive and ineffective, and different situations may require different leadership styles for effective management.
16 | 331 | You are the project manager for a cable service provider. Your team members are amiable with each other and are careful to make project decisions jointly. Which of the following statements is true? | They are in the forming stage of team development. | They are in the norming stage of team development. | They are in the storming stage of team development. | They are in the adjourning stage of team development. | 2 | 4B | 2 | a | m4A-2a | Teams in the norming stage of team development exhibit affection and familiarity with one another and make joint decisions.
16 | 332 | You are the project manager for a cable service provider. Your project team is researching a new service offering. They have been working together for quite some time and are in the performing stage of team development. A new member has been introduced to the team. Which of the following statements is true? | The team will start all over again with the storming stage. | The team will continue in the performing stage. | The team will start all over again with the forming stage. | The team will start all over again at the storming stage but quickly progress to the performing stage. | 3 | 4B | 2 | a | m4A-2a | The introduction of a new team member will start the formation and development of the team all over again with the forming stage.
16 | 333 | According to Tuckman, which of the following is not one of the stages of team development? | Delegating | Performing | Forming | Norming | 1 | 4B | 2 | a | m4A-2a | According to Tuckman, the stages of team development are Forming, Storming, Norming, Performing, and Adjourning.
16 | 334 | Which aspect of emotional intelligence involves understanding and responding to the emotions of others? | Self-awareness | Self-management | Social awareness | Relationship management | 3 | 4B | 2 | a | m4A-2a | Social awareness in emotional intelligence involves recognising and understanding one’s own emotions as well as the emotions of others. It is key to developing empathy and effectively managing interpersonal relationships.
16 | 335 | Conflict is more likely to arise in which of the following projects? | Small projects with low budgets | High-stake, visible projects | Projects with experienced team members | Projects with clear objectives | 2 | 4B | 2 | a | m4A-2a | Conflict is more likely to arise in large projects with diverse teams due to varying perspectives, goals, and communication styles. Managing such teams requires effective conflict resolution strategies.
16 | 336 | Which area of emotional intelligence involves understanding and recognising one’s own emotions? | Self-awareness | Self-management | Social awareness | Relationship management | 1 | 4B | 2 | a | m4A-2a | Self-awareness in emotional intelligence involves recognising and understanding one’s own emotions. This self-knowledge is fundamental to regulating behaviour and managing relationships effectively.
16 | 337 | Which of the following is not one of the conflict handling modes? | Competing/ Force/ Direct | Accommodating/ Smooth | Avoiding/ Withdraw | Coordinating/ Discuss | 4 | 4B | 2 | b | m4A-2b | Coordinating/ Discuss is not recognised as a specific conflict resolution style. Commonly acknowledged styles include competing, collaborating, compromising, avoiding, and accommodating.
16 | 338 | How does leadership differ from management? | Leadership is about control, while management is about empowerment. | Leadership focuses on the bottom line, while management focuses on relationships. | Leadership is about guiding and empowering, while management is about directing and controlling. | Leadership is short-term, while management is long-term. | 3 | 4B | 2 | b | m4A-2b | Leadership focuses on guiding and empowering team members, inspiring them towards achieving common goals. Management, on the other hand, involves planning, organising, and controlling resources to achieve these goals.
16 | 339 | Which habit from Covey’s framework emphasises taking responsibility for your actions and choices? | Seek First to Understand, Then to Be Understood | Be Proactive | Sharpen the Saw | Think Win-Win | 2 | 4B | 2 | b | m4A-2b | “Seek First to Understand, Then to Be Understood” is a habit from Stephen Covey’s framework that emphasises the importance of empathetic listening before expressing one’s own viewpoint. This habit fosters better communication and relationships.
16 | 340 | What is the focus of the affiliative leadership style? | Setting challenging goals and expectations | Active participation and involving the team in decision-making | Providing guidance and support for individual growth | Building strong relationships and fostering teamwork | 4 | 4B | 2 | b | m4A-2b | The affiliative leadership style focuses on building strong relationships and fostering team harmony. This style prioritises emotional bonds and a positive team atmosphere.
16 | 341 | What does the “Think Win-Win” habit encourage? | Collaboration and seeking mutually beneficial solutions | Setting challenging goals and expectations | Self-renewal through personal growth activities | Focusing on important tasks and time management | 1 | 4B | 2 | b | m4A-2b | The “Think Win-Win” habit encourages seeking mutually beneficial solutions and fostering a spirit of cooperation. It promotes the idea that agreements and solutions should benefit all parties involved.
16 | 342 | Which leadership style is described as “By working with others to identify needed changes, they empower others and guide changes through inspiration”? | Charismatic | Transformational | Transactional | Laissez-Faire | 2 | 4B | 2 | b | m4A-2b | The transformational leadership style is characterised by leaders working with others to identify needed changes, empowering others, and guiding changes through inspiration. Transformational leaders focus on creating a vision for the future, motivating and inspiring team members to achieve that vision, and fostering an environment of growth and innovation. The other options are incorrect. While charismatic leaders inspire and energise their followers, they do so more through their personal appeal rather than by systematically empowering others and guiding changes. Laissez-Faire leaders take a hands-off approach, providing minimal supervision and allowing team members to make their own decisions, which is different from actively guiding and inspiring change. Transactional leaders focus on structure, rewards, and penalties to manage their team, rather than inspiring and empowering them to drive change.
16 | 343 | What is Theory X in McGregor’s management theories? | The belief that workers inherently dislike their jobs and need strict oversight | The belief that workers are motivated by self-actualisation | The focus on employee well-being and community | The reliance on intrinsic motivation | 1 | 4B | 2 | b | m4A-2b | Theory X assumes that employees are naturally unmotivated and dislike working, leading to a management style that relies on control, direction, and even punishment to achieve organisational goals.
16 | 344 | You are managing a construction project involving a diverse team of engineers, architects, and contractors. During the storming stage, conflicts arise between the architects and engineers over design decisions. These conflicts threaten to delay the project. How should you respond to these changes to ensure compliance and project success? | Allow the team members to resolve the conflict on their own to build self-reliance | Implement a top-down decision-making process to quickly resolve the conflict | Facilitate a conflict resolution meeting to encourage open discussion and find a mutually agreeable solution | Replace the team members involved in the conflict to eliminate the issue | 3 | 4B | 2 | b | m4A-2b | Facilitating a conflict resolution meeting helps address the root causes of the conflict through open dialogue. This approach promotes understanding, cooperation, and a collaborative environment, essential for maintaining project momentum. A one-time comprehensive session might be overwhelming and less effective in addressing specific, evolving skill gaps. Allowing team members to choose training based on interest may not address the critical skill gaps needed for project success. Ignoring soft skills development can undermine teamwork, communication, and overall project efficiency.
16 | 345 | As a project manager for a high-rise building construction. Your team comprises members from different cultural backgrounds, and you notice communication barriers affecting team cohesion and productivity. Which team-building strategy should you implement to improve communication and collaboration among your culturally diverse team? | Focus on task-specific training to improve individual performance | Assign tasks based on cultural similarities to minimise conflicts | Conduct one-on-one meetings to address individual concerns | Organise regular team-building activities that promote cultural awareness and understanding | 4 | 4B | 3 |  | m4A-3 | Regular team-building activities focused on cultural awareness help team members understand and appreciate each other’s backgrounds, fostering better communication and collaboration. The other options are incorrect because task-specific training improves individual performance but does not address the communication barriers and team cohesion issues, assigning tasks based on cultural similarities can lead to segregation within the team and hinder overall collaboration, and one-on-one meetings are useful for individual concerns but do not address the broader issue of team communication and cohesion.
16 | 346 | Your construction project team includes individuals with varying levels of expertise and different motivational needs. To ensure that all team members are motivated and performing at their best, you need to apply a motivational theory that recognises these differences and tailors your approach accordingly. Which motivational theory should you apply to address the diverse needs of your team? | Maslow’s Hierarchy of Needs | Herzberg’s Two-Factor Theory | McClelland’s Acquired-Needs Theory | McGregor’s Theory X and Theory Y | 3 | 4B | 3 |  | m4A-3 | The correct answer is McClelland’s Acquired-Needs Theory because it recognises that individuals are motivated by different needs—achievement, affiliation, and power—which can be shaped by life experiences. By understanding these needs, you can tailor your management approach to support and sustain individual motivation. The other options are wrong because Maslow’s Hierarchy of Needs provides a general framework but may not address specific individual differences. Herzberg’s Two-Factor Theory focuses on job satisfaction and dissatisfaction but does not specifically address individual needs. McGregor’s Theory X and Theory Y presents contrasting views on employee motivation and management but does not provide a tailored approach for individual differences.
16 | 347 | As a project manager for a construction company, you are tasked with building a new office complex. Your initial plan involves utilising internal resources for the electrical work. However, an unexpected increase in internal projects has left your electrical team overcommitted. How should you adjust your resource acquisition strategy to address this issue? | Hire external electrical contractors to ensure the project timeline is met | Engage in a detailed cost-benefit analysis to justify reallocating the internal electrical team despite their current commitments | Implement a phased approach to electrical work, aligning it with the availability of the internal team to minimise disruption | Negotiate with the clients to extend the project deadline, allowing the internal team to complete the work | 1 | 4B | 3 |  | m4A-3 | Hiring external electrical contractors helps to maintain the project schedule without overburdening internal resources, aligning with the principles of effective resource management. The other options are incorrect. Engaging in a detailed cost-benefit analysis can justify resource reallocation but may not address immediate capacity issues or prevent delays. Implementing a phased approach may still cause overall project delays and disrupt coordination with other project tasks. Negotiating with clients to extend the project deadline risks client dissatisfaction and may affect the company’s reputation and future project opportunities.
16 | 348 | In a construction project, you are tasked with assembling a highly skilled team from within your organisation. However, key personnel are also critical to other ongoing projects. Which strategy would best ensure that you secure these resources without negatively impacting other projects? | Prioritising your project’s needs over others by asserting higher authority | Negotiating with other project managers to create a shared resource pool with clearly defined allocation schedules | Recruiting external contractors to replace the internal personnel, even if it exceeds the budget | Requesting the organisation to temporarily halt other projects to free up the necessary personnel | 2 | 4B | 3 |  | m4A-3 | Negotiating with other project managers to create a shared resource pool with clearly defined allocation schedules ensures that all projects can access the required expertise without overcommitting any single resource. The other options are wrong because prioritising your project can create conflicts and reduce overall organisational efficiency, recruiting external contractors can significantly increase costs, and halting other projects is impractical and can lead to organisational inefficiencies and conflicts.
16 | 349 | As a project manager for a construction project, you observe that your team’s morale is low, and productivity has declined. You decide to implement a reward and recognition system to motivate the team. What type of reward system would most effectively enhance team motivation and performance? | Individual bonuses based on personal performance metrics | Team-based rewards for achieving collective project milestones | Public recognition for the most productive team member | Extra vacation days for top-performing individuals | 2 | 4B | 3 |  | m4A-3 | Team-based rewards encourage collaboration and collective effort towards common goals, improving overall team performance and morale. Individual bonuses may foster competition rather than collaboration. Public recognition of one member can lead to resentment and undermine team cohesion. Extra vacation days for top performers may not address the root cause of low team morale and productivity.
16 | 350 | You manage a construction project with a highly diverse team, including members from various cultural backgrounds. While diversity brings valuable perspectives, it also leads to misunderstandings and conflicts. How can you leverage this diversity to enhance team performance and project outcomes? | Develop standard operating procedures that prioritise uniformity to minimise cultural misunderstandings and conflicts | Advocate for a culture-neutral approach where team members set aside cultural differences to maintain focus on project objectives | Facilitate ongoing cross-cultural training and create a continuous feedback loop to address and integrate diverse perspectives into team strategies | Strategically assign tasks based on an analysis of cultural strengths and weaknesses to optimise team efficiency and reduce potential conflicts | 3 | 4B | 3 |  | m4A-3 | Facilitating ongoing cross-cultural training and creating a continuous feedback loop allows team members to understand and appreciate diverse perspectives, integrating them into team strategies for better collaboration and innovation. The other options are incorrect because developing stringent standard operating procedures can stifle the creative and innovative benefits that diversity brings, advocating for a culture-neutral approach ignores the valuable insights that cultural diversity provides and does not address the root causes of misunderstandings, and strategically assigning tasks based on cultural strengths and weaknesses risks reinforcing stereotypes and missing out on the holistic advantages of a diverse team working collaboratively.
16 | 351 | In a large-scale infrastructure project, you observe that a key team member is consistently underperforming, which impacts the overall project schedule. As the project manager, how should you address this issue to improve performance while maintaining team morale? | Increase the oversight and have daily checks on the team member’s work to ensure deadlines are met | Reassign the team member to less critical tasks avoid discussing the performance issues directly | Replace the team member with another who has a proven track record | Provide specific, constructive feedback and offer additional support and resources to help the team member improve | 4 | 4B | 3 |  | m4A-3 | Providing specific, constructive feedback and offering additional support and resources directly addresses the root cause of underperformance, helping the team member improve while maintaining their morale and engagement. The other options are incorrect because increasing oversight and micromanagement can create a stressful work environment and diminish trust, reassigning the team member without addressing the issue directly does not solve the underlying problem and can lead to further issues, and replacing the team member without addressing performance issues does not provide an opportunity for improvement and can demoralise the team.
16 | 352 | In a construction project to build a new train line, nearby residents have raised numerous complaints about noise and traffic disruptions. As the project manager, you need to manage this conflict effectively. What initial step should you take? | Gather detailed information regarding the specific complaints from the residents to understand the extent and nature of the issues | Organise a community forum to openly discuss the residents’ concerns and potential mitigation measures | Deploy noise reduction technologies and traffic management strategies immediately to address the complaints | Conduct an internal review of the construction schedule to identify potential adjustments that could minimise disruptions | 1 | 4B | 3 |  | m4A-3 | Gathering detailed information regarding the specific complaints from the residents is the essential first step in understanding the exact nature and extent of the issues. This allows for a targeted and informed response. The other options are incorrect because organising a community forum is more effective after understanding the complaints, deploying noise reduction technologies and traffic management strategies without detailed information might not address the root causes effectively, and conducting an internal review of the construction schedule should follow the initial step of understanding the complaints in detail.
16 | 353 | As a project manager for a large-scale construction project, you have identified that some team members are highly motivated by achieving personal growth and learning new skills. Which approach should you take to motivate these team members? | Assign them repetitive tasks to ensure consistency | Provide opportunities for professional development and learning | Offer them financial incentives for completing tasks quickly | Implement a hierarchical structure with clear authority | 2 | 4B | 3 |  | m4A-3 | The correct answer is provide opportunities for professional development and learning because individuals motivated by personal growth will be more engaged and productive when given opportunities to learn and develop new skills. The other options are wrong because assigning repetitive tasks would not satisfy their need for growth. Offering financial incentives focuses on extrinsic motivation and may not address their intrinsic desire for learning. Implementing a hierarchical structure with clear authority might not align with their motivational drivers related to personal growth.
16 | 354 | You are managing a construction project that requires significant collaboration and teamwork among diverse professionals. Recently, there have been conflicts and a lack of cohesion within the team. To enhance team collaboration and create a more supportive work environment, you need to choose an appropriate motivational approach. Which motivational approach should you use to enhance team cohesion and collaboration? | Establish clear individual performance targets and rewards | Foster a sense of shared goals and collective responsibility | Implement regular team-building exercises and activities | Increase monitoring and control to ensure compliance | 2 | 4B | 4 |  | m4A-4 | The correct answer is to foster a sense of shared goals and collective responsibility because creating a cooperative and inclusive work environment encourages teamwork and positive interpersonal relationships, which are crucial for enhancing collaboration. Establishing clear individual performance targets and rewards may promote competition rather than collaboration. Implementing regular team-building exercises and activities can be beneficial, but it may not address the root causes of conflict and lack of cohesion as effectively as fostering shared goals. Increasing monitoring and control to ensure compliance can increase stress and reduce morale.
16 | 355 | You are managing a construction project that has experienced several unexpected challenges, including supply chain disruptions and regulatory changes. As a result, the team’s morale has declined, and there is a noticeable decrease in productivity. Which approach should you take to address both the immediate and long-term motivational needs of your team? | Conduct a thorough analysis of the challenges and provide transparent communication about the steps being taken | Implement a reward system based on individual contributions during the crisis period | Increase the overall budget to hire additional temporary staff to alleviate the workload | Schedule mandatory team-building retreats to improve team cohesion | 1 | 4B | 4 |  | m4A-4 | The correct answer is to conduct a thorough analysis of the challenges and provide transparent communication about the steps being taken because addressing the root causes of the challenges and maintaining open communication can help restore trust and motivation. Implementing a reward system based on individual contributions might foster competition rather than collaboration. Increasing the overall budget to hire additional temporary staff may not be feasible and does not address the motivational needs of the existing team. Scheduling mandatory team-building retreats might improve cohesion but does not directly address the immediate challenges and the need for transparent communication.
16 | 356 | During the initial phase of your construction project, you observe that some team members are highly motivated by career advancement opportunities, while others are more focused on work-life balance. To create a balanced motivational strategy that caters to these diverse needs, which approach should you implement? | Develop a personalised career development plan for each team member | Standardise work hours and offer uniform benefits to ensure fairness | Focus on team-wide incentives to promote collective success | Create flexible work arrangements and provide options for skill development | 4 | 4B | 4 |  | m4A-4 | The correct answer is to create flexible work arrangements and provide options for skill development because this approach caters to both the need for career advancement and work-life balance. Developing a personalised career development plan for each team member addresses only career-focused individuals. Standardising work hours and offering uniform benefits may not satisfy those seeking flexibility. Focusing on team-wide incentives promotes collective success but might not address individual motivational needs.
16 | 357 | You are overseeing a construction project with team members located in different regions. Despite technological tools, you notice a decline in team cohesion and communication quality. What strategy would most effectively enhance team cohesion and communication in a remote setting? | Increase the frequency of formal reporting to ensure accountability | Organise periodic face-to-face team-building events to strengthen relationships | Allow team members to choose their own communication tools to enhance comfort | Implement a communication schedule and encourage strict adherence to set times | 2 | 4B | 4 |  | m4A-4 | Periodic face-to-face events foster personal connections and strengthen relationships, enhancing overall team cohesion and communication when they return to remote work. The other options are incorrect as increasing formal reporting can add stress and reduce morale without necessarily improving cohesion, allowing team members to choose their own tools might lead to fragmentation and inefficiencies, and a rigid communication schedule may not account for the flexibility needed in a remote setting and can lead to decreased morale.
16 | 358 | In a high-stakes construction project, the project manager notices a growing sense of groupthink among team members, where everyone agrees without much discussion or challenge. How should the project manager address this situation to ensure diverse opinions and high-quality decision-making? | Continue with the consensus to avoid conflicts and maintain harmony | Encourage open discussions and actively solicit differing opinions | Make unilateral decisions to bypass groupthink | Focus on quick decision-making to keep the project on schedule | 2 | 4B | 4 |  | m4A-4 | Encouraging open discussions and differing opinions helps prevent groupthink and leads to better decision-making. The other options are wrong because avoiding conflicts by maintaining consensus can lead to poor decision-making and unforeseen challenges, making unilateral decisions does not leverage the team’s collective knowledge and can demotivate team members, and quick decision-making without thorough discussion can compromise the quality of decisions and project outcomes.
16 | 359 | In a construction project, you notice that team morale is low due to repeated conflicts and unresolved issues. What strategy should you employ to improve team morale and performance? | Implement regular check-ins and open discussions to address issues promptly | Ignore the conflicts and focus solely on project deadlines | Impose reasonable penalties to team members responsible for conflicts | Increase the workload to keep the team busy and see the need for teamwork | 1 | 4B | 5 |  | m4A-5 | Implementing regular check-ins and open discussions helps address issues promptly, improving team morale and performance. The other options are wrong because ignoring conflicts can lead to further issues, penalties can damage team relationships, and increasing the workload can exacerbate stress and decrease morale.
16 | 360 | You are managing a construction project where the team seems disengaged and lacks a clear understanding of the project goals. To align the team and enhance their commitment to the project’s objectives, you need to adopt a leadership style that provides clear direction and motivation. Which leadership style should you adopt to address this issue? | Visionary | Pace-setting | Democratic | Transactional | 1 | 4B | 5 |  | m4A-5 | The correct answer is visionary because this style involves setting a clear, compelling vision and effectively communicating it to inspire and align the team with the project goals. The other options are wrong because pace-setting focuses on high-performance standards and might increase pressure without addressing motivation and clarity. Democratic involves team participation but may not provide the strong direction needed. Transactional relies on rewards and punishments, which might not effectively address the underlying issues of disengagement and lack of understanding.
16 | 361 | As the project manager of a high-stakes construction project, your team is experiencing decreased motivation and engagement due to repetitive tasks and a lack of recognition for their hard work. You need to address these issues and enhance team motivation to ensure project success. Which approach should you adopt to effectively motivate your team and improve their engagement? | Increase financial bonuses for completing tasks | Assign more challenging and meaningful tasks | Implement stricter deadlines and penalties for delays | Provide free lunches and recreational facilities | 2 | 4B | 5 |  | m4A-5 | The correct answer is assign more challenging and meaningful tasks because intrinsic motivation, which is driven by personal satisfaction and interest, can be fostered by offering stimulating and challenging tasks. This approach aligns with motivational theories that suggest people are more engaged and committed when they find their work meaningful. The other options are wrong because increasing financial bonuses (extrinsic motivation) may provide short-term motivation but is less effective for long-term engagement. Implementing stricter deadlines and penalties can lead to increased stress and resentment, decreasing motivation. Providing free lunches and recreational facilities might improve the work environment but does not directly address the need for meaningful and challenging work.
16 | 362 | You are leading a project to construct a new office building. Your project team is highly skilled but lacks motivation and shows signs of low morale. Which of the following strategies would be most effective in enhancing team motivation and improving overall project performance? | Offering individual performance bonuses to top-performing team members | Developing a comprehensive team recognition and rewards system that acknowledges collective achievements | Rotating team members through different roles to maintain engagement | Implementing strict performance monitoring and providing regular feedback | 2 | 4B | 5 |  | m4A-5 | Developing a comprehensive team recognition and rewards system that acknowledges collective achievements fosters a sense of collaboration and unity, boosting team morale and motivation. The other options are wrong because offering individual bonuses may create competition rather than teamwork, rotating team members can cause disruption and instability, and strict performance monitoring may increase pressure and stress without necessarily improving motivation.
16 | 363 | In managing a large-scale construction project, you recognise the need for effective risk management through teamwork. What advanced technique should you employ to ensure your team collectively identifies and mitigates potential risks? | Conducting regular team meetings focused on risk brainstorming and collaborative problem-solving | Establishing a dedicated risk management team separate from the main project team | Using historical data from past projects to predict and assign risks individually | Assigning risk identification solely to senior team members with the most experience | 1 | 4B | 5 |  | m4A-5 | Conducting regular team meetings focused on risk brainstorming and collaborative problem-solving leverages the diverse perspectives and expertise of the entire team, leading to more comprehensive risk identification and effective mitigation strategies. The other options are wrong because assigning risk identification solely to senior members limits input and may overlook important risks, using historical data does not account for unique project-specific risks, and establishing a separate risk management team can create silos and reduce the integration of risk management into everyday project activities.
16 | 364 | During the construction of a new stadium, there are repeated delays due to poor weather conditions. What strategy should you implement to mitigate the impact of weather on the project schedule? | Conduct a detailed weather impact analysis and adjust scheduling to accommodate delays | Relocate critical project activities to sheltered areas and use weatherproof equipment | Negotiate with suppliers and subcontractors to expedite deliveries and services when weather permits | Increase manpower and equipment utilisation during favourable weather to compensate for lost time | 1 | 4B | 5 |  | m4A-5 | Conducting a detailed weather impact analysis and adjusting scheduling allows for proactive actions, ensuring the project can accommodate weather-related delays. The other options are incorrect because relocating activities and using weatherproof equipment may not always be feasible, negotiating with suppliers might not address the core issue of weather delays, and increasing manpower and equipment utilisation only provides a short-term solution and can lead to inefficiencies.
16 | 365 | Your construction project to build a new airport terminal is at risk due to a recent change in team composition. Several key team members have left, and new members are being onboarded. What should be your primary focus as the project manager to ensure the team remains cohesive and capable of meeting project objectives? | Increase the workload of the remaining team members temporarily to compensate for the loss | Communicate the changes clearly and support the new members in adapting to their roles | Delay the project until the new team members are fully integrated and trained | Immediately replace the new team members with more experienced professionals | 2 | 4B | 5 |  | m4A-5 | Communicating changes clearly and supporting new members ensures a smooth transition and helps maintain team morale and cohesion. The other options are wrong because increasing workload can lead to burnout, delaying the project may not be feasible, and replacing new members immediately could disrupt the team further and is not a sustainable solution.
16 | 366 | You are the project manager for a cable service provider. Your project team is researching a new service offering. They have been working together for quite some time and are in the performing stage of team development. A new member has been introduced to the team. Which of the following statements is true? | The team will start all over again with the storming stage. | The team will continue in the performing stage. | The team will start all over again with the forming stage. | The team will start all over again at the storming stage but quickly progress to the performing stage. | 3 | 4B | 2 |  | m4B-2 | The introduction of a new team member will start the formation and development of the team all over again with the forming stage.
16 | 367 | You are the project manager of a construction project nearing its completion phase. The project team has been working tirelessly, and there is a noticeable drop in their energy and enthusiasm. You need to find a way to reinvigorate the team and ensure they maintain their productivity until the project is completed. Which motivational strategy should you employ to re-energise your team and sustain their productivity? | Increase the frequency of performance reviews and feedback sessions | Rotate team members through different roles and responsibilities | Offer financial bonuses for meeting tight deadlines | Introduce new and interesting tasks to break the monotony | 4 | 4B | 2 |  | m4B-2 | The correct answer is to introduce new and interesting tasks to break the monotony because providing variety and interesting work can help alleviate fatigue and maintain motivation. Increasing the frequency of performance reviews and feedback sessions might add pressure without addressing the root cause of the drop in energy. Rotating team members through different roles and responsibilities can be beneficial but may not directly address the immediate need for re-energising the team. Offering financial bonuses for meeting tight deadlines focuses on extrinsic motivation and can increase stress, potentially leading to burnout.
16 | 368 | You are the project manager for a large infrastructure project, and you need to acquire a mix of internal and external resources. During the mid-phase review, you notice that the project is at risk of exceeding its budget due to high external contractor costs. Which of the following advanced strategies would best address this issue while maintaining project quality and timelines? | Reducing the scope of work for external contractors and reallocating those tasks to internal teams despite their current commitments | Renegotiating contracts with external contractors to lower their fees even if it means compromising on the quality of work | Implementing a cost-benefit analysis to identify and replace high-cost contractors with equally qualified but lower-cost alternatives | Halting the project to reassess all resource allocations and make budget adjustments accordingly | 3 | 4B | 2 |  | m4B-2 | Implementing a cost-benefit analysis to identify and replace high-cost contractors with equally qualified but lower-cost alternatives is an advanced strategy that helps maintain project quality and timelines while addressing budget concerns. The other options are wrong because reducing the scope of work for external contractors can overburden internal teams and affect their performance, renegotiating contracts to lower fees may lead to compromised quality, and halting the project can lead to significant delays and additional costs, disrupting the overall project flow.
19 | 369 | What is the formula for calculating the number of potential communication pathways within a project team? | N_pathway = n(n+1) | N_pathway = n/2 | N_pathway = (n(n-1))/2 | N_pathway = 2n | 3 | 4B | 2 |  | m4B-2 | The correct answer is “N_pathway = (n(n-1)) / 2”. This formula calculates the number of potential communication pathways within a team, where n represents the total number of team members. It accounts for all possible pairwise interactions between members, ensuring each connection is counted once. Other formulas, such as 2n or n(n+1), do not accurately reflect the number of unique communication pathways between pairs of team members.
19 | 370 | You are the project manager for your organisation, and you are working with a new client to start a project at the client’s site. You and the client are negotiating the price, schedule, and other concerns for a contract for the new project. In the negotiating, you and the client should be negotiating for what result? | Best price for the contracted work | Fair agreement for both the client and the vendor | Most profit for the contracted work | Risk distribution between the two parties | 2 | 4B | 2 |  | m4B-2 | The purpose of negotiations is to reach a fair agreement for all parties involved. The other options are incorrect because the options are mutually exclusive and not concerned with the other party in the contract. Risk distribution is not a valid choice because the fair agreement among the parties would address the risk distribution.
19 | 371 | You are managing a construction project, and your team is spread across several countries. One of your primary challenges is ensuring everyone receives timely updates on project milestones. After collecting the required data, you create weekly progress reports. Which of the following steps should you prioritise next to ensure effective communication? | Store the reports in a central document repository, where stakeholders can access and view. | Distribute the reports to the stakeholders through appropriate channels. | Schedule a meeting to discuss the report contents. | Monitor the team’s understanding of the reports. | 2 | 4B | 3 |  | m4B-3 | Effective communication depends on the timely dissemination of information to the relevant stakeholders. Simply creating the reports isn’t enough if they are not distributed properly. The other options are wrong because storing reports, scheduling meetings, or monitoring comprehension come after the essential step of ensuring the right people receive the information first.
19 | 372 | Your construction team uses formal reports and informal updates to communicate project progress. One team member suggests relying solely on informal meetings to improve flexibility and save time. What is the potential risk of following this suggestion? | Improved team relationships but missed deadlines. | Better rapport, but lack of formal records for project progress. | Reduced accountability and lack of structured communication documentation. | Faster decision-making but with increased risk of misinformation. | 3 | 4B | 3 |  | m4B-3 | While informal communication can enhance rapport and flexibility, it lacks the formality needed for accountability, consistent information dissemination, and project documentation. The other options are wrong because although they highlight potential benefits, the critical issue is the absence of formal records, which are essential for project transparency.
19 | 373 | As a project manager, you lead a large construction team, and communication complexity has increased. To manage this, you divide the team into smaller sub-teams, each with its communication protocols. What is the primary advantage of forming smaller teams in this context? | Increased team sise results in more detailed reports but, smaller teams tend to have faster reports. | Fewer communication pathways reduce complexity and improve clarity. | Teams can function independently without coordination, from other interferences. | More diverse opinions leading to better decisions, since a smaller team structure enables quicker updates. | 2 | 4B | 3 |  | m4B-3 | Dividing teams into smaller units reduces the number of communication pathways, making it easier to manage and ensuring clearer information flow. The other options are wrong because they either misrepresent the role of sub-teams in communication or ignore the complexity reduction benefit.
19 | 374 | Your construction project has several stakeholders with different communication preferences. Some prefer face-to-face meetings, while others prefer emails or detailed reports. How should you approach this challenge? | Use only face-to-face meetings to simplify communication. | Schedule more frequent meetings to accommodate all preferences, with all stakeholders thereby meeting their needs. | Adapt your communication strategy to meet the diverse needs of stakeholders. | Use a project management software to standardise all communication. | 3 | 4B | 3 |  | m4B-3 | Tailoring communication to the stakeholders’ preferences ensures that the message is understood and acted upon, enhancing the effectiveness of your communication. The other options are wrong because they either ignore stakeholder preferences or impose a one-sise-fits-all solution that could alienate key stakeholders.
19 | 375 | You are managing communications for a high-stakes construction project. The project’s schedule is behind schedule, and you must ensure all stakeholders are aligned on the new timeline. What is the most effective communication method for conveying this critical information? | A formal project update with supporting documents. | A casual conversation with the most impacted stakeholders. | A series of impromptu team meetings. | An email sent to all team members. | 1 | 4B | 3 |  | m4B-3 | Formal updates are critical when conveying important information like schedule changes, as they provide clear documentation and transparency. The other options are wrong because casual conversations or informal communications lack the necessary structure for such high-impact updates.
19 | 376 | During your construction project, you noticed that your team misinterpreted instructions via email. What is the best approach to improve the clarity of your communications? | Send more frequent emails to reinforce the message. | Use a mix of visual aids and in-person meetings to clarify key points. | Implement strict guidelines for email formatting. | Request detailed feedback from each recipient after sending emails. | 2 | 4B | 3 |  | m4B-3 | Complex instructions are often better communicated through visuals and face-to-face interaction, which reduces misinterpretations. The other options are wrong because relying solely on emails or strict formatting does not address the core issue of unclear communication.
19 | 377 | One of your team members avoids direct eye contact during meetings and seems disengaged despite verbally agreeing to all tasks. What should you do? | Trust the verbal agreement and proceed with the project. | Follow up with the team member privately to clarify their commitment. | Document their agreement in the meeting minutes for future reference. | Reassign the tasks to another team member who seems more engaged. | 2 | 4B | 3 |  | m4B-3 | The team member’s non-verbal cues suggest disengagement, and a private conversation can uncover any concerns they might have. The other options are wrong because they either ignore or escalate the issue without first attempting to understand the underlying problem.
19 | 378 | A construction team member does not understand the urgency of a recent change order communicated during a virtual meeting. Which of the following could have been improved in your communication process? | Monitoring non-verbal cues during the virtual meeting. | Sending follow-up emails summarising the meeting. | Ensuring the change order was documented in the project management software. | Increasing the frequency of virtual meetings. | 1 | 4B | 3 |  | m4B-3 | Non-verbal cues such as facial expressions or body language can indicate misunderstanding or lack of engagement, helping to gauge if the message is being received. The other options are wrong because while they may be useful, they do not directly address the importance of understanding the emotional and cognitive response of the recipient during the meeting.
19 | 379 | You have calculated that 45 potential communication pathways exist in a project team of 10 people. A stakeholder questions whether this level of complexity can be managed effectively. How would you respond? | By creating more formal reports. | By forming smaller sub-teams to reduce the number of pathways. | By increasing the frequency of meetings to ensure clarity. | By simplifying the message content to reduce confusion. | 2 | 4B | 3 |  | m4B-3 | Smaller sub-teams decrease communication complexity by reducing the number of pathways, making it easier to manage and track. The other options are wrong because they do not address the core problem of too many communication channels.
19 | 380 | You are your organisation's project manager and are working with a new client to start a project at the client’s site. You and the client are negotiating the price, schedule, and other concerns for a contract for the new project. What result should you and the client be negotiating for? | Best price for the contracted work | Fair agreement for both the client and the vendor | Most profit for the contracted work | Risk distribution between the two parties | 2 | 4B | 3 |  | m4B-3 | The purpose of negotiations is to reach a fair agreement for all parties involved. Best price and most profit are incorrect because these two choices are mutually exclusive and not concerned with the other party in the contract. Risk distribution is not a valid choice because the fair agreement among the parties would address the risk distribution.
19 | 381 | You are working on a project and discover that one of the business users responsible for testing the product never completed this activity. She has written an email requesting that one of your team members drop everything to assist her with a problem that could have been avoided if she had performed the test. This employee reports to a stakeholder, not to the project team. All project team members and stakeholders are collocated. Because your team also needs her to participate in an upcoming test, which of the following did you decide to do? | You decide to record the issue in the issue log and bring it up at the next status meeting. Everyone can benefit from understanding the importance of stakeholders fulfilling their roles and responsibilities on the project. | You decide to record the issue in the issue log and then phone the stakeholder to explain what happened. You know speaking with the stakeholder directly is the most effective means for resolving issues. | You decide to have a face-to-face meeting with the stakeholder because this is the most effective means for resolving issues with them. | You decide to email the stakeholder and explain what happened in a professional manner so you can incorporate their response in the next status report. | 3 | 4B | 3 |  | m4B-3 | Face-to-face meetings are the most effective means for resolving stakeholder issues, provided these meetings are practical.
19 | 382 | In project management, what is the primary purpose of the Manage Communications process? | Developing an accurate and comprehensive timeline for project tasks and milestones. | Reducing misunderstandings and fostering a collaborative team environment. | Aligning stakeholder perceptions and approvals with project progression. | Ensuring timely and appropriate information sharing and management. | 4 | 4B | 4 | a | m4B-4a | The correct answer is “Ensuring timely and appropriate information sharing and management”. The Manage Communications process ensures that relevant information is shared promptly and accurately among stakeholders, supporting informed decision-making and project progress. It involves creating, distributing, storing, and managing project communications to maintain alignment and transparency. Developing timelines falls under schedule management. Reducing misunderstandings and fostering collaboration is a result of effective communication but not the primary purpose. Aligning stakeholder perceptions and approvals is part of stakeholder engagement management.
19 | 383 | What model emphasises the importance of feedback loops and interactivity in effective communication? | Sender-Receiver Model | Linear Communication Model | One-way Communication Model | Static Communication Model | 1 | 4B | 4 | a | m4B-4a | The correct answer is “Sender-Receiver Model”. The Sender-Receiver Model emphasises the importance of feedback loops and interactivity in communication. It highlights that effective communication requires not just sending a message, but also receiving, understanding, and responding to it, ensuring that both parties are engaged in the process. In contrast, the Linear Communication Model is one-directional, without feedback. The One-way Communication Model also lacks interactivity, focusing on message delivery only. The Static Communication Model implies no dynamic exchange or feedback.
29 | 384 | You have just joined a project that has already been planned. You want to look at strategies to implement and actions to perform to facilitate stakeholders’ creative involvement in the project, such as making project decisions and project execution. Where will you look? | Stakeholders’ engagement assessment matrix | Mind mapping | The stakeholder engagement plan | Project stakeholder register | 3 | 4B | 4 | a | m4B-4a | The correct answer is stakeholder engagement plan. The other options are incorrect because mind mapping, assessment matrix are tools and techniques, stakeholder register contains information about the stakeholders and not the management strategies about them.
29 | 385 | You are managing the construction of a large commercial complex. Early in the project, you find that a key stakeholder, a city council member, is hesitant to support the project. Which of the following strategies would best secure their ongoing commitment? | Present the technical feasibility of the project to the stakeholder | Engage the stakeholder early, seek their input, and align the project with community goals | Minimise communication with the stakeholder until the project reaches key milestones | Rely on formal project contracts to ensure stakeholder compliance | 2 | 4B | 4 | a | m4B-4a | Engaging stakeholders early and aligning the project with their goals ensures ongoing support. The other options are wrong because presenting only technical details does not address the stakeholder’s broader concerns, minimising communication risks alienation, and relying solely on contracts can create conflict without fostering commitment.
29 | 386 | A major construction project faces conflicting expectations from two stakeholders: the local government and a community group. What is the most effective approach for managing these conflicting interests? | Focus on the government’s requirements, as they hold more power. Afterall, community opinion is fragmented. | Delay addressing the conflict until later stages of the project as tactical measure to get things moving. | Negotiate and facilitate open discussions between stakeholders to align expectations | Prioritise the major stakeholder that contributes the most financial resources to the project. | 3 | 4B | 4 | a | m4B-4a | Negotiating and facilitating open discussions allows stakeholders to align their expectations, which helps to resolve conflicts. The other options are wrong because focusing only on one stakeholder risks losing broader support and delaying conflict resolution can lead to escalation and project delays.
29 | 387 | Midway through a construction project, a powerful client requests changes that significantly increase the project’s scope. How should you manage this situation while maintaining stakeholder engagement? | Reject the changes outright to avoid delaying the project | Discuss the impact on the project’s timeline and budget, and negotiate a compromise, if possible. | Accept the changes without question to maintain a good relationship with the client, after all, it is the bosses most important customer. | Implement the changes and deal with the consequences later, as it has happened before. | 2 | 4B | 4 | a | m4B-4a | Negotiating a compromise ensures the project remains feasible while managing expectations. The other options are wrong because rejecting the request outright could damage the relationship, blindly accepting changes could cause project failure, and delaying action worsens project risk.
29 | 388 | In a project to build a public hospital, you identify a potential risk related to regulatory approval delays. What is the best approach to managing this risk in relation to key stakeholders? | Ignore the risk, hoping it will not materialise. Afterall, regulations might not change in time to become law. | Engage the regulatory authority early and develop a contingency plan. Early is better. | Wait until the approval process starts before addressing the risk. Nothing can move unless it is approved. | Focus on internal project controls rather than external risks, to save time. | 2 | 4B | 4 | a | m4B-4a | Engaging early and developing a contingency plan ensures risks are mitigated. The other options are wrong because ignoring risks or waiting leads to larger issues and focusing only on internal factors neglects critical external influences.
29 | 389 | You are managing a high-profile construction project and need the approval of local government authorities. Which approach demonstrates political awareness in managing this stakeholder group? | Understanding the broader urban development goals and aligning your project with them | Issuing an ultimatum that the project must be approved by a specific date, to force through the project forward. | Avoiding discussions with government officials to prevent complications, as this would complicate matters internally. Delegate the responsibility to higher management. | Focusing on the project’s financial benefits during communications. The financial input could help raise the company’s profit margin significantly. | 1 | 4B | 4 | a | m4B-4a | Aligning your project with the broader goals demonstrates an understanding of political dynamics. The other options are wrong because issuing ultimatums creates conflict, avoiding discussions undermines engagement, and focusing only on financial aspects neglects the broader political landscape.
29 | 390 | A conflict arises between two construction team members over resource allocation. As a project manager, how should you resolve this conflict while maintaining team cohesion? | Ignore the conflict and hope it resolves on its own as they were acting like children. | Facilitate a negotiation session to address the underlying concerns and find a compromise | Reassign one team member to a different task | Implement a strict top-down decision to settle the conflict | 2 | 4B | 4 | a | m4B-4a | Facilitating a negotiation addresses the root of the conflict and fosters collaboration. The other options are wrong because ignoring the issue or reassigning may lead to ongoing tension, and top-down decisions can damage team morale.
29 | 391 | In a construction project, the local community is concerned about the environmental impact of the build. How can you effectively communicate with this stakeholder group to address their concerns? | Provide a technical report on the environmental impact and how it could address their concerns | Tailor communication to focus on the project’s green initiatives and community benefits | Ignore the community concerns as some of them have links to a green group that objects to anything. | Emphasise the project’s financial return if it was carried out and that environment concerns might end up as in-consequential as time goes by. | 2 | 4B | 4 | b | m4B-4b | Focusing on green initiatives and community benefits shows that their concerns are taken seriously. The other options are wrong because providing only technical reports or ignoring concerns can alienate the community and create opposition.
29 | 392 | A key stakeholder expresses strong resistance to an aspect of your project’s design. The project is already behind schedule. What is your best course of action? | Ignore the resistance and proceed with the project to avoid further delays | Engage the stakeholder in dialogue to understand their concerns and explore potential compromises | Delay the project until the stakeholder’s concerns are resolved | Escalate the issue to senior management and let them handle it | 2 | 4B | 4 | b | m4B-4b | Engaging the stakeholder and exploring compromises preserves the relationship and can prevent future roadblocks. The other options are wrong because ignoring resistance leads to bigger issues, delaying indefinitely increases risk, and escalating without first trying to resolve the issue undermines your leadership.
29 | 393 | Your contractor requests additional compensation for unexpected work due to site conditions. How should you handle this situation to maintain a strong working relationship and project continuity? | Reject the request outright to avoid budget overruns | Negotiate by reviewing the contract terms and considering reasonable compensation for the additional work | Approve the request immediately to keep the project on schedule | Ignore the request and proceed with the original budget | 2 | 4B | 4 | b | m4B-4b | Negotiating and reviewing contract terms ensures fairness and maintains the relationship. The other options are wrong because outright rejection damages relationships, immediate approval risks budget issues, and ignoring the request creates resentment.
29 | 394 | Your client has requested a project completion date that you know is unrealistic given current constraints. What is the best approach to managing their expectations? | Communicate the constraints clearly and propose an achievable alternative timeline | Agree to the date and hope to meet it by increasing resources to support the project | Avoid discussing the timeline in the hopes it will be extended later | Present a worst-case scenario to lower expectations drastically, based on previous experience. | 1 | 4B | 4 | b | m4B-4b | Proposing an alternative timeline is transparent and realistic. The other options are wrong because agreeing without capacity risks failure, avoiding discussion leads to misunderstandings, and overly pessimistic forecasts damage trust.
4 | 395 | Which formula is used to calculate the Cost Variance (CV)? | CV = AC – EV | CV = PV – EV | CV = EV – PV | CV = EV – AC | 4 | 5A | 4 | b | m4B-4b | Cost Variance (CV) is calculated by subtracting the Actual Cost (AC) from the Earned Value (EV). This formula shows the difference between the budgeted cost of work performed and the actual cost. CV = AC – EV is incorrect because it reverses the formula. CV = PV – EV is incorrect because PV is not used in the CV formula. CV = EV – PV is incorrect because it compares the earned value with the planned value, not the actual cost.
4 | 396 | Which formula is used to calculate the Cost Performance Index (CPI)? | CPI = EV / AC | CPI = AC / EV | CPI = EV / PV | CPI = PV / EV | 1 | 5A | 4 | b | m4B-4b | The Cost Performance Index (CPI) is a measure of cost efficiency calculated by dividing the Earned Value (EV) by the Actual Cost (AC). CPI = AC / EV is the wrong formula. The options CPI = EV / PV and CPI = PV / EV are incorrect because PV is not used in the CPI formula.
4 | 397 | Which formula is used to calculate the Estimate at Completion (EAC) if the current cost performance index (CPI) or per cent complete (%C) is assumed to remain constant for the remaining portion of the project? | EAC = BAC / CPI | EAC = AC + (BAC − EV)/(CPI x SPI) | EAC = AC + BAC - EV | EAC = AC + Bottom-up ETC | 1 | 5A | 4 | b | m4B-4b | This formula assumes that future performance will be the same as past performance, making it suitable when the CPI is expected to remain constant.
4 | 398 | Which of the following statements correctly describes the relationship between the Cost Performance Index (CPI) and the To-Complete Performance Index (TCPI)? | If CPI > 1, the project is under budget, and TCPI must be less than 1 to complete within the original budget (BAC). | If CPI < 1, the project is over budget, and TCPI must be less than 1 to complete within the original budget (BAC). | If CPI = 1, the project is on budget, and TCPI must be greater than 1 to complete within the original budget (BAC). | If CPI < 1, the project is over budget, and TCPI must be greater than 1 to complete within the original budget (BAC). | 1 | 5A | 4 | c | m4B-4c | The correct answer is ‘If CPI > 1, the project is under budget, and TCPI must be less than 1 to complete within the original budget (BAC)’ because if the project is under budget, the performance required to stay within budget should be less than 1. The other options describe incorrect relationships.
4 | 399 | You are managing a construction project with a budget of $800,000. The project involves two construction teams working for six months, totalling 10,000 hours of labour. According to your project schedule, 38% of the work should be completed by now. However, you've noted that 40% of the work is complete, but 50% of the budget has already been spent. What does this indicate about your project's status? | The project is ahead of schedule and under budget. | The project is ahead of schedule but over budget. | The project is behind schedule but under budget. | The project is on schedule but over budget. | 2 | 5A | 4 | c | m4B-4c | The project is ahead of schedule (40% completed vs. 38% planned) but over budget (50% spent vs. 40% work done). Thus, the correct answer is ‘The project is ahead of schedule but over budget.’ The other options do not correctly describe both the schedule and budget status.
4 | 400 | Nine months into a two-year infrastructure upgrading project with a $4,200,000 budget, you have spent $1,650,000. The project's Cost Performance Index (CPI) is 0.875. Calculate the project's Estimate to Complete (ETC) based on this information. Assume future work is completed at the planned efficiency rate. | 2756250 | 3150000 | 4406250 | 3550000 | 1 | 5A | 4 | c | m4B-4c | From the question: BAC = $4,200,000, AC = $1,650,000, CPI = 0.875. Since the assumption is that future work will be completed at the planned efficiency rate (the same rate used for BAC), the formula EAC2 should be used. EAC = AC + BAC - EV = 1,650,000 + 4,200,000 - (CPI x AC). [CPI x AC = EV] = 1,650,000 +4,200,000 -(0.875 x 1,650,000) = $4,406,250. Therefore, to find ETC, ETC = EAC - AC = 4,406,250 - 1,650,000 = $2,756,250
4 | 401 | Assume that you are the project manager for the construction of a 15-km road. Further, assume that the work is uniformly distributed over 12 weeks. The total approved budget for this project is $600,000. At the end of the first three weeks of work, $160,000 was spent, and five km of road were completed. What is the project's earned value at the end of the first three weeks? | 160000 | 200000 | 150000 | 600000 | 2 | 5A | 4 | c | m4B-4c | The formula for earned value is EV = BAC × (work completed / total work required). This means EV = $600,000 × (5 km / 15 km) = $200,000. $160,000 is the actual cost (AC), $150,000 is not proportional to the fraction of work performed, and $600,000 is the budget at completion (BAC).
4 | 402 | Assume that you are the project manager for the construction of a 15-km road. Further, assume that the work is uniformly distributed over 12 weeks. The total approved budget for this project is $600,000. At the end of the first three weeks of work, $160,000 was spent, and five km of road were completed. What is the schedule variance? | 40000 | 50000 | Three weeks | Twelve weeks | 2 | 5A | 4 | c | m4B-4c | The formula for schedule variance is SV = EV – PV. This means SV = $200,000 – $150,000 = $50,000. SV is equal to EV – PV, not EV – AC, and is measured in cost units, not time units.
4 | 403 | Which performance measurement tells you what the projected total cost of the project will be at completion? | ETC | EV | AC | EAC | 4 | 5A | 4 | c | m4B-4c | Estimate at completion (EAC) estimates the total cost of the project at completion based on the project's performance to date.
4 | 404 | Which performance measurement tells you the cost of the work that has been authorised and budgeted for a WBS component? | PV | EV | AC | EVM | 1 | 5A | 4 | c | m4B-4c | Planned value is the cost of work that has been authorised and budgeted for a schedule activity or WBS component.
4 | 405 | As the project manager, you review your team's earned value analysis report. The SPI is 0.87. What does this figure mean to you? | Your project is running according to the budget. | The project is getting 87 cents out of each dollar spent. | You are ahead of schedule. | Your project's progress is only 87% of what was planned, so you are behind schedule. | 4 | 5A | 4 | c | m4B-4c | The Schedule Performance Index (SPI) is a measure of the project performance in terms of the time schedule. SPI < 1 shows that the project is behind schedule.
4 | 406 | This measurement is the value of the work that has been completed to date compared to the budget. | PV | AC | EV | EAC | 3 | 5A | 4 | c | m4B-4c | Earned value is referred to as the value of the work that’s been completed to date compared to the budget.
4 | 407 | You are a contract project manager for a wholesale flower distribution company. Your project is to develop a website for the company that allows retailers to place their flower orders online. You will also provide a separate link for individual purchases that are ordered, packaged, and mailed to the consumer directly from the grower’s site. This project involves coordinating the parent company, growers, and distributors. You are preparing a performance review and have the following measurements at hand: PV = 300, AC = 200, and EV = 250. What do you know about this project? | The EAC is a positive number, which means the project will finish under budget. | You do not have enough information to calculate CPI. | The CV is a negative number in this case, which means you’ve spent less than you planned to spend as of the measurement date. | The CV is a positive number in this case, which means you’re under budget as of the measurement date. | 4 | 5A | 5 |  | m4B-5 | The CV is a positive number and is calculated by subtracting AC from EV as follows: 250 – 200 = 50. A positive CV means the project is coming in under budget, meaning you’ve spent less than you planned as of the measurement date.
4 | 408 | Which of the following does a negative result from an SV calculation mean? | PV is higher than EV | PV equals 1 | EV is higher than PV | EV is higher than AC | 1 | 5A | 5 |  | m4B-5 | The SV calculation is EV – PV. If PV is higher than EV, you will get a negative number.
4 | 409 | You know that EAC = 375, PV = 300, AC = 200, and EV = 250. You expect the work of the project to continue as planned. What is the ETC? | 300 | 125 | 175 | 50 | 3 | 5A | 5 |  | m4B-5 | The correct formula for ETC for this question is as follows: EAC – AC. Therefore, ETC is as follows: 375 – 200 = 175.
4 | 410 | You expect future project performance to be consistent with the project performance experienced to date for this work component. If BAC = 800, ETC = 275, PV = 300, AC = 200, EV = 250, and CPI = 1.25, what is the EAC? | 640 | 750 | 600 | 550 | 1 | 5A | 5 |  | m4B-5 | When project performance is expected to behave like past performance, EAC is calculated as follows: EAC = BAC / CPI. Therefore, the calculation for this question looks like this: 800 / 1.25 = 640.
4 | 411 | Given that Variance at Completion (VAC) = BAC – EAC. You know that BAC = 500, PV = 325, AC = 275, CPI = 0.9, and EV = 250, and you are using actual costs to date and assuming EAC uses the planned efficiency rate. What is the VAC? | 25 | -52 | 52 | -25 | 4 | 5A | 5 |  | m4B-5 | You first have to calculate EAC in order to calculate VAC. EAC for variances that are atypical is AC + (BAC – EV). So, our numbers are 275 + (500 – 250) = 525. VAC is calculated this way: BAC – EAC. Therefore, 500 – 525 = –25. Our costs are not doing as well as anticipated.
4 | 412 | You know that BAC = 2500, PV = 1250, AC = 1275, EV = 1150, and assume CPI is constant for the remainder of the project. What is ETC? | 1467 | 2625 | 1503 | 2778 | 3 | 5A | 5 |  | m4B-5 | You must first calculate CPI in order to calculate ETC. CPI is EV / AC. We have 1150 / 1275 = .90. EAC1 (Assumes CPI or %C is constant for remaining project) = BAC/CPI = 2500/0.9 = 2778. ETC = EAC − AC = 2778 - 1275 = 1503
4 | 413 | Which formula is used to calculate the To-Complete Performance Index (TCPI) based on the BAC? | TCPI = (BAC - EV) / (EAC - AC) | TCPI = (BAC - EV) / (BAC - AC) | TCPI = EV / PV | TCPI = AC / EAC | 2 | 5A | 5 |  | m4B-5 | The correct answer is "TCPI = (BAC - EV) / (BAC - AC)" because the To-Complete Performance Index (TCPI) measures the efficiency required to complete the project within the BAC. The other options are incorrect because they either involve the EAC (used in a different context) or mix unrelated variables.
4 | 414 | Which formula is used to calculate the Schedule Performance Index (SPI)? | SPI = EV / PV | SPI = PV / EV | SPI = EV / AC | SPI = AC / PV | 1 | 5A | 5 |  | m4B-5 | The correct answer is "SPI = EV / PV" because the Schedule Performance Index (SPI) measures schedule efficiency by dividing the earned value (EV) by the planned value (PV). The other options are incorrect because they use the wrong combinations of variables or involve Actual Cost (AC), which is unrelated to SPI.
4 | 415 | You are managing a bridge construction project with a total budget (BAC) of $5,000,000. After six months, you have spent $2,500,000 and completed 40% of the work. What is the project's Cost Performance Index (CPI)? | 1.5 | 1 | 1.25 | 0.8 | 4 | 5A | 6 |  | m4B-6 | The formula for CPI is CPI = EV / AC. Here, EV = BAC × % Complete = $5,000,000 × 40% = $2,000,000. AC = $2,500,000. Therefore, CPI = $2,000,000 / $2,500,000 = 0.8.
4 | 416 | A road construction project has a BAC of $600,000 and is planned to be completed over 15 weeks. After 5 weeks, the project has spent $250,000 and completed 6 km out of 15 km. What is the Earned Value (EV) at the end of 5 weeks? | 200000 | 240000 | 250000 | 600000 | 2 | 5A | 6 |  | m4B-6 | The formula for EV is EV = BAC × (Work Completed / Total Work). Here, EV = $600,000 × (6 km / 15 km) = $240,000.
4 | 417 | A housing project has a total budget of $1,200,000 and is scheduled to be completed in 12 months. By the end of 4 months, the project has spent $400,000 and completed 30% of the work. What is the project's Schedule Performance Index (SPI)? | 0.9 | 1 | 1.25 | 1.5 | 1 | 5A | 6 |  | m4B-6 | The formula for SPI is SPI = EV / PV. EV = BAC × % Complete = $1,200,000 × 30% = $360,000. PV = BAC × Planned % Complete = $1,200,000 × (4 months / 12 months) = $400,000. Therefore, SPI = $360,000 / $400,000 = 0.9.
4 | 418 | Your software development project’s performance review shows PV = 500, EV = 450, and AC = 475. What do these values indicate about your project? | The project is ahead of schedule but over budget. | The project is behind schedule but under budget. | The project is behind schedule and over budget. | The project is on track with the schedule and budget. | 3 | 5A | 6 |  | m4B-6 | SPI = EV / PV = 450 / 500 = 0.9 (<1, indicating delay), and CPI = EV / AC = 450 / 475 = 0.95 (<1, indicating over budget).
4 | 419 | You are managing the construction of a residential building. The project’s measurements are PV = 400, AC = 350, and EV = 375. What do you know about this project? | The CPI is less than 1, indicating efficient cost performance. | The SPI is greater than 1, showing schedule delays. | The CV is negative, meaning you have spent more than planned. | The CV is positive, meaning you are under budget. | 4 | 5A | 6 |  | m4B-6 | PV = 400, AC = 350, and EV = 375. The CV is calculated as EV - AC = 375 - 350 = 25. A positive CV indicates the project is under budget. The other options are incorrect because SPI = EV/PV = 375/400<1; CPI = EV/AC = 375/350>1.
7 | 420 | What is one of the primary purposes of the Control Scope process in project management? | Defining project objectives | Monitoring project progress | Managing changes to the scope baseline | Capturing lessons learnt | 3 | 5A | 6 |  | m4B-6 | Control Scope ensures all scope changes are processed through the integrated change control process. "Defining project objectives" is part of project initiation. "Monitoring project progress" is a broader activity. "Capturing lessons learnt" is part of the closing process.
7 | 421 | Which of the following is crucial for effective scope control? | A detailed project management plan | A comprehensive configuration management plan | A well-defined scope | A well-defined project schedule | 3 | 5A | 2 | a | 5A-2a | A well-defined scope ensures that all stakeholders clearly understand the project boundaries.
7 | 422 | In project management, which processes work synergistically with the Control Scope process to maintain alignment between the evolving scope and its overarching plan? | Perform Integrated Change Control | Perform Quality Control | Monitor and Control Project Work | Validate Scope | 1 | 5A | 2 | a | 5A-2a | “Perform Integrated Change Control” is correct because Perform Integrated Change Control ensures changes are reviewed, approved, and managed in a structured way, maintaining alignment. “Perform Quality Control” is incorrect because Perform Quality Control focuses on ensuring the quality of deliverables, not scope alignment. “Monitor and Control Project Work” is incorrect because Monitor and Control Project Work oversee all project work, not specifically scope alignment. “Validate Scope” is incorrect because Validate Scope focuses on acceptance of deliverables, not alignment.
7 | 423 | Which of the following options identifies the key factors to consider when evaluating the impact of proposed changes? | Stakeholder satisfaction and risk | Budget, resources, and project objectives | Project complexity and available resources | Project timeline and scope | 2 | 5A | 2 | a | 5A-2a | Budget, resources, and project objectives are the correct answers as they directly impact the feasibility and alignment of changes. While stakeholder satisfaction and risk are important, they are secondary in this context. While relevant, project complexity and available resources are less directly impactful than budget and objectives. Project timeline and scope are typically defined within the project objectives and not during the evaluation of proposed changes.
7 | 424 | What risks are directly associated with scope creep? | Extended timelines, reduced work, and improved quality | Increased project complexity, lower stakeholder satisfaction | Additional work, increased costs, and extended timelines | Lower quality, increased costs, and improved stakeholder satisfaction | 3 | 5A | 2 | a | 5A-2a | The correct answer is “Additional work, increased costs, and extended timelines.” Scope creep leads to unplanned additional tasks that require more resources and time, thereby increasing project costs and extending timelines. It often results from the uncontrolled expansion of the project scope without proper adjustments to the project plan.
7 | 425 | What is essential to prevent scope creep? | Quick response to the additional scope | Proactive and disciplined approach | Ignoring power dynamics between clients and the project team | Flexible communications with stakeholders | 2 | 5A | 2 | a | 5A-2a | A proactive and disciplined approach is the correct answer, which is key to managing changes effectively. While quick response is important, discipline must accompany it to avoid scope creep. Ignoring power dynamics can lead to conflicts and mismanagement, highlighting the need for a balanced approach. Flexible communication is valuable, but it can be less effective without discipline.
7 | 426 | You are working on a project that was proceeding well until a manufacturing glitch occurred that requires corrective action. The glitch unintentionally enhanced the product, and the marketing people are into its potential. The corrective action is cancelled, and you continue to produce the product with the newly discovered enhancement. As the project manager, you know that a change has occurred to the product scope because the glitch changed the product's characteristics. Which of the following statements is true? | Changes to product scope should be reflected in the project scope. | Changes to product scope should be documented in the scope management plan. | Changes to product scope will result in cost changes. | Changes to product scope are a result of corrective action. | 1 | 5A | 2 | a | 5A-2a | Changes to product scope should be reflected in the project scope, which is the correct answer. When the product scope changes, it affects the project’s overall scope. Therefore, these changes must be updated in the project scope to ensure that all aspects of the project, including schedules, costs, and resources, are adjusted accordingly. For “Changes to product scope should be documented in the scope management plan”, while it is important to document scope changes, the specific requirement is that these changes are reflected in the project scope. Documentation is part of this process, but the key aspect is reflecting on the project scope. “Changes to product scope will result in cost changes” might be accurate, but it is not the primary consideration in this context. The focus here is on how changes to product scope need to be managed in the project scope. The option “Changes to product scope are a result of corrective action” is incorrect in this context because the change was not a result of corrective action; instead, it was a decision to adopt an unintentional enhancement.
7 | 427 | You are managing an IT project for an external client. The project is ahead of schedule, and your subsequent activities are testing and handover. Which of the following will you be more concerned about in this situation? | Time schedule | Performing quality control | Generating performance reports | Validate project scope | 4 | 5A | 2 | a | 5A-2a | You are close to performing the final product handover to the external client. Scope validation deals with acceptance by the customer. Without this acceptance, you cannot move into the next project phase.
7 | 428 | You are a project manager for Dakota Software Consulting Services. You are working with a major retailer that offers its products through mail-order catalogues. It is interested in knowing customer characteristics, the amounts of first-time orders, and similar information. The stakeholders have accepted the project scope. Work has begun on the project, and you are confirming some initial work results with the stakeholders. You have asked for acceptance of the work results. Which process are you performing? | Monitor Risks | Control Quality | Validate Scope | Control Scope | 3 | 5A | 2 | a | 5A-2a | The Validate Scope process is concerned with 8the acceptance of work results. It also formalises the acceptance of the project scope.
7 | 429 | You are the project manager for a top-secret software project for an agency of the United States government. Getting top-secret clearances for contractors takes quite a bit, and waiting for clearances would jeopardise the implementation date. Should you accept it, your mission is to complete the project using internal resources. Your programmers are 80 per cent of the way through the programming and testing work when your agency appoints a new executive director. Your programmers are siphoned off this project to work on the executive director’s hot new project. Which of the following addresses the purpose of Validate Scope in this case? | Validate Scope determines the correctness and completion of all the work. | Validate Scope documents the level and degree of completion. | Validate Scope determines whether the project results comply with quality standards. | Validate Scope documents the correctness of the work according to stakeholders’ expectations. | 2 | 5A | 2 | b | 5A-2b | Validate Scope should document the project's level and degree of completion given the circumstances in this question. If you return later and restart this project, Validate Scope will describe how far the project has progressed and give you an idea of where to start.
7 | 430 | You are managing a construction project that involves building a new office complex. The stakeholders have accepted the project scope, and you are in the process of reviewing deliverables with the stakeholders to formalise acceptance. Which process are you performing? | Control Quality | Validate Scope | Monitor Risks | Control Scope | 2 | 5A | 2 | b | 5A-2b | The correct answer is "Validate Scope" because it is focused on gaining formal acceptance of completed deliverables. The other options are incorrect because "Control Quality" ensures that deliverables meet quality standards, "Monitor Risks" involves risk tracking, and "Control Scope" focuses on managing changes to the scope baseline.
7 | 431 | You are reviewing project deliverables with the stakeholders and find that a deliverable does not meet the agreed-upon scope requirements. What should you do next? | Reject the deliverable and document it as a variance | Accept the deliverable with stakeholder approval | Update the project schedule to include corrective actions | Perform rework to align the deliverable with scope requirements | 4 | 5A | 2 | b | 5A-2b | The correct answer is "Perform rework to align the deliverable with scope requirements" because deliverables must meet the agreed-upon requirements before acceptance. The other options are incorrect because rejecting the deliverable or updating schedules without addressing the issue does not resolve the scope deviation.
7 | 432 | You are working on a project for a logistics company. Due to a client’s last-minute request, a significant scope change has been proposed. What should you prioritise when evaluating this change? | Assess the impact on the budget, timeline, and resources | Implement the change immediately to maintain client satisfaction | Reject the change to avoid project delays | Update the project management plan without approval | 1 | 5A | 2 | b | 5A-2b | The correct answer is "Assess the impact on the budget, timeline, and resources" because a thorough evaluation ensures that changes are feasible and align with project objectives. The other options are incorrect because they either bypass critical assessments or dismiss the change without evaluation.
9 | 433 | What is the purpose of the iteration burndown chart? | Monitoring resource utilisation | Tracking progress and identifying risks in an iteration | Analysing project costs | Evaluating stakeholder satisfaction | 2 | 5A | 2 | b | 5A-2b | “Tracking progress and identifying risks” is the correct answer, as iteration is a core component of successful agile project management. While monitoring resource utilisation is important, it is not the primary focus of tracking progress within an iteration. Analysing project costs is not the primary purpose of a burndown chart, which is primarily used to visualise the remaining work. Evaluating stakeholder satisfaction requires specific methods separate from tracking progress within an iteration.
9 | 434 | In controlling contractors' and suppliers' schedules, what is an effective way to monitor work progress? | Ensuring the accuracy of work performance data | Monitoring milestone status | Evaluating project costs | Reviewing project risks | 2 | 5A | 2 | b | 5A-2b | Monitoring milestones helps track progress at significant points in the project timeline, and thus, “monitoring milestone status” is the correct answer. Ensuring the accuracy of work performance data is important but does not explicitly address schedule monitoring. Evaluating project costs relates to cost management, not scheduling, and reviewing project risks focuses on risk management.
9 | 435 | Which process ensures that any schedule baseline amendments are carefully managed? | Perform Integrated Change Control | Control Schedule | Develop Schedule | Monitor and Control Project Work | 1 | 5A | 2 | b | 5A-2b | “Perform Integrated Change Control” is the correct answer, as it involves reviewing all change requests, approving changes, and managing them systematically. “Control Schedule” focuses on controlling the schedule but not the broader change control process. “Develop Schedule” is about creating the schedule, not managing changes. “Monitor and Control Project Work” involves tracking progress but not specifically managing schedule amendments.
9 | 436 | When should schedule status reviews and walkthroughs be conducted in controlling contractors' schedules? | At irregular intervals | After project completion | As needed based on contractor requests | Regularly and at milestone points | 4 | 5A | 2 | b | 5A-2b | Regular reviews and milestone walkthroughs ensure ongoing monitoring and timely detection of issues. The other options are incorrect because “At irregular intervals” lacks consistency and may miss critical issues, “After project completion” is too late to be effective, and “As needed based on contractor requests” may lead to biased and inconsistent reviews.
9 | 437 | From a schedule control point of view, what are the purposes of having scheduled walk-throughs? | Ensuring quality of work | Ensureing the reported progress is correct | Checking that scope requirements are met | Checking that the progress on site is ahead of schedule | 2 | 5A | 2 | b | 5A-2b | The correct answer is “Ensuring the reported progress is correct” because scheduled walk-throughs verify that the progress reported matches the actual work done. The other options are incorrect because “Ensuring quality of work” is more about quality control, “Checking that scope requirements are met” relates to scope management, and “Checking that the progress on site is ahead of schedule” is unrealistic.
9 | 438 | What are the performance measurements for the Control Schedule process? | SV = (EV – PV) and SPI = (EV / PV) | SV = (EV – AC) and SPI = (EV / AC) | SV = (EV – BAC) and SPI = (EV / BAC) | SV = (PV – EV) and SPI = (PV / EV) | 1 | 5A | 2 | b | 5A-2b | The schedule variance is (EV – PV), and the schedule performance index is (EV / PV).
9 | 439 | Why should you monitor the activities on the critical path more closely? | Because each activity on the critical path has zero float time and thereby poses a schedule risk | Because the activities on the critical path need to be performed before the activities on other paths are performed | Because the activities on the critical path are critical to the organisation’s strategy | Because the activities on noncritical paths depend upon the activities on the critical path | 1 | 5A | 2 | b | 5A-2b | Each activity on the critical path has zero-float time, meaning any delay in these activities will directly delay the entire project. The other options are incorrect statements about the activities on the critical path. Activities on the critical path do not necessarily need to be performed before those on other paths, are not inherently tied to the organisation’s strategy, and noncritical path activities do not depend on critical path activities.
9 | 440 | You are a junior project manager currently performing schedule-controlling activities. You approach one of your experienced colleagues for advice on how to reanalyse the project and predict the project’s remaining duration. She tells you to analyse the activity sequence with the least scheduling flexibility. Which technique is she referring to? | Gantt Chart | Critical path method | Resource levelling | Precedence diagramming method | 2 | 5A | 2 | b | 5A-2b | The Gantt chart only represents the project schedule; it is not an analysis method. The precedence diagramming method deals with the relationship between activities, not schedule flexibility. Resource levelling smooths the use of resources over a period of time. The only option that deals with schedule flexibility is the critical path method, which uses activity floats.
11 | 441 | What is the purpose of an Earned Value Analysis in the Control Cost process? | Provide a quantitative basis for updating the budget | Facilitate a quantitative risk assessment of project costs | Provide a basis for approving quality-related change requests | Provide the details needed for lessons learned related to cost management | 1 | 5A | 2 | b | 5A-2b | Earned Value Analysis provides a quantitative method for assessing cost performance and forecasting future performance. The other options are incorrect because facilitating risk assessment is not the primary purpose, providing a basis for quality-related change requests is not part of cost control, and providing details for lessons learned is part of project closure.
11 | 442 | What is the primary purpose of continuously monitoring cost performance against the approved cost baseline? | Updating the project schedule | Identifying and managing cost variances | Forecasting project risks | Managing change requests | 2 | 5A | 2 | b | 5A-2b | “Identifying and managing cost variances” is correct because it helps manage project finances effectively. Continuous monitoring helps detect deviations from the cost baseline, allowing for timely corrective actions. “Updating the project schedule” is incorrect because updating the project schedule is part of schedule management. “Forecasting project risks” is incorrect because forecasting risks is part of risk management. “Managing change requests” is incorrect because managing change requests is part of change control.
11 | 443 | What is the purpose of tracking costs at different levels, such as by period, work breakdown structure (WBS) component, and activity? | To facilitate detailed cost analysis and control | To improve project documentation accuracy | To ensure regulatory compliance | To enhance team collaboration and communication | 1 | 5A | 2 | b | 5A-2b | The primary purpose of tracking costs at various levels, including by period, work breakdown structure (WBS) component, and activity, is “to facilitate detailed cost analysis and control.” This meticulous tracking enables project managers to monitor and analyse the financial performance of specific project aspects, identify any variances from the budget, and take timely corrective actions. It ensures that the project remains within budget and aids in making informed financial decisions throughout the project lifecycle.
11 | 444 | Which of the following is not a common project cost control action? | Influencing the factors that create changes to the authorised cost baseline | Ensuring that all change requests are acted on in a timely manner | Monitoring work performance against funds expended | Informing the regulator of all approved changes and associated cost | 4 | 5A | 2 | b | 5A-2b | Informing regulators is not a typical project cost control activity. It is more about compliance and reporting. The other options are common actions in cost control processes.
11 | 445 | What is the Estimate at Completion (EAC) used in project cost management? | Updating the project schedule | Assessing project risks | Forecasting the total project cost | Managing changes to the cost baseline | 3 | 5A | 2 | b | 5A-2b | EAC provides a forecast of the total cost of the project at completion based on current performance. “Updating the project schedule” relates to schedule management. “Assessing project risks” refers to risk management. “Managing changes to the cost baseline” is part of cost control but not the direct purpose of EAC.
11 | 446 | What does the approved cost baseline represent? | The actual cost spent on the project | The authorised budget for the project | The initial budget for the project | The performance measurement baseline | 2 | 5A | 2 | b | 5A-2b | The cost baseline is the approved version of the project budget, including all approved changes. Thus, “The authorised budget for the project” is correct. The other options, “The actual cost spent” is actual costs, not the baseline, “The initial budget” is before any changes or approvals, and “The performance measurement baseline” is broader, including scope and schedule baselines.
11 | 447 | You are a project manager for Laurel’s Theatre Productions. Your new project is over budget and requires a cost change through the cost change control system. All of the following statements are true regarding Control Costs except for which one? | A description of how cost changes should be managed and controlled is found in the cost management plan. | Approved cost changes are reflected in the cost baseline. | EVM is used to determine the cost performance that must be realised for the remaining work of the project to meet the BAC goal. | This equation, EAC = BAC / CPI, forecasts an estimate at completion, assuming future project performance will be the same as past performance. | 3 | 5A | 2 | b | 5A-2b | “EVM is used to determine the cost performance that must be realised for the remaining work of the project to meet the BAC goal.” This statement is not true. Earned Value Management (EVM) measures current project performance and forecasts future performance, but it does not specifically determine the performance that must be realised to meet the BAC goal. The To-Complete Performance Index (TCPI) is used for this purpose.
14 | 448 | You are coaching several new project managers on effectively controlling stakeholder engagement. The project managers are confused about why change requests arise from this process. What is the most likely type of change that will result from monitoring stakeholders’ engagements? | Technology change | Errors or omissions in requirements | External changes | Corrective actions | 4 | 5B | 2 | b | 5A-2b | Defects are changes that have already happened and differ from what was planned in the project. To be solved, a defect requires a change through corrective action to bring the results back in alignment with the project scope. The other options are all examples of common change requests, but the most likely change from monitoring stakeholder engagements will be from corrective actions.
14 | 449 | Which of the following is not an input to controlling quality? | Project deliverables | Work performance measurements | Quality control measurements | Test and evaluation documents | 3 | 5B | 2 | b | 5A-2b | “Quality control measurements” is the correct answer because it is an output of controlling quality. The other options are incorrect because all these items are included in the input to quality control.
14 | 450 | Which tools or techniques are not listed in PGPG to be used in the Control Quality process? | Statistical sampling | Performance reviews | Fishbone diagrams | Change control tools | 4 | 5B | 2 | b | 5A-2b | “Change control tools” is the correct answer because they are a technique listed for use in the Perform Integrated Change Control process. The other options are incorrect because they are tools and techniques for the Control Quality process. Remember, cause-and-effect diagrams are also called Ishikawa diagrams and fishbone diagrams.
14 | 451 | These diagrams rank-order factors for corrective action by frequency of occurrence. They are also a type of histogram. What is it? | Control charts | Process flowcharts | Scatter diagrams | Pareto diagrams | 4 | 5B | 2 | b | 5A-2b | Pareto diagrams rank-order important factors for corrective action by frequency of occurrence.
14 | 452 | Which one of the following statements is correct? | Validate scope is primarily concerned with the correctness of deliverables. | Control quality is primarily concerned with the acceptance of the deliverables. | Control quality is generally performed before scope validation, but these two can be performed in parallel. | Validation of scope can only be done at the end of the project. | 3 | 5B | 2 | b | 5A-2b | Validate scope is primarily concerned with the acceptance of deliverables, while control quality is mainly concerned with the deliverables' correctness. Control quality is generally performed before scope validation, but these two can be performed in parallel. Validate scope can be done at the end of each project phase in the project life cycle and other points throughout the project as part of monitoring and controlling, i.e., validate scope is done multiple times during the project.
14 | 453 | You are managing a design project, and one of the project deliverables has a major defect. You have involved the project management and engineering teams in investigating the situation. The project management team believes that the defect is due to the lack of proper software to create the deliverable, and the engineering team believes that the lack of correct input information has caused the defect. You decide to use a fishbone diagram to address the root of the problem. In which part of the quality management process group are you involved? | Analyse quality | Control quality | Manage quality | Plan quality | 2 | 5B | 2 | b | 5A-2b | The situation described in the question is about quality control. While the project team is analysing the situation, “analyse quality” is a made-up term and is not the title of a project management process.
14 | 454 | The project manager wants to analyse the relationship between water pH levels and the number of pool leaks. Which tool should they use? | Scatter diagram | Flowchart | Check sheet | Pareto chart | 1 | 5B | 3 |  | m5A-3 | The correct answer is "Scatter diagram" because it evaluates the relationship between two variables. The other options are wrong because they serve different purposes, such as tracking or categorising issues​.
14 | 455 | To map the steps involved in pool equipment installation and identify bottlenecks, which quality tool should be used? | Run chart | Histogram | Flowchart | Check sheet | 3 | 5B | 3 |  | m5A-3 | The correct answer is "Flowchart" because it visually maps the steps in a process to identify bottlenecks. The other options are wrong because they do not provide process mapping​.
14 | 456 | A project team combines check sheets and control charts to assess defects and monitor trends. What is the advantage of combining these tools? | It helps identify root causes. | It monitors both frequency and process trends. | It ensures complete defect tracking. | It tracks defect correlation with other variables. | 2 | 5B | 3 |  | m5A-3 | The correct answer is "It monitors both frequency and process trends" because check sheets track frequency while control charts monitor trends over time. The other options are wrong because they misrepresent the tools' combined functionality​.
14 | 457 | A construction project team is using a fishbone diagram to analyse quality issues. What is the primary purpose of this tool? | Monitor project timelines | Identify potential delays | Track the frequency of defects | Categorise root causes of problems | 4 | 5B | 3 |  | m5A-3 | The correct answer is "Categorise root causes of problems" because the fishbone diagram visually maps causes and their relationships to a problem. The other options are wrong because this tool is not used for tracking or monitoring timelines​.
17 | 458 | Midway through a construction project, project manager John encounters an unexpected shortage of essential construction machinery, impacting progress. How does John address this resource shortage effectively? | John decides to reduce the project’s scale to match the available machinery. | He continues the project with the existing equipment, accepting potential delays. | John promptly coordinates with the procurement team to acquire additional necessary machinery. | He asks for help from another contractor who has the required equipment. | 3 | 5B | 3 |  | m5A-3 | When encountering an unexpected shortage of essential construction machinery, John should promptly coordinate with the procurement team to address the shortage effectively. This involves identifying the required machinery, assessing availability, and finding suppliers who can provide the needed equipment. Coordinating with the procurement team ensures that the machinery is sourced quickly, minimising project delays and maintaining progress.
17 | 459 | Your project sponsor has asked you to ensure that allotted resources are used, unused resources are immediately released, and no unplanned resources should be allotted. To ensure that, which process would you run? | Plan Resource Management | Control Resources | Manage Resources | Acquire Resources | 2 | 5B | 3 |  | m5A-3 | The Control Resources process in project management ensures that physical resources assigned and allocated to the project are available as planned, used efficiently, and released when no longer needed. This process involves monitoring resource utilisation, managing resource performance, and ensuring that the project uses only the resources that were planned and allocated, releasing unused resources promptly, and avoiding the allocation of unplanned resources. The other options are incorrect because they do not address the ongoing monitoring and control of resource utilisation.
17 | 460 | In the context of project management, which work performance data are commonly utilised to update and adjust resource allocation? | Schedule adherence, stakeholder feedback, and risk assessments. | Resource utilisation rates, actual costs incurred, and individual or team performance metrics. | Changes in project scope, quality metrics, and customer satisfaction levels. | Environmental factors, market trends, and organisational process assets. | 2 | 5B | 3 |  | m5A-3 | Analysing the cost report to identify the cause of the overspend and taking corrective action is the appropriate response. This approach helps in understanding the issue and implementing measures to prevent further overruns and bring the project back on track. Stopping all construction work is a drastic measure and is usually unnecessary and can delay the project further. Disregarding the overspending can lead to bigger financial problems. Requesting additional funds without analysis or understanding the cause does not address the underlying problem.
17 | 461 | During a construction project, project manager John detects a significant overspend on materials compared to the budget. What is John’s likely next step based on his approach to monitoring resource expenditures? | He immediately stops all construction work to reassess the project budget. | John analyses the cost report to identify the reasons for the overspend and seeks to adjust future expenditures. | He disregards the overspend as a minor issue and continues with the project as planned. | John requests additional funds from the client as soon as possible. | 2 | 5B | 4 |  | m5A-4 | When John detects a significant overspend on materials, the appropriate next step is to analyse the cost report to identify the cause of the overspend. This involves examining the details of the expenditure, understanding where the budget has been exceeded, and determining the factors contributing to the overspend. Once the root cause is identified, John can take corrective action, such as renegotiating with suppliers, finding more cost-effective alternatives, or adjusting the project plan to align with the budget.
17 | 462 | As the project manager of a commercial building construction project, you realise that the utilisation of certain materials, such as steel and concrete, is significantly lower than planned. Which advanced strategy should you employ to ensure optimal resource utilisation and avoid unnecessary costs? | Postpone the current tasks involving these materials and divert the team to other tasks that do not require them | Initiate a comprehensive audit to uncover the root causes of underutilisation and implement targeted corrective actions | Increase the order quantity for these materials to build a buffer against future shortages | Temporarily halt the project to reassess and revise the overall resource management plan | 2 | 5B | 4 |  | m5A-4 | Initiating a comprehensive audit allows you to identify the underlying issues causing underutilisation and implement targeted corrective actions, ensuring optimal resource usage. The other options are incorrect because postponing tasks can lead to scheduling issues, increasing order quantity can result in excess inventory and wasted resources, and halting the project can cause significant delays and disrupt the project timeline.
17 | 463 | As the project manager for a large-scale residential development, you notice that the cost of raw materials has unexpectedly increased, threatening to exceed the project budget. What strategy should you implement to manage these escalating costs while maintaining project progress? | Freeze current purchases and use existing stock, hoping that material prices will decrease soon | Redirect funds from the contingency budget to cover the increased costs without altering the project plan | Conduct a value engineering exercise to identify potential cost-saving opportunities without compromising quality | Negotiate with the current suppliers for extended payment terms to manage cash flow better | 3 | 5B | 4 |  | m5A-4 | Conducting a value engineering exercise allows you to find cost-saving opportunities without compromising the quality of the project. The other options are incorrect because negotiating extended payment terms addresses cash flow but not the increased costs, freezing purchases and using existing stock can halt progress and redirecting funds from the contingency budget without a plan can lead to further financial issues.
17 | 464 | During the construction of a major infrastructure project, you find that the utilisation of heavy machinery is inefficient, leading to higher operational costs. What approach should you take to optimise machinery use? | Schedule intensive training sessions for operators to improve their efficiency and reduce machine idle time | Lease additional machinery to distribute the workload and minimise wear and tear on existing equipment | Implement a machine performance monitoring system to gather data and adjust operations based on real-time insights | Rotate machinery between different project sites to ensure consistent use and avoid over-reliance on specific machines | 3 | 5B | 4 |  | m5A-4 | Implementing a machine performance monitoring system allows for data-driven adjustments to operations, optimising machinery use and reducing operational costs. The other options are incorrect because intensive training may not address all efficiency issues, leasing additional machinery increases costs, and rotating machinery can cause logistical challenges and might not solve the core inefficiency problem.
17 | 465 | You are overseeing the construction of a new hospital, and a key subcontractor has repeatedly failed to meet deadlines, affecting the overall project schedule. What approach should you take to manage this situation effectively? | Terminate the subcontractor’s contract immediately and hire a replacement without further assessment | Develop a detailed performance improvement plan with the subcontractor, including clear milestones and regular reviews | Absorb the delayed tasks into the main project team to ensure they are completed on time | Escalate the issue to the client and seek their directive on how to proceed with the subcontractor | 2 | 5B | 4 |  | m5A-4 | Developing a detailed performance improvement plan ensures that the subcontractor is held accountable while providing them with the opportunity to improve performance. The other options are incorrect because terminating the contract immediately can cause further delays and legal issues, absorbing tasks into the main project team can overwhelm your resources, and escalating the issue to the client may not provide a timely solution and can affect client confidence in the project management.
17 | 466 | A construction project faces unexpected cost overruns due to inaccurate cost estimations in the early planning phase. What is the best course of action to manage these overruns? | Request additional funding from the client to cover the overruns | Reallocate funds from other project areas | Conduct a cost review and implement cost-saving measures, such as value engineering | Halt the project temporarily to reassess the budget and obtain new estimates | 3 | 5B | 4 |  | m5A-4 | The correct answer is "Conduct a cost review and implement cost-saving measures, such as value engineering" because it allows the team to address overruns strategically without halting or jeopardising other critical activities. The other options are incorrect as they either fail to assess the issue or disrupt progress.
20 | 467 | What are some common tools and techniques a project manager can use to assess whether a communication is appropriate for the intended audience? | Observation and Conversation, Expert Judgment, and Stakeholder Engagement Assessment Matrix | Observation and Conversation, Risk Register, Project Schedule | Risk Register, Expert Judgment, and Stakeholder Engagement Assessment Matrix | Observation and Conversation, Stakeholder Engagement Assessment Matrix, Risk Register | 1 | 5B | 4 |  | m5A-4 | The correct answer is “Observation and Conversation, Expert Judgment, and Stakeholder Engagement Assessment Matrix”. These tools and techniques help a project manager assess the appropriateness of communication. Observation and Conversation offer real-time feedback by gauging stakeholder reactions and understanding. Expert Judgment leverages experience to determine the most effective communication strategies. The Stakeholder Engagement Assessment Matrix evaluates whether communication aligns with stakeholder expectations and engagement levels. The Risk Register and Project Schedule focus on risk management and timelines, not directly on communication assessment.
20 | 468 | In project management, what is the primary objective of the Monitor Communications process? | To revise and fine-tune the communication management plan based on project evolution. | To maintain effective information exchange as outlined in the communications management plan and stakeholder engagement plan. | To design and implement new methods of project communication as the project progresses. | To track communication milestones and integrate them into the overall project timeline. | 2 | 5B | 5 |  | 5A-5 | The correct answer is “To maintain effective information exchange as outlined in the communications management plan and stakeholder engagement plan”. The primary objective of the Monitor Communications process is to ensure that communication remains effective and aligned with the project’s needs, following the guidelines set in the communications management plan and stakeholder engagement plan. This process helps identify and resolve any communication issues in a timely manner to keep stakeholders informed and engaged. On the other hand, revising plans happens during the change management process if needed. Designing new communication methods is not typically a focus of monitoring. Tracking communication milestones is not a standalone objective but part of broader project performance tracking.
20 | 469 | You are managing a large-scale construction project. The stakeholders have raised concerns that they are not receiving critical updates on project timelines, leading to delays in decision-making. You review the communications management plan and notice that the chosen communication channels and the frequency of updates may not suit the stakeholders’ needs. How should you proceed to address this issue? | Increase the frequency of email updates to all stakeholders to ensure everyone is informed regularly. | Conduct a stakeholder engagement assessment to identify the communication preferences and needs of key stakeholders. | Implement weekly team meetings to provide updates in person and ensure face-to-face communication. | Use expert judgment to decide on the most effective communication channels without consulting the stakeholders. | 2 | 5B | 5 |  | 5A-5 | The correct answer is conducting a stakeholder engagement assessment as it allows you to understand the specific communication needs of stakeholders and tailor your approach accordingly. This ensures that the right stakeholders receive the right information at the right time. The other options are wrong because may overwhelm stakeholders with irrelevant information, may not suit all stakeholders’ availability or preferences, and disregards the need for stakeholder input, which is crucial in ensuring communication effectiveness.
20 | 470 | During the construction of a multi-story building, you notice that several communication issues have arisen. The project team misunderstood a critical update, resulting in the wrong materials being delivered on-site. You want to ensure that such miscommunications do not occur in the future. What is the best course of action to improve communication? | Review the message delivery process and ensure that all communications are sent through email to maintain a written record. | Update the stakeholder engagement plan to ensure more frequent meetings to discuss project updates face-to-face. | Conduct a review of the communication process, focusing on message content, audience analysis, and channel appropriateness. | Rely on observation and expert judgment to identify any potential gaps in communication and fix them. | 3 | 5B | 5 |  | 5A-5 | The correct answer is reviewing the communication process comprehensively by focusing on message content, audience analysis, and channel appropriateness helps to ensure that the right message reaches the right stakeholders effectively. The other options are wrong because it assumes that email is the most appropriate channel, which may not be true for all stakeholders, increases the frequency of meetings but does not address the underlying communication process, and it uses a more reactive approach rather than systematically addressing the root cause of communication breakdowns.
20 | 471 | You are performing actions such as collecting and reporting information regarding the progress of the project and ensuring that the right information is delivered to the right people at the right time. Which process are you performing? | Monitor Communications | Perform Integrated Change Control | Monitor and Control Project Work | Control Procurements | 1 | 5B | 5 |  | 5A-5 | This question describes the Monitor Communications process, which is concerned with collecting and reporting information regarding project progress and project accomplishments to the stakeholders.
20 | 472 | You are managing a construction project for a new corporate headquarters. Your team identifies recurring issues with the delivery of project updates to suppliers, causing delays in material shipments. What is the best way to resolve these communication issues? | Create a centralised project dashboard to share updates with all stakeholders in real-time | Increase the frequency of email communications to ensure suppliers are always informed | Hold daily meetings with suppliers to discuss project updates in detail | Assign a dedicated communications officer to manage supplier interactions | 1 | 5B | 5 |  | 5A-5 | The correct answer is "Create a centralised project dashboard to share updates with all stakeholders in real-time" because it provides a consistent and transparent platform for communication. The other options are either inefficient or do not address the root cause of the issue effectively.
23 | 473 | Why is it crucial to continuously assess the effectiveness of implemented risk responses in a construction project? | To avoid the need for further risk management planning | To document risk management efforts for future projects | To ensure that risks are being managed effectively and adjustments can be made as needed | To satisfy regulatory requirements | 3 | 5B | 5 |  | 5A-5 | Continuously assessing the effectiveness of implemented risk responses in a construction project is crucial to ensure that risks are being managed effectively and that any necessary adjustments can be made promptly. Construction projects are dynamic and can encounter unforeseen challenges, making it essential to regularly evaluate whether risk responses are achieving their intended outcomes. This ongoing assessment helps in identifying any new risks, changing conditions, or ineffective strategies, allowing the project team to adapt and take corrective actions to mitigate risks and keep the project on track.
23 | 474 | Which of the following is not an input to the Monitor Risks process? | Work performance reports | Work performance information | Work performance data | Risk management plan | 2 | 5B | 5 |  | 5A-5 | Work performance information is the correct answer because work performance information is an output of the Monitor Risks process, not its input. The other options are incorrect because these items are included in the input of monitoring risks.
23 | 475 | During the construction of a high-rise building, the project manager, Sarah, identifies a significant risk: the potential delay in the delivery of a custom-made glass façade, which is crucial for the project. She initially chooses to mitigate this risk by contracting multiple suppliers. However, midway through the project, one key supplier suddenly goes out of business. How should Sarah adjust her risk response plan to address this unique risk effectively? | Sarah should continue with the remaining suppliers, ignoring the potential impact of losing one key supplier. | She progressively slows down suitable construction activities until a new supplier is found, to avoid further risks. | Sarah reassesses the situation and decides to expedite orders with the remaining suppliers and looks for additional suppliers to fill the gap. | She changes the building design to accommodate readily available materials, compromising the original architectural plan. | 3 | 5B | 6 |  | 5A-6 | When a key supplier goes out of business, Sarah needs to promptly seek alternative suppliers to ensure the custom-made glass façade is delivered on time. Additionally, she should revise the project schedule to accommodate any potential delays caused by this disruption. This adjustment involves updating the risk response plan to include the new suppliers, renegotiating delivery timelines, and communicating the changes to stakeholders to manage their expectations. The other options are incorrect as to immediately stop all work related to the glass façade until a new supplier is found could cause unnecessary delays and is not a proactive approach. Similarly, if Sarah decides to proceed with the remaining suppliers without seeking new ones, it might not mitigate the risk effectively, especially if the remaining suppliers cannot meet the demand. Requesting for additional funds does not directly solve the problem of missing supplier and may lead to further complications.
23 | 476 | What is a common output of monitor risk process if a significant shift in overall project risk is identified? | Change Requests | Risk Register | Lessons Learned | Updated Project Charter | 1 | 5B | 6 |  | 5A-6 | When a significant shift in overall project risk is identified during the Monitor Risks process, a common output is updates to the risk management plan. This involves reassessing risks, updating risk responses, and making necessary adjustments to the plan to reflect the new risk landscape. It ensures that the project remains aligned with its risk management strategy and that all stakeholders are informed of the changes.
23 | 477 | During a bridge construction project, project manager Alex finds that unforeseen geological challenges significantly increase excavation difficulty, impacting the project risk. What should Alex consider regarding the project’s contingency reserves considering this new information? | Conduct a reserve analysis to evaluate whether to adequately enhance the contingency reserves to cover the heightened risks associated with the complex excavation | Review the current contingency reserves by conducting a cost-benefit analysis to determine whether they are sufficient | Strategically reallocate existing project funds, while keeping contingency reserves unchanged, to address the new excavation challenges | Consult with stakeholders to understand the implications of increasing reserves versus adjusting project scope or timelines | 1 | 5B | 6 |  | 5A-6 | Conducting a reserve analysis allows Alex to evaluate the adequacy of the current contingency reserves considering the new geological challenges. This process involves assessing whether the existing reserves are sufficient to cover the increased risks and determining if additional reserves are necessary. Enhancing the contingency reserves ensures that the project has a financial buffer to address the unforeseen difficulties without jeopardising the overall project budget and timeline. While reviewing reserves is important, a cost-benefit analysis alone may not provide a comprehensive evaluation of the adequacy of reserves in relation to the heightened risks. While stakeholder consultation is valuable, it should be preceded by a thorough reserve analysis to inform the discussion and decision-making process. Strategically reallocate existing project funds may compromise other aspects of the project and does not address the need for sufficient contingency reserves to manage the increased risks.
23 | 478 | A project manager is getting risk-related recommended corrective actions recommended by his team. In which of the following processes is the project manager involved? | Perform Integrated Change Control | Plan Risk Responses | Identify Risks | Monitor Risk | 4 | 5B | 6 |  | 5A-6 | Monitor Risk is the correct answer because risk-related recommendations for corrective actions are the output of the risk monitoring and controlling process. The other options are incorrect because the outputs of these processes do not include recommended corrective actions.
23 | 479 | During the construction of a residential complex, the project team identifies a significant delay risk associated with unforeseen delays in obtaining regulatory permits. What should the project manager do to address this risk effectively? | Continue with the construction activities even if the permits are not obtained as the chances of being caught is low | Allocate additional funds from the contingency budget to cover the delays | Engage with regulatory authorities to expedite the permit process and adjust the project schedule | Focus on completing other project activities to mitigate the expected delays in the issuance of permits | 3 | 5B | 6 |  | 5A-6 | The correct answer is "Engage with regulatory authorities to expedite the permit process and adjust the project schedule" because this approach directly addresses the risk by working with stakeholders to mitigate delays. The other options are incorrect because continuing construction increases the risk of the project, focusing on other project activities does not decrease the risk of this activity, and reallocating funds does not resolve the underlying issue.
26 | 480 | Which of the following improves the reliability of a project procurement system? | Project risk management plan that focuses on procurement activities. | Organisation’s code of ethics that spells out what should and should not be done. | Project charter describing the activities of Procurement and how it is run. | Project management plan that necessitates a procurement plan. | 2 | 5B | 6 |  | 5A-6 | The correct answer is “Organisation’s code of ethics that spells out what should and should not be done”. A code of ethics improves the reliability of a procurement system by promoting transparency, fairness, and integrity. It sets clear expectations for appropriate behaviour, ensuring that procurement activities are conducted ethically, which helps prevent fraud and conflicts of interest. In contrast, the risk management plan focuses on mitigating procurement risks but does not ensure reliability on its own. The project charter outlines high-level project objectives, not detailed procurement processes. The project management plan ensures procurement planning but does not directly address ethical behaviour, which is crucial for reliability.
26 | 481 | How can project teams prevent paying for incomplete or unsatisfactory work? | By conducting detailed risk assessment on the seller’s profile | Ensure that there are good communications with the seller | By closely monitoring the progress of the seller against the contract milestones and deliverables | By ensuring that sellers are carefully selected | 3 | 5B | 6 |  | 5A-6 | The correct answer is “By closely monitoring the progress of the seller against the contract milestones and deliverables”. Monitoring the seller’s progress ensures that payments are tied to specific milestones or deliverables outlined in the contract. This approach helps identify and address issues early, ensuring that work meets expectations before payment is released. In contrast, risk assessments and careful selection of sellers help minimise risks but do not directly ensure satisfactory work delivery. Good communication supports smooth operations but must be coupled with proper monitoring to ensure work quality.
26 | 482 | Which of the following is not a typical consideration when making changes to procurement agreements? | Proper planning and communication | Team morale | Written documentation | Compliance with legal requirements | 2 | 5B | 6 |  | 5A-6 | The correct answer is “Team morale”. While team morale is important for project success, it is not a primary factor in making changes to procurement agreements. Changes to procurement agreements focus more on ensuring proper planning, clear communication, legal compliance, and maintaining a record of the changes through written documentation. In contrast, planning and communication are crucial for managing procurement changes effectively. Written documentation ensures transparency and accountability. Compliance with legal requirements is essential to avoid disputes or legal issues.
26 | 483 | Why should agreement changes ideally be made in writing? | To increase project transparency so that all stakeholders have access to the modified agreement | To provide a clear and documented record to prevent misunderstanding among the parties | To speed up the change process | To reduce legal costs involved in the change process | 2 | 5B | 7 |  | 5A-7 | The correct answer is “To provide a clear and documented record to prevent misunderstanding among the parties”. Making agreement changes in writing ensures there is a clear, formal record of the modifications, helping to avoid misunderstandings or disputes between the parties involved. It ensures that everyone is aligned on the new terms and can refer to the documentation if needed. In contrast, while written changes can increase transparency, the primary goal is to avoid misunderstandings. Written agreements do not necessarily speed up the process or reduce legal costs but provide essential clarity and legal protection.
26 | 484 | Which external factor can influence procurement decisions, and organisations should monitor it closely? | Project budget overruns coming from vendor overtime. | Market conditions due to an oversupply of materials. | Supplier capabilities have improved due to more experienced staff hired. | Internal processes have been optimised through purchasing a new software. | 2 | 5B | 7 |  | 5A-7 | The correct answer is “Market conditions due to an oversupply of materials”. Market conditions are an external factor that can significantly impact procurement decisions. Factors like material availability, pricing fluctuations, and supply-demand imbalances affect procurement strategies. Organisations must monitor these conditions to capitalise on favourable market trends or mitigate risks. In contrast, budget overruns and internal process improvements are internal factors. Supplier capabilities reflect vendor-specific changes, not broader external market conditions.
26 | 485 | You are a project manager for an engineering company. Your company won the bid to add ramp-metering lights to several on-ramps along a stretch of highway at the south end of the city. You subcontracted a portion of the project to another company. The subcontractor’s work involves digging the holes and setting the lamp poles in concrete. The subcontractor’s performance to date does not meet the contract requirements. Which of the following is not a valid option? | You document the poor performance in written form and send the correspondence to the subcontractor. | You terminate the contract for cause and submit a change request through Control Procurements. | You submit a change request through the Control Procurements process demanding that the subcontractor comply with the terms of the contract. | You agree to meet with the subcontractor to see whether a satisfactory solution can be reached. | 3 | 5B | 7 |  | 5A-7 | The contract change control system describes the processes you will use to make changes to the contract; it is not a means of communication. The changes might include contract term changes, date changes, and termination of a contract.
26 | 486 | As a project manager overseeing a large construction project, you notice that the project is lagging due to delays in material deliveries from multiple suppliers. You initiate a procurement performance review to determine which suppliers are responsible for the delays and how to address them. What would be the most appropriate action based on the procurement performance review? | Cancel all contracts with the suppliers and switch to new vendors immediately. | Initiate claims against the suppliers for breach of contract, regardless of the cause of delay. | Adjust procurement schedules to reflect the revised timelines and address the delays with corrective actions. | Continue with current suppliers and accept that the delay is part of project risks. | 3 | 5B | 7 |  | 5A-7 | The correct approach is to adjust procurement schedules and apply corrective actions to address delays. This aligns with effective procurement performance management, which involves understanding the root causes of delays and adjusting plans accordingly. The other options are wrong because cancelling contracts without proper analysis can create more issues, initiating claims without reviewing the contractual terms may lead to legal complications, and passively accepting delays without action risks further project setbacks.
26 | 487 | During the construction of a residential building, new government regulations regarding environmental safety standards come into effect, which requires changes to the material specifications in your current procurement contracts. You need to implement these changes quickly to avoid penalties. Which action should you take to manage this contract change effectively? | As they are regulatory requirements, modify the contracts immediately and notify suppliers after the changes are implemented. | Proceed with the project as per the old contracts and negotiate new terms after completion. Perhaps ask for an exemption. | Refuse to implement changes as they were not part of the original agreement. | Follow the predefined change control process to ensure changes are documented, approved, and communicated. | 4 | 5B | 7 |  | 5A-7 | The correct response is to follow the predefined change control process, which ensures that all changes are properly documented, reviewed, and approved, thus maintaining legal and project integrity. The other options are wrong because making unilateral changes without supplier consent may lead to legal disputes, delaying change negotiations until after project completion is risky and non-compliant, and refusing to implement required changes would breach legal and regulatory obligations.
26 | 488 | As a project manager for a commercial complex, you observe that a supplier is requesting payment before delivering a significant portion of materials. However, this goes against the payment terms outlined in the contract, which specify that payment will be made only upon the delivery of goods. What should be your response in this situation? | Pay the supplier immediately to maintain a good relationship and ensure future deliveries. | Re-negotiate the payment terms to accommodate the supplier’s request. | Delay the payment until the entire order is delivered as per the contract. | Uphold the contract terms, ensuring payment is linked to deliverables and work completed. | 4 | 5B | 7 |  | 5A-7 | Upholding the original contract terms ensures that payments are tied to deliverables and actual work completed, which protects the project’s financial interests. The other options are wrong because paying in advance increases financial risk, re-negotiating terms might undermine contract stability without proper revie, and delaying payment beyond agreed terms can damage the relationship unnecessarily.
26 | 489 | You are managing a government construction project that requires strict adherence to procurement audit standards. During an audit, you discover discrepancies in the documentation of materials purchased for a section of the project. Some records do not match the physical inventory. | Ignore the discrepancies, assuming they will not impact the audit results, since it might have been a mistake by the store. | As there is not enough time, replace the missing documents with fabricated records to align with the audit. | Halt procurement activities until the discrepancies are resolved. Use root cause analysis to find out why the discrepancies. | Investigate the cause of the discrepancies, update the procurement records, and inform the auditors. | 4 | 5B | 7 |  | 5A-7 | The correct approach is to investigate and resolve discrepancies while maintaining transparency with auditors. This builds trust and ensures compliance with procurement standards. The other options are wrong because ignoring discrepancies can result in penalties, fabricating documents is unethical and illegal, and halting procurement activities could delay the project unnecessarily without addressing the root cause of the issue.
26 | 490 | You are a project manager for an engineering company. Your company won the bid to add ramp-metering lights to several on-ramps along a stretch of highway at the south end of the city. You subcontracted a portion of the project to another company. The subcontractor’s work involves digging the holes and setting the lamp poles in concrete. The subcontractor’s performance to date does not meet the contract requirements. Which of the following is not a valid option? | You document the poor performance in written form and send the correspondence to the subcontractor. | You terminate the contract for cause and submit a change request through Control Procurements. | You submit a change request through the Control Procurements process demanding that the subcontractor comply with the terms of the contract. | You agree to meet with the subcontractor to see whether a satisfactory solution can be reached. | 3 | 5B | 2 |  | m5B-2 | The contract change control system describes the processes you’ll use to make changes to the contract; it is not a means of communication. The changes might include contract term changes, date changes, and termination of a contract.
30 | 491 | As the project manager of a major construction project, you have noticed increasing dissatisfaction among the local community. You conducted regular meetings with key stakeholders and implemented feedback mechanisms. However, despite adjusting, complaints have increased, particularly after a scope change. What is the most effective next step in managing this situation? | Stop stakeholder feedback collection to avoid more complaints. | Revise the stakeholder engagement plan to address scope-related concerns. | Focus solely on internal project teams since they are the primary stakeholders. | Conduct a new root cause analysis and modify communication channels accordingly. | 4 | 5B | 2 |  | m5B-2 | The correct answer is conducting a root cause analysis which allows the project manager to identify underlying issues beyond surface-level complaints. By modifying communication channels, the project manager can better align with stakeholder expectations. The other options are wrong because avoiding feedback worsens relationships, revising the stakeholder engagement plan alone would not address unidentified root causes, and focusing only on internal teams overlooks external stakeholders who are essential in a construction project.
30 | 492 | Your construction project is at the mid-stage, and stakeholders from various sectors (e.g., investors, local authorities, and environmental groups) are giving conflicting feedback. You are in the process of modifying the stakeholder engagement plan to maintain project alignment. What tool or technique would be most effective in this situation? | Stakeholder Engagement Assessment Matrix | Social Media Monitoring | Active Listening | Alternatives Analysis | 1 | 5B | 2 |  | m5B-2 | The correct answer is Stakeholder Engagement Assessment Matrix as it helps in mapping out stakeholders’ current and desired levels of engagement, which is critical when balancing conflicting feedback. The other options are wrong because social media monitoring is more suited for public feedback management, active listening helps in communication but does not provide an analytical framework, and alternatives analysis focuses on comparing solutions rather than stakeholder dynamics.
30 | 493 | During the final phase of a construction project, a sudden change in government regulations requires a revision of several project elements. What is the most critical immediate action to ensure effective stakeholder engagement? | Continue with the current stakeholder engagement strategies as the project is nearly complete. | Inform stakeholders of the change during the next scheduled meeting. | Assess the impact of the regulation changes on key stakeholders and modify the engagement plan accordingly. | Delay project activities until a new engagement strategy is developed. | 3 | 5B | 2 |  | m5B-2 | The correct answer emphasises the importance of assessing the impact of regulatory changes on stakeholders and adapting the engagement plan to manage potential concerns or risks. The other options are wrong because sticking to old strategies is ineffective considering new regulations, delaying communication may lead to misalignment, and delaying the project without addressing stakeholder concerns can cause further disruptions.
30 | 494 | In a complex construction project, you observe that the effectiveness of your communication channels has diminished, and stakeholders are becoming disengaged. Which action is the best way to ensure continued stakeholder engagement? | Increase the frequency of meetings without changing the format. | Perform a communication analysis to assess and improve the clarity, frequency, and accessibility of communications. | Delegate stakeholder communication responsibilities to junior team members. | Use formal communication only for major updates and rely on informal channels for minor issues. | 2 | 5B | 2 |  | m5B-2 | The correct answer is performing a communication analysis which allows the project manager to assess and improve how communication methods align with stakeholder expectations. The other options are wrong because increasing the frequency without addressing underlying issues could exacerbate disengagement, delegating to junior staff risks ineffective communication, and relying on informal channels may cause critical information to be missed or misunderstood.
30 | 495 | Your construction project has reached a point where stakeholder feedback indicates dissatisfaction due to unclear project objectives and frequent changes in scope. Which approach should be adopted to enhance stakeholder satisfaction moving forward? | Update the project scope but maintain the current communication frequency. | Conduct regular surveys among stakeholders and adjust the engagement plan based on the feedback. | Address the dissatisfaction by explaining that scope changes are inevitable in construction projects. | Focus on delivering the project on time, even if it means reducing communication with stakeholders. | 2 | 5B | 2 |  | m5B-2 | The correct answer is conducting regular surveys which ensures continuous feedback collection, enabling the adjustment of the engagement plan to address specific stakeholder concerns about project scope and objectives. The other options are wrong because does not address the feedback loop, merely explaining the situation does not solve the problem, and reducing communication risks further stakeholder disengagement and dissatisfaction.
30 | 496 | Which of the following is not an output of monitoring stakeholder engagement? | Performance reports | Change requests | Issues resolved | Stakeholder engagement plan changed | 1 | 5B | 2 |  | m5B-2 | "Performance reports" is correct because work performance information, not performance reports, is an output of monitoring stakeholder engagement. The other options are incorrect because they all are outputs of monitoring stakeholder engagement.
5 | 497 | What is the primary purpose of the “Close Project or Phase” process in project management? | To initiate a new project phase, since the project has ended and that the sponsor is very eager to continue | To finalise all activities for the project or phase | To create a detailed project final report so that closing the project can be done | To ensure all lessons learned are captured at this stage as knowledge management is important for companies as they move forward | 2 | 6 | 2 |  | m5B-2 | The correct answer is “To finalise all activities for the project or phase”. The primary purpose of the “Close Project or Phase” process is to ensure that all activities are completed and that the project or phase is formally closed. This includes verifying that all deliverables are met, closing contracts, and obtaining stakeholder acceptance. In contrast, creating a final report and capturing lessons learned are part of the closure process but are not the primary objective. Initiating a new phase is not relevant to the closure process, as the focus is on completing the current project or phase.
5 | 498 | What does “termination by murder” refer to in project management? | A sudden termination to a project without closure. | Gradual reduction of project funding or cutting off funds from the sponsor to choke the project to naturally end. | Successful integration of project outcomes such that a welcomed end is achieved. | The creation of something entirely new within the organisation, as the top management of the company has decided to introduce this term to describe project progress. | 1 | 6 | 3 |  | m5B-3 | The correct answer is “A sudden termination to a project without closure”. In project management, “termination by murder” refers to a situation where a project is abruptly halted without following formal closure procedures. This could occur due to shifts in priorities, external disruptions, or leadership changes, leaving the project incomplete and without proper documentation or handover. In contrast, gradual reduction of funding describes a slow phase-out, not abrupt termination. Successful integration of outcomes refers to a positive project completion. Introducing new terms within an organisation is unrelated to this concept.
5 | 499 | What is the usual purpose of the “Sticky Note party” during project closure? | Celebrate project completion | Conduct regression analysis | Create project transition plan | Gather stakeholder feedback | 4 | 6 | 3 |  | m5B-3 | The correct answer is “Gather stakeholder feedback”. A “Sticky Note party” is an informal, interactive session often used during project closure to gather feedback from stakeholders. Participants write their thoughts, lessons learned, or improvement suggestions on sticky notes, facilitating open discussions and reflection on the project. In contrast, while celebrating completion is important, the Sticky Note party focuses more on feedback collection. Regression analysis and transition planning are more formal processes handled separately during closure.
5 | 500 | What is the significance of a closeout meeting in project management? | It marks the beginning of a project, so that issues can closeout before the implementation of the early phase. | It is held during project execution such as to end the project meeting before moving to the next activity. | It is an opportunity to assess project performance, before closing it. | It is focused on project initiation, such that all agreements are closeout before starting. | 3 | 6 | 3 |  | m5B-3 | The correct answer is “It is an opportunity to assess project performance, before closing it”. A closeout meeting provides a final opportunity to review the project’s performance, ensuring all deliverables are completed, lessons learned are documented, and stakeholder feedback is gathered. It helps identify successes, challenges, and areas for improvement to apply in future projects. In contrast, project initiation and execution activities occur earlier in the project lifecycle, not during the closeout phase. A closeout meeting is not about closing issues before starting but about finalising and learning from the completed project.
5 | 501 | At the closure phase of a construction project, the project team compiles a “Project Punch List”. What is the primary purpose of this list in ensuring the successful completion of the project? | To revisit and evaluate the achievement of key project milestones and objectives. | To organise a formal event or meeting to mark the completion of the construction project. | To perform a final trend analysis of the project’s performance metrics and outcomes. | To itemise any remaining minor tasks, fixes, or contractual elements that need to be addressed before final handover. | 4 | 6 | 3 |  | m5B-3 | The correct answer is “To itemise any remaining minor tasks, fixes, or contractual elements that need to be addressed before final handover”. A Project Punch List is a detailed checklist of outstanding tasks or issues, such as minor repairs, adjustments, or incomplete work that must be resolved before the project is officially closed and handed over. It ensures that all elements meet the required standards and that no loose ends remain. In contrast, evaluating milestones and trend analysis are part of project performance assessments, not punch list creation. A formal event or meeting marks completion but does not replace the need for a punch list to finalise deliverables.
5 | 502 | When developing a ____ plan, the project team should work with managers in affected operating departments, and the contents of the plan should be tailored to fit the support needs of the project. | training | transition | performance | contingency | 2 | 6 | 3 |  | m5B-3 | The correct answer is “transition”. A transition plan outlines how the project’s outputs (such as deliverables, systems, or services) will be handed over to operational departments for ongoing use or maintenance. The project team works closely with managers in affected departments to ensure a smooth transfer, tailoring the plan to meet the operational needs. In contrast, a training plan focuses on skill development. A performance plan measures objectives and targets. A contingency plan addresses potential risks and unforeseen events.
5 | 503 | Which of the following statements is false? | A lesson learned report during closing is a good-to-have. | It is important to formally close a terminated project. | Closing includes releasing organisational resources. | Closing often includes a final presentation and report. | 1 | 6 | 3 |  | m5B-3 | The correct answer is “A lesson learned report during closing is a good-to-have”. This statement is false because a lessons learned report is not just a “good-to-have”, it is a critical component of project closure. It documents insights, challenges, and successes, providing valuable knowledge for future projects. In contrast, the other statements are true: Terminated projects must still go through formal closure. Releasing resources is essential during closure to reallocate them. A final presentation and report are common elements to summarise the project outcomes.
5 | 504 | What type of project closure occurs when a project’s funding is gradually reduced until it is not sustainable to continue the project? | Extinction | Termination by Murder | Integration | Starvation | 4 | 6 | 4 |  | m5B-4 | The correct answer is “Starvation”. Starvation closure happens when a project’s funding or resources are gradually reduced, making it unsustainable to continue. This can occur intentionally, often as a passive method to end a project without formally cancelling it. In contrast, extinction occurs when a project is completed and achieves its objectives. Termination by Murder refers to a sudden and unexpected termination. Integration happens when the project’s outcomes are absorbed into the organisation’s operations or another initiative.
5 | 505 | You are a project manager at Cinema Snicker Productions, a company that specializes in producing comedy films for the big screen. Your latest project has just been completed and accepted, and you have been assigned your next project, which starts immediately. Which of the following statements is true? | This project ended due to extinction because it was completed and accepted. | This project ended due to integration because it was completed and accepted and the project manager moved on to a new project. | This project ended due to addition because it was completed, accepted, and archived into the company’s catalogue of available films. | This project ended due to integration because it was completed and accepted. | 1 | 6 | 4 |  | m5B-4 | Extinction is the best type of project end because it means the project was completed successfully and accepted by the sponsor or customer.
5 | 506 | You are a project manager for Aloha Productions. Your company specialises in producing period films for the small screen. Your latest project has just been cancelled because of budget cuts. Which of the following statements is true? | This project ended due to starvation because the funding was cut off. | This project ended due to integration because the resources were distributed elsewhere. | This project ended due to starvation because the resources were distributed elsewhere. | This project ended due to integration because the funding was cut off. | 1 | 6 | 4 |  | m5B-4 | Starvation occurs because the project no longer receives the resources needed to continue. Resources include people, equipment, money, and the like.
5 | 507 | As a project manager, you are currently involved in a Close Project or Phase process. In this situation which one of the following activities might possibly be unnecessary? | Finalising all activities across all the Project Management Process Groups. | Measuring the project scope against the project management plan. | Performing activities such as finalising open claims, updating procurement records to reflect results, and archiving such information for future use. | If a project is terminated before completion, starting procedures to investigate and document the reasons for this early termination. | 3 | 6 | 4 |  | m5B-4 | Closing out a contract involves administrative activities such as finalising open claims, updating records to reflect results, and archiving such information for future use. Procurement Close could be done at any stage of the project and is not associated only with Close Project or Phase process.
5 | 508 | As the manager of a large project, including a huge part of procurement activities, you are about to start project closure activities. All final deliverable of the project is validated. What should be your first step in project closure? | Start closing out contracts | Ensure completion of scope as per Project Management Plan | Start Claims Administration | Start Administrative Closure | 2 | 6 | 4 |  | m5B-4 | When closing the project, the project manager must review all the prior information from the previous phase closure to ensure that all project work is completed and that the project has met its objectives. Since project scope is measured against the scope management plan, the project manager reviews the scope baseline (part of the project management plan) to ensure completion before considering the project closed.
5 | 509 | As the project manager for a large commercial building project, you are nearing the close of the project and are responsible for compiling the lessons learned report. You notice that several project team members express reluctance to participate, citing time constraints and a lack of formal procedures. How should you approach this situation to ensure effective knowledge transfer and organisational learning? | Forgo the lessons learned report as time is tight and focus on project closure tasks. | Conduct a formal meeting with the project team and gather lessons learned despite time constraints, as this process is essential for organisational improvement. | Outsource the documentation process to an external consultant to save time and ensure objectivity. | Rely on informal discussions with team members to gather lessons learned and document them as you see fit. | 2 | 6 | 4 |  | m5B-4 | Conducting a formal meeting with the project team to document lessons learned is crucial for ensuring organisational improvement and knowledge transfer. Effective project managers recognise the importance of formal procedures, as failing to capture these lessons hinders learning for future projects. The other options are wrong because forgoing the report disregards the value of knowledge sharing, outsourcing can lead to a lack of internal accountability and insights, and relying on informal discussions risks missing key lessons that structured meetings can capture.
5 | 510 | You are managing a construction project that is nearing completion. Your organisation values knowledge management and expects a comprehensive handover to the operations team. However, budget cuts have left you with limited resources for knowledge transfer sessions. What is the best approach to ensure that knowledge is effectively transferred despite these constraints? | Postpone knowledge transfer until additional budget can be secured. | Provide written documentation only, as this is less resource intensive. | Prioritise critical knowledge transfer sessions with key personnel in smaller groups to ensure continuity. | Skip knowledge transfer altogether, assuming the operations team can learn by trial and error. | 3 | 6 | 4 |  | m5B-4 | Prioritising critical knowledge transfer sessions with key personnel ensures that vital information is communicated, even with limited resources. Small groups allow for detailed knowledge exchange, ensuring continuity and reducing the risk of miscommunication. The other options are wrong because postponing risks delays in operations, written documentation alone may not ensure understanding, and skipping transfer undermines the whole process of efficient project handover.

## Quiz
cell_index | question_index | question_text | opt_1 | opt_2 | opt_3 | opt_4 | answer | mod | parent | sub | id
0 | 1 | Which of the following is an attribute of a project? | A project has a unique purpose. | A project can be temporary or ongoing. | A project is developed in a linear fashion. | A project involves certainty. | 1 | 1 | 2 | 0 | m120-01
0 | 2 | Project ____ may be defined as a test of whether a project has met scope, time, and cost goals. | depth | clarity | success | vision | 3 | 1 | 2 | 0 | m120-02
0 | 3 | Project success is unlikely to be defined based on which of the following? | Business value created | Scope, schedule, and cost goals | Customer satisfaction | Comprehensiveness of project management plan | 4 | 1 | 2 | 0 | m120-03
0 | 4 | Which of the following is not an attribute of a project? | Projects are unique | Projects involve no uncertainty | Project has a primary customer or sponsor | Projects are developed using progressive elaboration | 2 | 1 | 2 | 0 | m120-04
0 | 5 | Which of the following is not part of the triple constraint of project management? | Meeting scope goals | Meeting schedule goals | Meeting communication goals | Meeting cost goals | 3 | 1 | 2 | 0 | m120-05
0 | 6 | What role do projects play within an organization? | Maintaining the status quo | Initiating operational activities | Driving change within the organization | Following day-to-day routines | 3 | 1 | 2 | 0 | m120-06
0 | 7 | What represents the change in a project’s context? | Remaining in the current state | Maintaining consistent operations | Transitioning from future state to current state | Moving from current state to a new future state | 4 | 1 | 2 | 0 | m120-07
0 | 8 | What role does business value play in project justification? | It ensures operational efficiency | It guarantees intangible benefits | It justifies the investment in the project | It determines the project timeline | 3 | 1 | 2 | 0 | m120-08
0 | 9 | What are the four main factors identified by PMI’s PGPG that lead to the initiation of projects? | Financial gains, operational efficiency, risk reduction, and market expansion. | Regulatory compliance, stakeholder satisfaction, product innovation, and technological advancements. | Meeting regulatory, legal, or social requirements, satisfying stakeholder needs, improving products or services, and implementing business strategies. | Employee training, internal communication, supplier relations, and branding efforts. | 3 | 1 | 2 | 0 | m120-09
0 | 10 | What is the primary goal of a project manager when dealing with the schedule aspect of the triple constraint? | To create a realistic timeline for project activities | To ensure the project meets safety and health standards | To complete the project ahead of schedule | To allocate the budget efficiently for resources | 1 | 1 | 2 | 0 | m120-010
0 | 11 | Which factor is not part of the triple constraint in project management? | Time | Safety | Scope | Cost | 2 | 1 | 2 | 0 | m120-011
0 | 12 | Which of the following determines whether a project is truly successful? | The alignment between outcomes and desired results | The number of project phases completed | The number of stakeholders involved | The speed at which tasks are completed | 1 | 1 | 2 | 0 | m120-012
0 | 13 | Why is communication with customers and sponsors critical for project success? | To ensure immediate project completion | To allocate more resources to the project | To minimize the need for stakeholder feedback | To understand and meet their expectations | 4 | 1 | 2 | 0 | m120-013
0 | 14 | A project is considered successful when __________. | The product of the project has been manufactured. | The project sponsor announces the completion of the project. | The product of the project is turned over to the operations area to handle the ongoing aspects of the project. | The project achieves its objectives and meets the expectations of the stakeholders. | 4 | 1 | 2 | 0 | m120-014
0 | 15 | _________ is the application of knowledge, skills, tools, and techniques to project activities to meet project requirements. | Program management | Project management | Project portfolio management | Project performance domain | 2 | 1 | 3 | 0 | m130-01
0 | 16 | A _______ is a temporary endeavor undertaken to create a unique product, service, or result. | program | process | project | portfolio | 3 | 1 | 3 | 0 | m130-02
0 | 17 | Project portfolio management addresses _______ goals of an organization, while project management addresses ______ goals. | strategic, tactical | tactical, strategic | internal, external | external, internal | 1 | 1 | 3 | 0 | m130-03
0 | 18 | A ______ is defined as projects, programs, subsidiary portfolios, and operations managed as a group to achieve strategic objectives. | core | portfolio | hybrid approach | strategy | 2 | 1 | 3 | 0 | m130-04
0 | 19 | It often makes sense to break large projects down into two or more smaller ______. | projects | programs | portfolios | enterprises | 1 | 1 | 3 | 0 | m130-05
0 | 20 | Which of the following statements best describes the relationship between megaprojects, programs, and portfolios? | Megaprojects can be a subset of programs and portfolios. | Megaprojects are smaller in scope compared to programs and portfolios. | Programs and portfolios are subsets of megaprojects. | Megaprojects, programs, and portfolios are unrelated concepts. | 1 | 1 | 3 | 0 | m130-06
0 | 21 | Many organizations claim that using project management ____. | lower costs | reduces internal coordination | lengthens development time | diminishes customer relations | 1 | 1 | 4 | 0 | m140-01
0 | 22 | One of the project management principles is to focus on ____. | value | people | the customer | quality | 1 | 1 | 4 | 0 | m140-02
0 | 23 | Why is project management considered an important skill for individuals, even if they are not full-time project managers? | To minimize investment waste in projects | To increase prominence and recognition in different industries | To drive changes and introduce new products | To effectively manage personal projects and ensure success | 4 | 1 | 4 | 0 | m140-03
0 | 24 | Which of the following is false about the project-oriented industry? | More people are expected to work in project-oriented industry | Project managers are expected to earn more than functional managers | GDP contributions from project-oriented industries are expected to increase | Good project management can protect investments | 2 | 1 | 4 | 0 | m140-04
0 | 25 | According to a study by the Chartered Institute of Building (CIOB), which of the following reflects poor project management standard in the construction industry? | 30% of projects do not have project managers | 20% of respondents feel that project managers are not given sufficient authority | 50% of respondents feel that there are not enough project management courses in the industry | 10% of respondents are familiar with the use of project management software | 4 | 1 | 4 | 0 | m140-05
0 | 26 | The project management framework (based on the PMBOK® Guide 7th Edition) is driven by the 12 _______. | performance domains | project management principles | artifacts | methods | 2 | 1 | 5 | 0 | m150-01
0 | 27 | _________ coordinate the work of all other project management knowledge areas. | Program management | Project integration management | Project management | Project portfolio management | 2 | 1 | 5 | 0 | m150-02
0 | 28 | Which of the following is a key difference between the PMBOK Guide 6th Edition and 7th Edition? | 7th Edition emphasizes PM principles and performance domains, but 6th Edition emphasizes PM processes | 7th Edition discourages the use of PM processes, but 6th Edition emphasizes PM processes | 7th Edition has 11 knowledge area, but 6th Edition has 10 | 7th Edition emphasizes process groups, but not 6th Edition | 1 | 1 | 5 | 0 | m150-03
0 | 29 | _______ is deliberately adapting the project management approach, governance, and processes to make them more suitable for the given environment and the work. | Tailoring | Change management | Customizing | Way of working | 1 | 1 | 5 | 0 | m150-04
0 | 30 | What do the ten knowledge areas provide in terms of project management? | A strict project timeline | A set of project objectives | A structure to discuss and learn project management | A detailed project budget | 3 | 1 | 5 | 0 | m150-05
0 | 31 | What is the purpose of the "being a steward" principle in project management? | Issuing orders and demanding results from the team | Reducing project challenges and barriers for the team | Applying the concept of situational leadership | Managing financial resources effectively | 2 | 1 | 5 | 0 | m150-06
0 | 32 | What is a crucial skill for project managers to navigate conflicting interests and reach consensus? | Providing direction | Recognizing system interactions | Leading collaborative teams | Negotiating agreements | 4 | 1 | 5 | 0 | m150-07
0 | 33 | What is a project life cycle? | The period during which a project is executed and completed | The sequential phases through which a project progresses from initiation to closure | The documentation and reporting requirements of project | The ongoing maintenance and support activities after project completion | 2 | 1 | 6 | 0 | m160-01
0 | 34 | Predictive projects involve five project management process groups: initiating, planning, ________, monitoring and controlling, and closing. | development | maintaining | designing | executing | 4 | 1 | 6 | 0 | m160-02
0 | 35 | There are ______ processes in the Process Groups: A Practice Guide. | 5 | 10 | 12 | 49 | 4 | 1 | 6 | 0 | m160-03
0 | 36 | Examples of a _____ life cycle include phases called introduction, growth, maturity, and decline/retirement. | product | project | program | development | 1 | 1 | 6 | 0 | m160-04
0 | 37 | Based on the PMBOK® Guide 6th Edition, which process group includes processes for only one knowledge area? | Planning | Executing | Monitoring | Closing | 4 | 1 | 6 | 0 | m160-05
0 | 38 | Who is responsible for evaluating the business value of a project and documenting it to justify the project before project initiation? | Project manager | Project sponsor | Project champion | Senior manager | 2 | 1 | 6 | 0 | m160-06
0 | 39 | What is the purpose of a phase gate or review in a project life cycle? | To allocate resources to different project phases | To determine the project's scope and objectives | To evaluate the project's performance and progress | To finalize the project management plan | 3 | 1 | 6 | 0 | m160-07
0 | 40 | Which construction project life cycle phase involves the creation of detailed architectural and engineering plans? | Prototype | Design | Feasibility study | Transition | 2 | 1 | 6 | 0 | m160-08
0 | 41 | What is the main purpose of the process group known as "monitoring and control"? | To initiate the project | To create detailed plans | To execute project activities | To track and adjust project performance | 4 | 1 | 6 | 0 | m160-09
0 | 42 | What is the key goal of the integrated project delivery (IPD) approach? | Minimize stakeholder involvement | Reduce project efficiency | Encourage active collaboration among stakeholders | Promote individual decision-making | 3 | 1 | 6 | 0 | m160-010
0 | 43 | Why might projects be introduced at different stages of a product's lifecycle? | To enhance customer support capabilities | To improve stakeholder communication | To reduce project complexity | To speed up product development | 1 | 1 | 6 | 0 | m160-011
0 | 44 | What of the following states the five project management process groups in the correct order? | Initiating, Executing, Planning, Monitoring and Controlling, and Closing | Initiating, Monitoring and Controlling, Planning, Executing, and Closing | Initiating, Planning, Monitoring and Controlling, Executing, and Closing | Initiating, Planning, Executing, Monitoring and Controlling, and Closing | 4 | 1 | 6 | 0 | m160-012
0 | 45 | ________ project management is used to describe an approach where the project scope cannot be well-defined upfront, incremental releases are desired, and changes are expected. | Agile | Predictive | Scrum | Hybrid | 1 | 1 | 7 | 0 | m170-01
0 | 46 | What does tailoring refer to in project management? | Adjusting the project schedule based on team availability | Customizing project management processes and methodologies | Modifying project objectives to align with stakeholder expectations | Refining project deliverables based on quality standards | 2 | 1 | 7 | 0 | m170-02
0 | 47 | Adaptive project management is used when the project scope ________. | is large | is small | can be well-defined upfront | cannot be well-defined upfront | 4 | 1 | 7 | 0 | m170-03
0 | 48 | Which is another term for predictive project management? | Hybrid | Adaptive | Waterfall | Agile | 3 | 1 | 7 | 0 | m170-04
0 | 49 | Many ______ projects require project charters, scope statements, and Gantt charts. | hybrid | predictive | adaptive | agile | 2 | 1 | 7 | 0 | m170-05
0 | 50 | Which of the following is an example of a tool or technique used in cost management? | Earned value management | Gantt chart | Scope statement | Work breakdown structure | 1 | 1 | 7 | 0 | m170-06
0 | 51 | What does the term "hybrid approach" mean in project management? | Using only agile approaches for all project phases | Combining predictive, agile, or other approaches as needed | Exclusively using iterative methods throughout the project | Adapting a single approach for all projects | 2 | 1 | 7 | 0 | m170-07
1 | 52 | A ____ is a document that provides justification for investing in a project. | project charter | business case | project management plan | business document | 2 | 2 | 2 | 0 | m220-01
1 | 53 | Which of the following processes is typically not part of the pre-initiating phase in project management? | Defining the project’s objectives and success criteria | Involve stakeholders to create a shared understanding of the success criteria | Developing the project charter | Establishing the project team and assigning roles and responsibilities | 3 | 2 | 2 | 0 | m220-02
1 | 54 | A business case is a document that outlines the justification for undertaking a project and includes various components. Which of the following is typically not included in a business case? | Business objectives | Potential risks | Budget estimate and financial analysis | Project execution plan and timeline | 4 | 2 | 2 | 0 | m220-03
1 | 55 | Which of the following is one of the roles of a project sponsor? | Leading the project team | Documenting project evaluation | Setting project objectives | Advocating for the project and team | 4 | 2 | 2 | 0 | m220-04
1 | 56 | What does a cost-benefit analysis include? | Project risk mitigation | Financial viability | Project schedule | Stakeholder engagement | 2 | 2 | 2 | 0 | m220-05
1 | 57 | When are project managers typically identified? | During project initiation | During project planning | During project execution | During project monitoring and control | 1 | 2 | 2 | 0 | m220-06
1 | 58 | In contrast to a project sponsor, what is the main role of a project manager? | Documenting project requirements | Running the project and making tactical decisions | Advocating for the project | Setting project objectives | 2 | 2 | 2 | 0 | m220-07
1 | 59 | Why might a project be divided into smaller projects? | To reduce project risks | To increase stakeholder engagement | To facilitate effective management | To simplify documentation | 3 | 2 | 2 | 0 | m220-08
1 | 60 | One of the main tasks normally involved in project initiation is identifying project _______. | shareholders | stakeholders | critics | analysts | 2 | 2 | 3 | 0 | m230-01
1 | 61 | What of the following processes are part of the initiating process group? i. Develop project charter ii. Develop project management plan iii. Define scope iv. Identify stakeholders | i. | ii. iv. | i. iii. | i. iv. | 4 | 2 | 3 | 0 | m230-02
1 | 62 | After a project is approved, senior managers should meet to determine the ______, time, and cost constraints for the project. | range | scope | vision | boundary | 2 | 2 | 3 | 0 | m230-03
1 | 63 | When is the kick-off meeting with key stakeholders typically held? | During the planning phase | During the execution phase | During the initiating phase | During the closing phase | 3 | 2 | 3 | 0 | m230-04
1 | 64 | What is an output of the "develop project charter" process? | Stakeholder register | Assumption log | Change request register | Project schedule | 2 | 2 | 3 | 0 | m230-05
1 | 65 | Why might the initiating process lead to changes in the project management plan and project documents? | Due to completion of the project charter | Due to stakeholder resistance | Due to new stakeholders and their requirements | As a result of completed deliverables | 3 | 2 | 3 | 0 | m230-06
1 | 66 | Which of the following processes belong to the Project Integration Management Knowledge Area and Initiating Process Group? | Identify stakeholders | Define scope | Develop project charter | Define project charter and identify stakeholders | 3 | 2 | 3 | 0 | m230-07
1 | 67 | Which of the following is true regarding the project charter? | The project charter should be issued by a manager external to the project. | The project charter should be issued by a key stakeholder’s name. | The project charter should be issued by the project sponsor. | The project charter should be issued by the project manager. | 4 | 2 | 4 | 0 | m240-01
1 | 68 | What are the inputs to the Develop Project Charter process? | Agreements, EEFs, and OPAs | Business case, benefits management plan, and OPAs | Agreements, business documents, EEFs, and OPAs | Business case, benefits management plan, EEFs | 1 | 2 | 4 | 0 | m240-02
1 | 69 | Which of the following statements about project charter is true? | Some organizations initiate projects using a letter of agreement or formal contracts | All large projects must have a project charter | Project charter is part of the project management plan | A project charter authorizes a project sponsor to initiate the project | 1 | 2 | 4 | 0 | m240-03
1 | 70 | Business documents include which of the following? | Business case and Agreements | Project charter and benefits management plan | Business case and benefits management plan | Project charter and agreements | 2 | 2 | 4 | 0 | m240-04
1 | 71 | Which of the following is not an enterprise environmental factor (EEF)? | Organisational culture | Employee capability | Legal restrictions | Project structure | 4 | 2 | 4 | 0 | m240-05
1 | 72 | Which of the following is not an organizational process asset (OPA)? | Checklists | Lessons learned | Communications channel | Report template | 3 | 2 | 4 | 0 | m240-06
1 | 73 | Which of the following is a possible entry for an assumption log of a residential construction project? | Delivery of marble tiles from Italy will take about 2 months | The neighbors next to the site have made three complaints about noise level at night | Based on the soil investigation report, the risk of soil settlement during construction is low | The procurement of marble tiles is to be performed by the contractor | 1 | 2 | 4 | 0 | m240-07
1 | 74 | Which of the following is not a project complexity that should be identified in a project charter? | The possible ambiguity in roles of project stakeholders | The interactions between the major structural and geotechnical work | The age profile of workers involved in the project | Sustainability requirements that constrain the design | 3 | 2 | 4 | 0 | m240-08
27 | 75 | For a construction project, which of the following is most likely an external stakeholder? | Safety auditor | Reinforcement concrete sub-contractor | Client project sponsor | Quantity surveyor | 1 | 2 | 5 | 0 | m250-01
27 | 76 | For a construction project, which of the following is most likely an internal stakeholder? | Government inspector | Change control board members | Concrete supplier | Residents near the site | 2 | 2 | 5 | 0 | m250-02
27 | 77 | Which of the following is not commonly used during stakeholder identification? | Document analysis | Brainstorming | Meetings | Statistical analysis | 4 | 2 | 5 | 0 | m250-03
27 | 78 | Which of the following need not be included in a stakeholder register during initiation? | Internal or external stakeholder | Role in project | Level of influence of stakeholder | Position | 3 | 2 | 5 | 0 | m250-04
27 | 79 | Stakeholder analysis belongs to which process group? | Initiation | Planning | Execution | Monitoring and controlling | 2 | 2 | 5 | 0 | m250-05
1 | 80 | Which of the following is unlikely to be a purpose of a kick-off meeting? | To create a sense of team spirit | To energize the team | To encourage open communication | To evaluate proposed schedule changes | 4 | 2 | 6 | 0 | m260-01
1 | 81 | Which statement about kick-off meeting is true? | It must be face-to-face | Not all stakeholders need to be present | If well-conducted, it can ensure better buy-in | It can be conducted during execution stage | 3 | 2 | 6 | 0 | m260-02
1 | 82 | Who cannot be absent from a kick-off meeting for a construction project? | Project sponsor | Labour supplier | Regulator | Drywall sub-contractor | 1 | 2 | 6 | 0 | m260-03
1 | 83 | Which of the following agenda items is not essential for a kick-off meeting? | Introduction of attendees | Discuss project organizational structure | Identify potential risks | Discuss project scope | 3 | 2 | 6 | 0 | m260-04
1 | 84 | Which of the following need not be used as an input when planning the kick-off meeting? | Project charter | Project management plan | Change control procedure | Stakeholder register | 3 | 2 | 6 | 0 | m260-05
2 | 85 | How many processes are there in the planning process group based on PMBOK Guide 6th Edition? | 12 processes | 24 processes | 36 processes | 49 processes | 2 | 3a | 2 | 0 | m3a20-01
2 | 86 | The main purpose of project planning is to guide project ____. | initiation | execution | review | evaluation | 2 | 3a | 2 | 0 | m3a20-02
2 | 87 | Why is project integration management crucial for project managers? | It coordinates all the project management knowledge areas. | It focuses on individual staff duties and KPIs. | It facilitates communication among stakeholders. | It ensures consistency across scope, schedule, and budget. | 1 | 3a | 2 | 0 | m3a20-03
2 | 88 | What is the purpose of a PM plan? | It ensures consistency across scope, schedule, and budget. | It facilitates project integration management by outlining how the project will be executed, monitored, controlled, and closed. | It focuses on individual staff duties and KPIs. | It facilitates communication among stakeholders. | 2 | 3a | 2 | 0 | m3a20-04
2 | 89 | What is the purpose of baselines in project management? | Future predictions of project outcomes | Benchmarks for measuring project performance | Initial estimates of project scope, schedule, and cost | Observations made during project execution | 2 | 3a | 2 | 0 | m3a20-05
2 | 90 | Which of the following are the first three steps in the integrated change management process? | Change Evaluation, Impact Assessment, Approval | Identification, Impact Assessment, Change Evaluation | Change Planning and Implementation, Change Communication and Stakeholder Engagement, Monitoring and Control | Monitoring and Control, Documentation, Lessons Learned | 2 | 3a | 2 | 0 | m3a20-06
2 | 91 | Scope performance measurement is based on the scope ____. | definition | revision | baseline | statement | 3 | 3a | 2 | 0 | m3a20-07
2 | 92 | Project management ____ facilitates communication among stakeholders and provide a baseline for progress measurement and project control. | charter | contract | standard | plan | 4 | 3a | 2 | 0 | m3a20-08
2 | 93 | What is the purpose of the "Change Management Plan" in project integration? | To manage the project schedule | To document project stakeholders | To control project budget | To authorize and incorporate change requests | 4 | 3a | 2 | 0 | m3a20-09
2 | 94 | Which of the following is a common element in a Project Management Plan? | Performance measurement baseline | Cost forecasts | Activity list | Risk register | 1 | 3a | 2 | 0 | m3a20-010
6 | 95 | A scope baseline is composed of an approved scope statement, a WBS, and a ______. | cost estimate | project schedule | WBS dictionary | project charter | 3 | 3a | 3 | a | m3a3a-01
6 | 96 | Which of the following is not an output of planning for project integration and scope management? | Project website | Project management plan | Scope management plan | WBS | 1 | 3a | 3 | a | m3a3a-02
6 | 97 | A ______ is a deliverable-oriented grouping of the work involved in a project that defines the total scope of the project. | Contract | Gantt chart | WBS | Network diagram | 3 | 3a | 3 | a | m3a3a-03
6 | 98 | What is the first process in project scope management? | Plan scope management | Define scope | Collect requirements | Create WBS | 1 | 3a | 3 | a | m3a3a-04
6 | 99 | What is the purpose of project scope management in a project? | To define and manage project boundaries and deliverables | To gather project requirements from stakeholders | To create a WBS | To define project goals and objectives | 1 | 3a | 3 | a | m3a3a-05
6 | 100 | What is the main difference between validation and verification in project management? | Validation focuses on compliance with regulations, while verification focuses on meeting stakeholder goals. | Validation involves obtaining acceptance from stakeholders, while verification ensures compliance with requirements. | Validation is performed during quality control, while verification is performed during quality assurance. | Validation is a part of scope management, while verification is a part of requirements management. | 2 | 3a | 3 | a | m3a3a-06
6 | 101 | Why is it important for the scope management plan to define roles and responsibilities? | To assign project tasks to team members | To create a detailed project schedule | To establish accountability for scope-related activities | To ensure compliance with regulatory standards | 3 | 3a | 3 | a | m3a3a-07
6 | 102 | Which of the following is the project scope for a construction project? | The need for the loading and unloading bay of a building to be easily accessible for a container truck | The loading and unloading bay of a building that needs to be constructed | A loading and unloading bay that fits a 16-foot container truck | An advanced hydraulic lift system to enhance the efficiency of the loading and unloading bay for handling heavy containers. | 2 | 3a | 3 | a | m3a3a-08
6 | 103 | Which of the following is not included in a scope management plan? | Scope management process | WBS | WBS dictionary | Product scope statement | 4 | 3a | 3 | a | m3a3a-09
6 | 104 | A requirement ________ is a table that lists requirements, various attribute | traceability matrix | management matrix | tracking tool | management plan | 1 | 3a | 3 | b | m3a3b-01
6 | 105 | What is the purpose of a requirements traceability matrix (RTM)? | To create a concise checklist of project requirements | To track the progress of each requirement and ensure proper implementation | To document project requirements in extensive notebooks | To create visual representations of project requirements | 2 | 3a | 3 | b | m3a3b-02
6 | 106 | Why is it important for the project management plan to include information o | To ensure compliance with legal requirements | To provide a comprehensive overview of the project's requirements management | To create a separate document for tracking requirements | To eliminate the need for a separate tracking document | 2 | 3a | 3 | b | m3a3b-03
6 | 107 | Which document outlines the process for collecting and managing requirements | Business case | Requirements documentation | Project charter | Requirements management plan | 4 | 3a | 3 | b | m3a3b-04
6 | 108 | Which of the following describes the requirements management plan correctly? | It describes the detailed project requirements | It records the change process for project requirements | It describes the process for collecting and managing requirements | Requirements management plan | 3 | 3a | 3 | b | m3a3b-05
6 | 109 | What is the purpose of a project scope statement? | To outline the project’s time, cost, and resource estimations | To establish clear communication channels within the project team | To identify the product requirements, user acceptance criteria, and deliverables | To document the project's exclusions and limitations | 3 | 3a | 3 | c | m3a3c-01
6 | 110 | Why is having a well-defined scope important for project success? | It eliminates the need for time, cost, and resource estimations. | It provides a basis for project monitoring and control. | It is the basis for communications within the project team. | It ensures user acceptance of the deliverables. | 2 | 3a | 3 | c | m3a3c-02
6 | 111 | Which of the following best describes a scope creep? | The addition of features and functionalities to a project without customer approval. | The lack of careful evaluation during the scope drafting stage. | The lack of discipline in project management. | The addition of features and functionalities that impact time, cost, and resources. | 4 | 3a | 3 | c | m3a3c-03
6 | 112 | Which of the following is most likely to require updating the scope statement? | New user requirements, constraints, and regulations | Changes in senior management and client relationships | New project team member | Changes in the project timeline due to unexpected events | 1 | 3a | 3 | c | m3a3c-04
6 | 113 | Which technique helps in comparing different execution alternatives during project planning to select optimal solutions? | Expert judgement | Stakeholder engagement | Value engineering | Multicriteria decision analysis | 3 | 3a | 3 | c | m3a3c-05
6 | 114 | What are the six areas of consideration highlighted by PMI’s construction extension to the PMBOK® Guide for defining scope in the construction industry? | Risk assessment, quality standards, stakeholder engagement, project milestones, budget management, regulatory compliance | Statutory requirements, stakeholder requirements, contracts, design specifications, life cycle costing, project management aspects | Supplier selection, technology adoption, legal considerations, financial management, scheduling, project milestones | Communication plan, risk management, resource allocation, change management, stakeholder engagement, quality control | 2 | 3a | 3 | c | m3a3c-06
6 | 115 | The main planning tasks performed as part of project scope management include planning scope management, collecting requirements, defining scope, and creating the _______. | WBS | requirement management plan | requirement traceability matrix | portfolio | 1 | 3a | 3 | d | m3a3d-01
6 | 116 | High level items in a WBS are broken down or ______ into smaller tasks. | segregated | decomposed | allocated | separated | 2 | 3a | 3 | d | m3a3d-02
6 | 117 | A WBS _____ is a document that describes the deliverables on the WBS in more detail. | glossary | statement | dictionary | appendix | 3 | 3a | 3 | d | m3a3d-03
6 | 118 | The _______ approach to creating a WBS is often easier when team members understand the detailed work but are not necessarily thinking of the project from the deliverable perspective. | analogy | top-down | mind-mapping | bottom-up | 4 | 3a | 3 | d | m3a3d-04
6 | 119 | The hierarchy of deliverables in a work breakdown structure (WBS) can be presented in which of the following forms? | Sequential or chronological | Tabular or list form | Activity-focused | Task-oriented | 2 | 3a | 3 | d | m3a3d-05
6 | 120 | How does a work breakdown structure (WBS) contribute to preventing scope creep? | By focusing on project activities | By defining project budget | By identifying scope and boundaries | By reducing the number of stakeholders | 3 | 3a | 3 | d | m3a3d-06
6 | 121 | Which of the following is the most suitable description for an WBS item? | Raft foundation | Raft foundation on compacted hardcore | Excavate the raft foundation | Excavate the raft foundation using excavators and backhoes | 1 | 3a | 3 | d | m3a3d-07
8 | 122 | What is a schedule model? | It is an instance or estimation of the schedule | It is the best-case scenario of the schedule | It is the schedule baseline | It is the worst-case scenario of the schedule | 1 | 3b | 2 | a | m3b2a-01
8 | 123 | Which of the following is not a common way to present a schedule? | Bar chart | Network diagram | Activity list | Earned value method | 4 | 3b | 2 | a | m3b2a-02
8 | 124 | Which planning process produces an activity list? | Define activities | Plan schedule management | Develop schedule | Define project scope | 1 | 3b | 2 | a | m3b2a-03
8 | 125 | Which scheduling approach is most used in project management? | Agile methodology | Waterfall methodology | Critical path method | Scrum framework | 3 | 3b | 2 | a | m3b2a-04
8 | 126 | What is the purpose of a schedule baseline in project management? | To create a snapshot of the project’s status | To facilitate comparisons and track deviations from the original plan | To serve as the final project schedule | To determine the project’s critical path | 2 | 3b | 2 | a | m3b2a-05
8 | 127 | What is the purpose of the “Control Thresholds” section in the Schedule Management Plan? | To specify the maximum allowable duration for each project activity | To outline the criteria for selecting a scheduling tool | To describe how the schedule will be monitored and controlled based on variance | To define the process for creating a Work Breakdown Structure (WBS) | 3 | 3b | 2 | a | m3b2a-06
8 | 128 | What is the first planning process in schedule management? | Creating a schedule management plan | Developing an activity list | Assigning resources to the project | Determining activity sequencing | 1 | 3b | 2 | a | m3b2a-07
8 | 129 | Activity ______ provide schedule-related information about each activity, such as predecessors, successors, logical relationships, leads and lags, resource requirements, constraints, imposed dates, and assumptions related to the activity. | features | characteristics | properties | attributes | 4 | 3b | 2 | b | m3b2b-01
8 | 130 | The goal of the Defining Activities Process is to ensure team members have a “complete” understanding of what? | Resource requirements of all activities | Budget allocation to all the activities | All the work they must do as part of the project scope | The project’s overall goal | 3 | 3b | 2 | b | m3b2b-02
8 | 131 | Which element is included in activity attributes to indicate work sequence? | Predecessors and successors | Resource constraints | Budget estimates | Stakeholder preferences | 1 | 3b | 2 | b | m3b2b-03
8 | 132 | What is the purpose of leads and lags in activity attributes? | Documenting activity progress | Identifying resource constraints | Managing stakeholder expectations | Describing time relationships between activities | 4 | 3b | 2 | b | m3b2b-04
8 | 133 | What information should be included in the activity attributes? | Budget allocation | Resource availability | Project assumptions | Team member names | 3 | 3b | 2 | b | m3b2b-05
8 | 134 | Activity list and attributes should be in line with ______. | WBS and WBS dictionary | Stakeholder register | Resource requirements | Assumptions | 1 | 3b | 2 | b | m3b2b-06
8 | 135 | Project teams often create a ______ to ensure that all major activities are accounted for. | Gantt chart | milestone list | project steering committee | checklist | 2 | 3b | 2 | c | m3b2c-01
8 | 136 | A(n) _____ normally does not have any cost or duration. | activity | milestone | critical task | baseline | 2 | 3b | 2 | c | m3b2c-02
8 | 137 | What is the primary purpose of a milestone in a project? | To allocate resources to activities | To mark the beginning of a project phase | To identify necessary or critical activities | To set a strict project schedule | 3 | 3b | 2 | c | m3b2c-03
8 | 138 | Which of the following is not a typical example of a milestone? | Awarding a contract to a supplier | Completing specific products | Documenting project assumptions | Sign-off of key documents | 3 | 3b | 2 | c | m3b2c-04
8 | 139 | What is the purpose of including estimated completion dates for milestones? | To facilitate project monitoring | To align with project constraints | To establish a flexible project timeline | To clarify the project’s overall goal | 1 | 3b | 2 | c | m3b2c-05
8 | 140 | What is the significance of using the SMART framework in sequencing milestones? | To allocate resources effectively | To ensure milestones are attainable | To identify project stakeholders | To define project assumptions | 2 | 3b | 2 | c | m3b2c-06
8 | 141 | What is the primary purpose of sequencing activities in project management? | Allocating resources to activities | Determining project dependencies | Developing the project scope statement | Managing project milestones | 2 | 3b | 2 | d | m3b2d-01
8 | 142 | A project schedule network diagram is an output of the _______ process. | define activities | estimate activity resources | sequence activities | estimate activity durations | 3 | 3b | 2 | d | m3b2d-02
8 | 143 | Which tool is commonly used for sequencing activities along with other scheduling methods like Critical Path Method (CPM)? | Precedence diagramming method (PDM) | WBS dictionary | Gantt chart | Activity network diagram | 1 | 3b | 2 | d | m3b2d-03
8 | 144 | In which type of relationship can two activities have both SS and FF dependencies? | Mandatory relationships | Discretionary relationships | Logical relationships | External relationships | 3 | 3b | 2 | d | m3b2d-04
8 | 145 | Which of the following describes a lead? | The successor activity can start 2 days before the predecessor activity finished | The successor activity can start 2 days after the predecessor activity has finished | The predecessor activity can finish 2 days after the successor activity has started | The predecessor activity can finish only if the successor activity has finished | 1 | 3b | 2 | d | m3b2d-05
8 | 146 | If a construction project requires the inspection activity to be start with the interior finishing work, which precedence relationship should be used? | Start to Start (SS) | Start to Finish (SF) | Finish to Start (FS) | Finish to Finish (FF) | 1 | 3b | 2 | d | m3b2d-06
8 | 147 | Which of the following can be modelled using a finish-to-finish relationship in project sequencing? | Training classes starting after training materials are ready | Concrete pouring starting after excavation is completed | Wiring inspection concurrent with wiring installation | Accounts payable system starting before old system shuts down | 3 | 3b | 2 | d | m3b2d-07
8 | 148 | What is the most common type of dependency between activities? | Finish to Start (FS) | Start to Finish (SF) | Start to Start (SS) | Finish to Finish (FF) | 1 | 3b | 2 | d | m3b2d-08
8 | 149 | You are the project manager for a residential construction project. You have produced a project schedule network diagram and have updated the project documents, including the activity list, activity attributes, assumption log, and milestone list. Which process have you just finished? | The Define Activities process, which identifies all the specific activities of the project | The Sequence Activities process, which identifies all the activity dependencies | The Develop Schedule process, which diagrams project network time estimates | The Estimate Activity Durations process, which estimates activity durations | 2 | 3b | 2 | d | m3b2d-09
8 | 150 | In the context of a network diagram, a ______ is simply the starting and ending point of an activity. | cell | vertex | source | node | 4 | 3b | 2 | e | m3b2e-01
8 | 151 | What is a network diagram in project management? | A visual representation of project stakeholders | A schematic display of project funding sources | A graphical representation of logical relationships among project activities | A chart showing project risk assessments | 3 | 3b | 2 | e | m3b2e-02
8 | 152 | Which method of network diagramming only shows finish-to-start dependencies? | Activity on Arrow (AOA) | Precedence Diagramming Method (PDM) | Finish-to-Finish (FF) Method | Start-to-Start (SS) Method | 1 | 3b | 2 | e | m3b2e-03
8 | 153 | What type of relationships can be represented using the Precedence Diagramming Method (PDM)? | Finish-to-Start (FS) only | Start-to-Finish (SF) only | Finish-to-Finish (FF) only | All the options | 4 | 3b | 2 | e | m3b2e-04
8 | 154 | Which network diagramming method is more comprehensive in terms of activity information? | Activity on Arrow (ADM) | Precedence Diagramming Method (PDM) | Critical Path Method (CPM) | Gantt Chart | 2 | 3b | 2 | e | m3b2e-05
8 | 155 | Which software tool is commonly used to create Precedence Diagramming Method (PDM) diagrams? | Microsoft Excel | Microsoft Word | Microsoft Project | Microsoft PowerPoint | 3 | 3b | 2 | e | m3b2e-06
8 | 156 | In the Precedence Diagramming Method (PDM), which information is typically included in the activity attributes? | Duration and start date | Logical relationship only | Finish-to-Start dependencies | Only the assigned resources | 1 | 3b | 2 | e | m3b2e-07
8 | 157 | If you have only two paths through a project network diagram where path 1 has a length of 20 weeks and path 2 has a length of 30 weeks, what is the estimated duration of the project? | 20 weeks | 25 weeks | 30 weeks | There is not enough information to answer | 3 | 3b | 2 | e | m3b2e-08
8 | 158 | Duration estimates are provided as a ____ number, such as four weeks; as a range, such as three to five weeks; or as a three-point estimate. | continuous | random | fractional | discrete | 4 | 3b | 2 | f | m3b2f-01
8 | 159 | Which technique involves using historical data from a similar activity or project to estimate duration? | Expert judgment | Analogous estimating | Three-point estimating | Parametric estimating | 2 | 3b | 2 | f | m3b2f-02
8 | 160 | What is one of the primary purposes of the Program Evaluation and Review Technique (PERT)? | To estimate labor costs | To sequence activities | To estimate project duration with uncertainty | To create a network diagram | 3 | 3b | 2 | f | m3b2f-03
8 | 161 | How is the PERT estimate calculated using the optimistic, most likely, and pessimistic estimates? | (Optimistic + Most Likely + Pessimistic) / 3 | (Optimistic + Most Likely + Pessimistic) / 2 | (Optimistic + 4 * Most Likely + Pessimistic) / 6 | (Optimistic + 2 * Most Likely + Pessimistic) / 4 | 3 | 3b | 2 | f | m3b2f-04
8 | 162 | In a three-point estimate, what does the “most likely” value represent? | The most optimistic estimate | The median estimate | The most probable to occur under normal conditions | The least likely estimate | 3 | 3b | 2 | f | m3b2f-05
8 | 163 | What is the PERT weighted average based on an optimistic estimate of six days, a most likely estimate of eight days, and a pessimistic time of sixteen days? | six | nine | eight | ten | 2 | 3b | 2 | f | m3b2f-06
8 | 164 | Which cost estimating technique would you be using if you estimate the cost of materials based on the floor area in square meters? | Top-down | Bottom-up | Analogous | Parametric Modeling | 4 | 3b | 2 | f | m3b2f-07
8 | 165 | What technique involves estimating duration based on an algorithm using project parameters or historical data? | Expert judgment | Parametric estimating | Analogous estimating | Three-point estimating | 2 | 3b | 2 | f | m3b2f-08
8 | 166 | What is the main advantage of using a Monte Carlo simulation for project scheduling? | It offers a comprehensive analysis of different activity durations, considering variability and interdependencies. | It is straightforward to implement and relies on limited input data. | It effectively incorporates a range of probabilities and uncertainties, modeling potential variations in the project timeline. | It facilitates direct computation of Program Evaluation and Review Technique (PERT) estimates, including optimistic, pessimistic, and most likely durations. | 3 | 3b | 2 | f | m3b2f-09
8 | 167 | Which number should be smallest when creating a three-point estimate for an activity duration? | Worst credible estimate | Pessimistic estimate | Most likely estimate | Optimistic estimate | 4 | 3b | 2 | f | m3b2f-010
8 | 168 | What is the primary objective of the schedule development process in project management? | To create a Gantt chart | To establish start and end dates for activities and the overall project | To optimize resource allocation | To determine project milestones | 2 | 3b | 2 | g | m3b2g-01
8 | 169 | Which diagramming technique is frequently used to represent project schedules? | PERT chart | Decision tree | Gantt chart | Fishbone diagram | 3 | 3b | 2 | g | m3b2g-02
8 | 170 | What is the main advantage of using a Gantt chart for schedule management? | It offers a standardized framework for displaying detailed resource allocation and timelines. | It supports flexible, agile planning methodologies. | It presents a clear, calendar-style visualization of project activities along with their respective start and finish dates. | It enables automatic computation and visualization of the critical path in project activities. | 3 | 3b | 2 | g | m3b2g-03
8 | 171 | Under what circumstances is the Linear Scheduling Method (LSM) more advantageous compared to Gantt charts? | When dealing with software development projects requiring iterative and flexible planning. | When managing linear construction projects where activities need to be coordinated along a physical path. | When conducting detailed critical path analysis for complex projects with numerous interdependent activities. | When systematically monitoring and addressing potential project risks in megaprojects. | 2 | 3b | 2 | g | m3b2g-04
8 | 172 | What does the schedule baseline serve as for a project? | A visual representation of project tasks | A foundation for monitoring project progress | A tool for resource optimization | A method for risk analysis | 2 | 3b | 2 | g | m3b2g-05
8 | 173 | What is the significance of resource calendars in project scheduling? | It helps create Gantt charts | It provides a basis for estimating project duration | It defines the project's critical path | It assists in managing resource availability and constraints | 4 | 3b | 2 | g | m3b2g-06
8 | 174 | When managing a construction project, why is it crucial for the project manager to coordinate and analyze subcontractors' schedules alongside the overall project schedule? | To ensure compliance with environmental regulations and legal requirements. | To optimize the use of building materials and reduce waste. | To prevent conflicts and safety issues due to concurrent work in the same area. | To facilitate regular stakeholder communication and updates. | 3 | 3b | 2 | g | m3b2g-07
8 | 175 | What is the purpose of understanding the critical path in project management? | To identify the easiest tasks | To highlight activities requiring close monitoring | To determine the shortest path in the network | To allocate resources efficiently | 2 | 3b | 2 | h | m3b2h-01
8 | 176 | Slack or ____ is the amount of time an activity may be delayed without delaying a succeeding activity or the project finish date. | margin | float | redundancy | space | 2 | 3b | 2 | h | m3b2h-02
8 | 177 | How is the critical path defined? | The shortest path in the network diagram | The path with the maximum amount of float | The path with the minimum amount of slack | The longest path within the network diagram | 4 | 3b | 2 | h | m3b2h-03
8 | 178 | What is the significance of float or slack in project scheduling? | It shows the amount of time a task can be delayed. | It indicates the flexibility of a task’s deadline. | It determines the critical path in the project. | It reflects the total project duration. | 1 | 3b | 2 | h | m3b2h-04
8 | 179 | How does a delay in activities specifically located on the critical path impact overall project scheduling? | It necessitates a reevaluation of non-critical activities to maintain the original project finish date. | It results in an automatic reduction of the critical path length due to the compression of remaining tasks. | It typically leads to an extension of the project's finish date, as these activities directly influence the project duration. | It increases the total float across the project, offering more flexibility in the scheduling of other tasks. | 3 | 3b | 2 | h | m3b2h-05
8 | 180 | How is total float calculated for a schedule activity? | Early finish minus early start | Late finish minus early finish | Late start minus early finish | Early start minus late start | 2 | 3b | 2 | h | m3b2h-06
8 | 181 | How does the concept of free float differ from total float in project scheduling, and what does it specifically indicate? | Free float measures the time an activity can be delayed without affecting the project's finish date, while total float pertains to individual task flexibility. | Free float refers to the amount of time an activity can be delayed without affecting early start dates of any successor, unlike total float which impacts the project's finish date. | Total float is the time a project can be delayed without cost overruns, whereas free float represents the leeway in starting a new activity. | Total float is the delay allowed in an activity without impacting its immediate successors, while free float affects the entire project schedule. | 2 | 3b | 2 | h | m3b2h-07
8 | 182 | Why do activities on the critical path usually have zero free float? | Because they are the most time-consuming tasks | Because they have the least number of resources allocated | Because they have limited flexibility and no room for delays | Because they are the most critical tasks in the project | 3 | 3b | 2 | h | m3b2h-08
8 | 183 | What does the total float measure in project scheduling? | The amount of time a task can be delayed without affecting the early start of any successor | The total duration of the project | The flexibility of the project finish date | The amount of time a task can be delayed without affecting the project finish date | 4 | 3b | 2 | h | m3b2h-09
8 | 184 | What is the main challenge in compressing a project schedule by reducing the project scope? | Increased coordination challenges | Risk of burnout among resources | Potential clashes between activities | Scope already agreed upon in the contract | 4 | 3b | 2 | i | m3b2i-01
8 | 185 | Which project schedule compression approach involves overlapping activities that would preferably be done sequentially? | Resource allocation | Task reassignment | Crashing | Fast-tracking | 4 | 3b | 2 | i | m3b2i-02
8 | 186 | What is the primary downside of fast-tracking as a schedule compression strategy? | Increased resource allocation | Greater likelihood of quality issues | Higher project budget | More coordination challenges and clashes | 4 | 3b | 2 | i | m3b2i-03
8 | 187 | Which document in the project management plan should identify the management and stakeholder who have the authority to approve crashing and fast-tracking? | Detailed cost breakdown | Stakeholder communication plan | Schedule management plan | Risk mitigation strategy | 3 | 3b | 2 | i | m3b2i-04
8 | 188 | Which of the following is an essential information to allow a project manager to make schedule trade-off decisions? | Critical path | Project stakeholder list | WBS | Risk register | 1 | 3b | 2 | i | m3b2i-05
8 | 189 | What distinguishes the critical chain approach from the traditional critical path method? | Focus on task sequence | Emphasis on resource availability and time | Allocation of physical resources | Prioritization of multitasking | 2 | 3b | 2 | j | m3b2j-01
8 | 190 | Feeder buffers and the project buffer are part of which of the following Develop Schedule tool and technique? | Critical path method | Schedule network analysis | Applying leads and lags | Critical chain method | 4 | 3b | 2 | j | m3b2j-02
8 | 191 | What is the primary purpose of a project buffer in Critical Chain Method? | To ensure the availability of critical resources at key stages of the project. | To provide additional time at the end of the critical chain to protect the project's completion date. | To absorb delays from non-critical paths before they impact the critical chain. | To optimize the allocation of resources across various project tasks. | 2 | 3b | 2 | j | m3b2j-03
8 | 192 | In Critical Chain Project Management, what role does a feeder buffer play? | It is a reserve of extra materials and personnel allocated to critical tasks. | It provides additional time to non-critical tasks feeding into the critical chain. | It is added at the end of the project to ensure on-time completion. | It represents a financial contingency for unforeseen project expenses. | 2 | 3b | 2 | j | m3b2j-04
8 | 193 | How does a resource buffer differ from a project buffer in Critical Chain Project Management? | A resource buffer is a time reserve added to the end of the project, while a project buffer is for resource allocation. | A resource buffer ensures the availability of key resources at critical points, unlike a project buffer which is a time reserve. | Both buffers serve the same purpose but at different stages of the project. | A resource buffer is used only in software projects, while a project buffer is used in construction projects. | 2 | 3b | 2 | j | m3b2j-05
8 | 194 | Critical chain scheduling considers limited resources when creating a project schedule and includes ______ to protect the project completion date. | reserves | multitasking | outsource | buffers | 4 | 3b | 2 | j | m3b2j-06
10 | 195 | Which of the following are the three main cost management processes during the planning phase? | Develop Budget, Estimate Costs, Monitor Costs | Plan Cost Management, Estimate Costs, Determine Budget | Control Costs, Budget Planning, Cost Estimation | Calculate Costs, Forecast Budget, Expense Monitoring | 2 | 3b | 3 | a | m3b3a-01
10 | 196 | Cost ____ involves allocating the overall cost estimate to individual tasks over time to establish a baseline for measuring performance. | estimating | account | allowance | budgeting | 4 | 3b | 3 | a | m3b3a-02
10 | 197 | A cost baseline is a(n) ____ budget that project managers use to measure and monitor cost performance. | incidental | basic | time-phased | incremental | 3 | 3b | 3 | a | m3b3a-03
10 | 198 | Which approach should be taken while formulating a comprehensive cost management plan? | Rely solely on expert judgment | Consult stakeholders, analyze data, and engage experts | Base decisions on personal experience | Delegate planning to the project manager | 2 | 3b | 3 | a | m3b3a-04
10 | 199 | What are some key outputs of the cost management processes? | Project charter and risk management plan | Cost management plan and project funding requirements | Earned value management and constructability analysis | Inflation assumptions and currency fluctuations | 2 | 3b | 3 | a | m3b3a-05
10 | 200 | In cost management planning within the construction industry, what is the role and composition of a Bill of Quantities (BQ)? | A BQ is a financial document that outlines the overall budget of the project, including labor, materials, and overhead costs. | A BQ is a detailed list that includes the measured quantities of each element of work identified in the construction drawings and specifications. | A BQ is a contractual agreement that specifies the timelines for project completion, including penalties for delays. | A BQ is a project management plan that outlines the schedule and sequence of construction activities. | 2 | 3b | 3 | a | m3b3a-06
10 | 201 | In project management, how do cost management, life cycle costing, value engineering, and constructability analysis collectively contribute to project success? | They focus solely on reducing the project's upfront costs without considering long-term performance or quality. | These tools work together to minimize expenses and time requirements, enhance project quality and performance, maximize design-to-cost efficiency, and streamline the decision-making process. | They prioritize environmental sustainability over cost efficiency and project timelines. | Each tool operates independently, focusing on different phases of the project lifecycle without overlapping in objectives or benefits. | 2 | 3b | 3 | a | m3b3a-07
10 | 202 | Which component of cost estimation is crucial to understanding the factors considered during the estimation process? | Budget allocation | Basis of estimates | Cost of quality | Labor allocation | 2 | 3b | 3 | b | m3b3b-01
10 | 203 | What is the focus of the parametric estimating technique in cost estimation? | Using expert judgement for estimation | Collecting optimistic and pessimistic estimates | Applying mathematical algorithms to calculate costs | Breaking down the project into work packages | 3 | 3b | 3 | b | m3b3b-02
10 | 204 | How does the implementation of a quality management plan affect the cost estimates in a project? | It increases the overall project cost due to the high expense of implementing quality standards. | The plan primarily impacts the project timeline, with minimal effect on cost estimates. | It contributes to cost estimates by reducing rework and defects, accounting for the cost of quality, guiding supplier selection, fostering quality improvement initiatives, and managing quality-related risks. | It focuses solely on the technical aspects of project execution, leaving cost estimates unaffected. | 3 | 3b | 3 | b | m3b3b-03
10 | 205 | Considering its feasibility and effectiveness, why is the bottom-up cost estimation approach particularly beneficial for small-scale projects? | It capitalizes on the use of generalized statistical models suitable for various project sizes. | It provides precise and detailed cost estimates, which is more manageable and realistic in the scope of smaller projects. | It depends heavily on extensive design details, typically available in smaller projects. | Its efficiency and time-saving aspects are more pronounced in smaller projects compared to larger ones. | 2 | 3b | 3 | b | m3b3b-04
10 | 206 | You have received the following estimates for a complex activity that is critical to the success of your project. The three-point estimates are as follows: The most likely estimate is $42, the optimistic estimate is $35, and the pessimistic estimate is $54. What is the expected activity cost of this activity using the PERT formula (rounded to the nearest dollar)? | 49 | 39 | 43 | 44 | 3 | 3b | 3 | b | m3b3b-05
10 | 207 | Your project sponsor has requested a cost estimate for the project. She would like the cost estimate to be as accurate as possible because this might be her one and only chance to secure a budget for this project because of recent cuts in special projects. You decide to use _________. | Analogous estimating techniques | Bottom-up estimating techniques | Top-down estimating techniques | Expert judgment techniques | 2 | 3b | 3 | b | m3b3b-06
10 | 208 | What is the primary output of the “determine budget” process in project cost management? | Cost Baseline | Project Document Updates | Project Funding Requirements | Control accounts | 1 | 3b | 3 | c | m3b3c-01
10 | 209 | What is the main purpose of a contingency reserve in a project budget? | To cover unexpected risks and uncertainties | To allocate funds for specific deliverables | To address funding requirements | To monitor expenditure | 1 | 3b | 3 | c | m3b3c-02
10 | 210 | Which of the following is displayed as an S-curve? | Funding requirements | Cost baseline | Cost estimates | Expenditures to date | 2 | 3b | 3 | c | m3b3c-03
10 | 211 | What is the purpose of a management reserve in a project budget? | Cover unexpected risks | Account for inflation | Fund project management expenses | Provide flexibility for unforeseen changes | 4 | 3b | 3 | c | m3b3c-04
10 | 212 | What is the primary objective of including a contingency reserve in a project's budget? | To fund routine administrative and operational costs throughout the project lifecycle. | To provide a financial safeguard against unexpected events, changes, or risks encountered during the project. | To facilitate the regular monitoring and reporting of the project's financial outlay. | To earmark budgetary provisions exclusively for designated work packages within the project. | 2 | 3b | 3 | c | m3b3c-05
12 | 213 | Which aspect of project management focuses on guaranteeing that the project fulfills both the explicit and implicit requirements set forth at its inception? | Integration management, which coordinates all project elements to work together effectively. | Quality management, which is dedicated to maintaining the standards and satisfaction criteria throughout the project lifecycle. | Portfolio management, which aligns the project with strategic organizational objectives. | Performance management, which monitors and measures the project's progress and outcomes. | 2 | 3c | 2 | 0 | m3c20-01
12 | 214 | What is the fundamental focus of quality in project management? | Adhering strictly to the customer’s scheduled timelines. | Keeping to customer’s financial constraints set for the project. | Ensuring alignment with customer expectations and project specifications. | Fostering extensive engagement and satisfaction among stakeholders. | 3 | 3c | 2 | 0 | m3c20-02
12 | 215 | According to ISO 9000:2015, how is quality defined? | The extent to which a product meets design specifications | The degree to which inherent characteristics fulfill requirements | The level of customer satisfaction achieved | The overall efficiency of project processes | 2 | 3c | 2 | 0 | m3c20-03
12 | 216 | What is the main purpose of continuous improvement in project management? | Reducing project scope to streamline execution | Minimizing project risks through strict control | Enhancing project performance and effectiveness | Maximizing customer satisfaction through frequent updates | 3 | 3c | 2 | 0 | m3c20-04
12 | 217 | The term "Fitness for Use" in quality management primarily refers to which aspect of a product or service? | The cost-effectiveness and budget alignment of the product or service. | The extent to which the product or service adheres to its intended purpose and satisfies user needs. | The time efficiency in the production or delivery of the product or service. | The degree to which the product or service involves stakeholder engagement during development. | 2 | 3c | 2 | 0 | m3c20-05
12 | 218 | What is the main distinction between quality assurance and quality control? | Quality assurance is proactive, while quality control is reactive | Quality assurance focuses on project scope, while quality control focuses on cost | Quality assurance addresses defects, while quality control focuses on prevention | Quality assurance is performed by external auditors, while quality control is internal | 1 | 3c | 2 | 0 | m3c20-06
12 | 219 | Which of the following is a typical example of quality metrics? | The total revenue generated from a new product line. | The percentage of failure rates of products. | The number of employees involved in the production process. | The duration of the product development cycle. | 2 | 3c | 2 | 0 | m3c20-07
12 | 220 | Which of the following is a key component of the quality management plan? | Defining project milestones and deliverables | Identifying project resource allocation | Outlining stakeholder communication strategy | Outlining acceptance criteria for project deliverables and product performance standards and metrics | 4 | 3c | 2 | 0 | m3c20-08
12 | 221 | Which of the following options correctly lists a set of the Seven Principles of Quality Management? | Market Analysis, Financial Planning, Risk Management, Stakeholder Satisfaction, Resource Allocation, Data Security, and Globalization. | Customer Focus, Leadership, Engagement of People, Process Approach, Improvement, Evidence-Based Decision Making, and Relationship Management. | Product Innovation, Competitive Strategy, Human Resource Management, Operational Efficiency, Brand Positioning, Legal Compliance, and Corporate Social Responsibility. | Cost Efficiency, Team Building, Supply Chain Optimization, Technological Advancement, Business Continuity, Market Expansion, and Corporate Governance. | 2 | 3c | 2 | 0 | m3c20-09
15 | 222 | What is the primary goal of project resource management planning? | To develop a detailed project schedule | To identify project risks and mitigation strategies | To allocate financial resources for the project | To develop a comprehensive strategy to acquire and manage project resources effectively | 4 | 3c | 3 | a | m3c3a-01
15 | 223 | What is the primary objective of a team management plan in the context of project resource management? | To outline the financial budget allocated for team training and development. | To detail the project’s scope and deliverables with input from all team members. | To define roles and responsibilities, team development, and management strategies for the project team. | To specify the technical specifications and quality standards of project deliverables. | 3 | 3c | 3 | a | m3c3a-02
15 | 224 | In a RACI chart, each task may have multiple ____ entries. | R, C, or I | A, R, or I | A, C, or R | A, C, or I | 1 | 3c | 3 | a | m3c3a-03
15 | 225 | Which resource management tool provides insights into resource demand over time for each type of resource? | Responsibility assignment matrix | RACI chart | Resource histogram | Organizational chart | 3 | 3c | 3 | a | m3c3a-04
15 | 226 | What is the main purpose of resource leveling in project management? | To extend the project schedule | To ensure resource overloads are minimized | To prioritize project activities | To increase the number of available resources | 2 | 3c | 3 | a | m3c3a-05
15 | 227 | What does a resource histogram help project managers visualize? | Project milestones and deliverables | Stakeholder engagement levels | Resource demand and availability | Financial expenditures for project resources | 3 | 3c | 3 | a | m3c3a-06
15 | 228 | A RACI chart is a type of _____. | responsibility assignment matrix | project organizational chart | resource histogram | project dashboard | 1 | 3c | 3 | a | m3c3a-07
15 | 229 | A ______ describes when and how people will be added to and taken off a project. | project organizational chart | resource histogram | responsibility assignment matrix | staffing management plan | 4 | 3c | 3 | a | m3c3a-08
15 | 230 | On a RACI chart, which role and responsibility should only appear once for a task? | R | A | C | I | 2 | 3c | 3 | a | m3c3a-09
15 | 231 | What does the resource smoothing technique aim to achieve? | Minimize resource overloads while extending the schedule. | Balance resource allocation without affecting the project timeline. | Focus on assigning tasks directly to individuals. | Prioritize tasks and resources based on project dependencies. | 2 | 3c | 3 | a | m3c3a-010
15 | 232 | A(n) ____ histogram is a column chart that shows the number of resources required for or assigned to a project over time. | resource | requirements | allocation | assignment | 1 | 3c | 3 | a | m3c3a-011
15 | 233 | A project ____ chart is a graphic representation of how authority and responsibility is distributed within the project. | organizational | planning | stakeholder | management | 1 | 3c | 3 | a | m3c3a-012
15 | 234 | A _____ is a document created when planning resource management to help promote teamwork and clarify team communications. | team charter | team communications plan | teamwork plan | communications management plan | 1 | 3c | 3 | a | m3c3a-013
15 | 235 | Which process is closely linked to estimating activity resources in project management? | Define quality | Scope verification | Risk identification | Estimating activity durations and costs | 4 | 3c | 3 | b | m3c3b-01
15 | 236 | Why is it important to regularly update resource estimates throughout a project? | To increase project complexity | To ensure resource availability aligns with project needs | To maintain project scope | To expedite project closure | 2 | 3c | 3 | b | m3c3b-02
15 | 237 | In the process of estimating activity resources, which key output delivers a detailed, hierarchical representation of resources, categorized by type, and need? | The Work Breakdown Structure (WBS), which outlines all project deliverables and work components. | The Resource Breakdown Structure (RBS), which organizes resources by categories and hierarchies. | The Project Charter, which defines the initial scope, objectives, and stakeholders of the project. | The Risk Register, which identifies and assesses potential risks and their impact on project resources. | 2 | 3c | 3 | b | m3c3b-03
15 | 238 | Which of the following is not an input of the estimate activity resources process? | Project schedule | Resource management plan | Cost estimates | Activity attributes | 1 | 3c | 3 | b | m3c3b-04
15 | 239 | Which of the following elements are typically included to comprehensively detail the resource requirements of an activity? | The Work Breakdown Structure (WBS), activity name, resource type, resource name, quantity required, grade or qualification of resources, their availability, and the associated cost. | The Project Charter details, stakeholder list, resource type, resource name, quantity, project timeline, and overall project cost. | The Risk Register entries, activity duration, resource type, resource name, resource cost, project phase, and stakeholder engagement levels. | The quality requirements, resource type, resource grade or qualification, availability, cost, activity name, and resource utilization rate. | 1 | 3c | 3 | b | m3c3b-05
18 | 240 | What is the key output of the Plan Communications Management process? | Communications allocation and resource plan | Communications management plan | Communications matrix | Communications risk assessment report | 2 | 3c | 4 | 0 | m3c40-01
18 | 241 | What is a primary communications management challenge in the construction industry? | Lack of skilled workers | Complex regulatory environment | Short-term collaboration with multiple stakeholders | Excessive project funding | 3 | 3c | 4 | 0 | m3c40-02
18 | 242 | What is the primary purpose of a communications management plan? | To guide effective project communications | To guide effective selection of communications channels | To define communications needs | To assess project risks arising from communications | 1 | 3c | 4 | 0 | m3c40-03
18 | 243 | Project ____ management involves generating, collecting, disseminating, and storing project information. | information | communications | resources | risk | 2 | 3c | 4 | 0 | m3c40-04
18 | 244 | What is the primary purpose of project dashboards? | Managing project finances | Documenting project decisions | Assigning tasks to team members | Providing a centralized and visual representation of key project information | 4 | 3c | 4 | 0 | m3c40-05
18 | 245 | Which software tools are commonly used to develop in-house project dashboards? | PowerPoint and Excel | Word and Outlook | Photoshop and Illustrator | Power BI and Tableau | 4 | 3c | 4 | 0 | m3c40-06
18 | 246 | Why might the specialized terminology in the construction industry hinder effective communication? | It makes communication more formal. | It creates communication barriers. | It fosters collaboration among team members. | It improves clarity of messages. | 2 | 3c | 4 | 0 | m3c40-07
18 | 247 | Achieving an average course evaluation of at least 3.0 on a 5.0 scale is an example of a ________. | requirement | dashboard | Key Performance Indicator | outcome | 3 | 3c | 4 | 0 | m3c40-08
18 | 248 | Many projects ______ use red, yellow, and green to indicate the status of each metric. | control charts | dashboards | control panels | risk register | 2 | 3c | 4 | 0 | m3c40-09
18 | 249 | What section of a communications management plan describes how issues should be handled? | issue log | revision procedures | escalation procedures | arbitration procedures | 3 | 3c | 4 | 0 | m3c40-010
28 | 250 | The Power/Interest Grid categorizes stakeholders based on their ______. | communication preferences | geographic location | power and level of interest | budget allocation | 3 | 3c | 5 | 0 | m3c50-01
28 | 251 | Which stakeholder usually has less power and interest in a residential construction project? | Office chair supplier | National Environment Agency | Client or Developer | Mechanical engineer for lift system | 1 | 3c | 5 | 0 | m3c50-02
28 | 252 | What is the primary advantage of customizing communication strategies to suit different stakeholders in a project? | Guaranteeing adherence to legal and regulatory standards. | Effectively managing and aligning stakeholder expectations with project goals. | Completely mitigating all risks associated with the project. | Streamlining the distribution and utilization of project resources. | 2 | 3c | 5 | 0 | m3c50-03
28 | 253 | What is the purpose of evaluating engagement activities in the Stakeholder Engagement Plan? | Identifying project risks | Assessing regulatory compliance | Monitoring project timelines | Improving future engagement strategies | 4 | 3c | 5 | 0 | m3c50-04
28 | 254 | What does the “unaware stakeholder” category refer to? | Stakeholders with low interest in the project | Stakeholders with low power and high interest | Stakeholders with low power and low interest | Stakeholders with little knowledge about the project | 4 | 3c | 5 | 0 | m3c50-05
28 | 255 | In what way should stakeholder engagement strategies be adapted to effectively address varying stakeholder attitudes towards a project? | By increasing the budget and resources allocated to stakeholder-related activities. | By evaluating and aligning with stakeholder-specific regulatory and compliance requirements. | By customizing communication and involvement tactics to either mobilize support or mitigate opposition from stakeholders. | By modifying the project's timelines to accommodate the preferences and expectations of different stakeholders. | 3 | 3c | 5 | 0 | m3c50-06
28 | 256 | In project management, stakeholders can be categorized based on their awareness and attitude towards a project. Which of the following correctly matches the stakeholder category with its description? | Unaware: Stakeholders who are aware of the project and actively contribute to its success. | Resistant: Stakeholders who are aware of the project and support the changes it brings. | Neutral: Stakeholders who know about the project but are indifferent to its outcomes. | Supportive: Stakeholders who are unaware of the project and its potential impacts on them. | 3 | 3c | 5 | 0 | m3c50-07
28 | 257 | You are in the process of analyzing and visually representing your stakeholders. Which of the following is false? | The salience model is useful for displaying stakeholder analysis for small projects or straightforward stakeholder interactions. | Data analysis includes stakeholder analysis and document analysis techniques. | A power/interest grid displays stakeholder information in a quadrant format to display whether the stakeholder is a key player or is one who needs only periodic updates. | Salience models are displayed as Venn diagrams. | 1 | 3c | 5 | 0 | m3c50-08
21 | 258 | What is a risk register in project risk management? | A document that summarizes project objectives | A tool used to analyze project costs | A comprehensive table of identified risks and proposed actions | A report on project stakeholders’ opinions | 3 | 3d | 2 | b | m3d2b-01
21 | 259 | What is the primary purpose of a project risk report? | To summarize project milestones | To communicate overall project risks to stakeholders | To outline project budget estimates | To describe project resource allocation | 2 | 3d | 2 | b | m3d2b-02
21 | 260 | Which analysis technique involves a comprehensive evaluation of four internal and external categories that could impact the project? | Brainstorming | Checklists | SWOT analysis | Document analysis | 3 | 3d | 2 | b | m3d2b-03
21 | 261 | What is the purpose of a Risk Breakdown Structure? | To assign resources to project tasks | To identify and categorize risks | To track project milestones | To analyze project budgets | 2 | 3d | 2 | b | m3d2b-04
21 | 262 | Which external factor category does the PESTLE acronym not cover? | Political | Economic | Social | Project | 4 | 3d | 2 | b | m3d2b-05
21 | 263 | What is the purpose of identifying triggers in a risk register? | To rank risks based on severity | To assign risk owners | To indicate potential response actions | To signal the occurrence of risk events | 4 | 3d | 2 | b | m3d2b-06
21 | 264 | What information should a project risk report include about individual risks? | Only risk description and owner | Only probability and impact | Only risk response strategies | Probability, impact, description, and owner | 4 | 3d | 2 | b | m3d2b-07
21 | 265 | Which technique is used to visualize the decision-making process and its potential outcomes in quantitative risk analysis? | Sensitivity analysis | Monte Carlo analysis | Decision tree analysis | Simulation analysis | 3 | 3d | 2 | d | m3d2d-01
21 | 266 | What is the main objective of using simulation techniques, like Monte Carlo, in quantitative risk analysis within project management? | To precisely predict the exact date and cost at which the project will be completed. | To identify and eliminate all potential risks in the project. | To assess the combined impact of various risks on project objectives, providing a range of possible outcomes and their probabilities. | To develop a detailed project plan that outlines every step in the project execution. | 3 | 3d | 2 | d | m3d2d-02
21 | 267 | In the context of quantitative risk analysis, what is the primary focus of sensitivity analysis? | Evaluating the constraints and limitations inherent in the project. | Determining how variations in different project variables can influence the overall project outcomes. | Assessing the likelihood of occurrence for individual risks within the project. | Analyzing past project data to predict future project performance. | 2 | 3d | 2 | d | m3d2d-03
21 | 268 | What are the inputs to perform quantitative risk analysis? | Assumption log, cost forecasts, organizational process assets | Project management plan, enterprise environmental factors, risk report | Project documents, expert judgment, decision tree analysis | Risk management plan, sensitivity analysis, project history | 2 | 3d | 2 | d | m3d2d-04
21 | 269 | What is the purpose of the "Plan Risk Responses" process in project management? | Assigning project tasks to team members | Identifying project stakeholders | Developing strategies to address project risks | Creating a project schedule | 3 | 3d | 2 | e | m3d2e-01
21 | 270 | What is the purpose of a probability/impact matrix in during Plan Risk Responses? | To identify project stakeholders | To allocate project resources | To guide selection of risk responses | To define project milestones | 3 | 3d | 2 | e | m3d2e-02
21 | 271 | In the probability/impact matrix, risks in the "no-go zone" can be described as which of the following? | Risks that are acceptable without intervention | Risks that require interventions before proceeding | Risks that should be exploited | Risks that are tolerable with monitoring | 2 | 3d | 2 | e | m3d2e-03
21 | 272 | What does the "Avoid" risk response strategy involve? | Eliminating or terminating the risk | Decreasing the probability of a risk | Transferring responsibility to another party | Accepting the risk without taking actions | 1 | 3d | 2 | e | m3d2e-04
21 | 273 | Which risk response strategy involves transferring the responsibility of managing a risk to another party? | Escalate | Share | Exploit | Mitigate | 2 | 3d | 2 | e | m3d2e-05
21 | 274 | What is the purpose of contingency reserves in project risk management? | To allocate buffer time for project tasks | To set aside funds for unknown risks | To determine project milestones | To allocate extra budget for known risks | 4 | 3d | 2 | e | m3d2e-06
21 | 275 | What is the purpose of a fallback plan, and when is it typically utilized? | A fallback plan is a preliminary strategy used to prevent project risks and is implemented at the beginning of the project. | Fallback plans are developed for high-impact risks and are activated if initial risk mitigation efforts are unsuccessful. | A fallback plan is used to manage financial risks exclusively and involves securing additional funding if the initial budget is insufficient. | Fallback plans are long-term strategies that are implemented after project completion to address any post-project issues. | 2 | 3d | 2 | e | m3d2e-07
21 | 276 | Which strategy involves actively taking steps to ensure that a positive risk or opportunity is realized? | Exploit | Mitigate | Avoid | Escalate | 1 | 3d | 2 | e | m3d2e-08
21 | 277 | Which strategy involves increasing the probability or impact of a risk? | Accept | Share | Exploit | Enhance | 4 | 3d | 2 | e | m3d2e-09
21 | 278 | Your supplier left you a voicemail saying that a hurricane in China will prevent your materials from arriving on time. You identified a risk response strategy for this risk and have arranged for a local company to lease you the needed equipment until yours arrives. This is an example of which risk response strategy? | Transfer | Acceptance | Mitigate | Avoid | 3 | 3d | 2 | e | m3d2e-010
21 | 279 | What is the purpose of contingency plans in project risk management? | To eliminate all risks | To address known risks if they occur | To transfer risks to other parties | To exploit positive risks | 2 | 3d | 2 | e | m3d2e-011
21 | 280 | Risk ______ is a response strategy for a positive risk where you do whatever you can to make sure the positive risk happens. | sharing | enhancement | exploitation | acceptance | 3 | 3d | 2 | e | m3d2e-012
21 | 281 | You decide to take out an insurance policy in case a risky event occurs. What risk response strategy are you using? | Risk transference | Risk mitigation | Risk avoidance | Escalation of the risk | 1 | 3d | 2 | e | m3d2e-013
24 | 282 | In the case of the reconstruction project for the I-35W Mississippi River Bridge Collapse, what procurement practice motivated the early completion of the project? | Recognition from the project manager | Incentive fees and financial rewards | Legal obligations | Public recognition and media coverage | 2 | 3d | 3 | a | m3d3a-01
24 | 283 | What important aspect of procurement does the procurement management plan document? | Project scope | Supplier relationships | Guidelines for managing procurement processes | Project milestones | 3 | 3d | 3 | a | m3d3a-02
24 | 284 | What distinguishes EPC (Engineering, Procurement, and Construction) contracts from EPCM (Engineering, Procurement, and Construction Management) contracts in terms of project management and execution? | In an EPC contract, the project owner is responsible for the construction or installation, whereas in an EPCM contract, the EPCM contractor supervises the construction. | EPC contracts assign complete project responsibility to a single contractor, while EPCM contracts involve the project owner playing a more active role in overseeing various contractors through an EPCM contractor. | Under an EPC contract, a single contractor is responsible for the entire construction or installation, while in an EPCM contract, the EPCM contractor is responsible for selecting and supervising different contractors. | In EPC contracts, different contractors are selected for engineering, procurement, and construction, whereas in EPCM contracts, a single contractor manages all these phases. | 3 | 3d | 3 | a | m3d3a-03
24 | 285 | What is the primary purpose of the "Procurement Constraints" section in the procurement management plan? | To highlight any project constraints which must be considered as part of the procurement management process. | To define the number of available procurement staff, which may constrain the procurement management process. | To highlight the procurement risks that may impact the procurement management process. | To describe the availability of technical experts, which may constrain the procurement management process. | 3 | 3d | 3 | a | m3d3a-04
24 | 286 | You want to lower the risk arising from a contract to purchase goods and services from a supplier. As the buyer, what type of contract should you use? | fixed price | unit price | cost reimbursable | time and materials | 1 | 3d | 3 | a | m3d3a-05
24 | 287 | In the procurement process, a Request for ______ is a formal document issued by a company to invite suppliers to submit detailed proposals or bids, often encompassing not only pricing but also approaches and methodologies. What term completes this phrase? | Proposal | Price | Quote | Information | 3 | 3d | 3 | a | m3d3a-06
24 | 288 | You would use a(n) ____-or-buy analysis to decide whether to purchase or lease items for a particular project. | retain | lease | acquire | make | 2 | 3d | 3 | b | m3d3b-01
24 | 289 | What is the focus of a make-or-buy analysis? | Comparing in-house expertise to external options | Analyzing competitors’ offerings | Evaluating procurement strategies | Assessing customer satisfaction | 1 | 3d | 3 | b | m3d3b-02
24 | 290 | In a construction project, a make-or-buy decision could involve: | Choosing between different marketing strategies | Deciding on a building’s color scheme | Determining whether to use in-house workers or subcontract | Selecting the project manager’s office location | 3 | 3d | 3 | b | m3d3b-03
24 | 291 | In a lease-or-buy analysis, what should be considered before deciding? | Personal preferences | Historic weather data | Employee morale | Availability of expertise | 4 | 3d | 3 | b | m3d3b-04
24 | 292 | Which factor might favor the decision to lease equipment rather than buying it? | Short project duration | Higher long-term costs | Lower utilization rates | Need for customization | 1 | 3d | 3 | b | m3d3b-05
24 | 293 | Assume you can lease a machine you need for a project for $2000/day. To purchase the machine, the cost is $26,000 plus a daily operational cost of $300/day. How long will it take for the purchase cost to be the same as the lease? | 2 days | 153 days | 15 days | 29 days | 3 | 3d | 3 | b | m3d3b-06
24 | 294 | You are the project manager for an upcoming outdoor concert event. You are working on the procurement plan for the computer software program that will control the lighting and screen projections during the concert. You compare the cost of purchasing a software product to the cost of your company programmers writing a custom software program. You are engaged in which of the following? | Procurement planning | Using expert judgment | Creating the procurement management plan | Make-or-buy analysis | 4 | 3d | 3 | b | m3d3b-07
24 | 295 | What is the purpose of a supplier evaluation matrix in project procurement management? | To negotiate prices with potential suppliers | To select suppliers based on their popularity | To objectively assess and compare potential suppliers against predetermined criteria | To eliminate all potential suppliers except one | 3 | 3d | 3 | d | m3d3d-01
24 | 296 | In the procurement process, what factors are typically evaluated in a supplier evaluation matrix to determine the best supplier for a project? | Adherence to project deadlines and the size of the supplier's workforce. | Workforce morale and the supplier's corporate values and culture. | Proximity to the project site and alignment with current market trends. | Cost effectiveness, product or service quality, technological capabilities, record of past performance, and efficiency of management. | 4 | 3d | 3 | d | m3d3d-02
24 | 297 | How does the weighted scoring model help in supplier evaluation? | It allows for an objective comparison of potential suppliers based on predetermined criteria with different levels of importance. | It includes opportunities for working with new suppliers by randomly assigning scores to suppliers. | It ensures fairness by assigning equal importance to all criteria. | It prevents cost overrun by focusing solely on the supplier's cost factor. | 1 | 3d | 3 | d | m3d3d-03
24 | 298 | How are the weights assigned to criteria in a supplier evaluation matrix determined? | They are randomly assigned. | They are determined by the supplier. | They reflect the project's specific needs and priorities. | They are the same for all projects. | 3 | 3d | 3 | d | m3d3d-04
24 | 299 | How is the overall score for a supplier calculated in a supplier evaluation matrix? | By summing up the supplier's past performance | By averaging the scores of all criteria | By multiplying the supplier's score for each criterion by its weight and summing up the results | By comparing the supplier's cost to its quality | 3 | 3d | 3 | d | m3d3d-05
24 | 300 | Why is it important to consider both short-term and long-term costs when evaluating a supplier's offerings? | Short-term costs are always more important than long-term costs | Different projects have different cost preferences | Long-term costs are irrelevant in supplier evaluation | Short-term costs are more predictable than long-term costs | 2 | 3d | 3 | d | m3d3d-06
13 | 301 | In project management, the manage quality process is pivotal for ensuring that the project's deliverables meet the established standards. What is the core objective of this process? | To oversee and report on the project's progression against its performance benchmarks. | To maintain financial discipline by managing the project's costs within the allocated budget. | To operationalize the quality management plan by implementing the activities necessary for achieving quality objectives. | To construct a detailed timetable that outlines the project's phases and milestones. | 3 | 4a | 3 | 0 | m4a30-01
13 | 302 | Which process reflects the project’s overall quality status to stakeholders by utilizing data from the control quality process? | Plan Quality | Manage Quality | Quality Assurance | Control Quality | 2 | 4a | 3 | 0 | m4a30-02
13 | 303 | Quality assurance in project management involves __________. | Monitoring project schedule | Managing project resources | Analyzing project risks | Ensuring compliance with quality standards | 4 | 4a | 3 | 0 | m4a30-03
13 | 304 | Which of the following are a subset of the inputs for the manage quality process? | Project schedule, Risk register, Quality control measurements | Quality management plan, Risk report, Stakeholder register | Lessons learned register, Quality metrics, Organizational process assets | Cost baseline, Issue log, Quality assurance plan | 3 | 4a | 3 | 0 | m4a30-04
13 | 305 | Which tool or technique is used for data gathering in the manage quality process? | Checklists | Benchmarking | Flowcharts | Six Sigma | 1 | 4a | 3 | 0 | m4a30-05
13 | 306 | What does the Fishbone Diagram (Ishikawa or Cause and Effect Diagram) help identify? | Project milestones | Causes of problems | Resource allocation | Stakeholder communication | 2 | 4a | 3 | 0 | m4a30-06
13 | 307 | What do quality audits use to assess project activities, processes, and outputs? | Quality risks in the risk register | Quality suggestions from stakeholders | Predefined quality standards | Causes identified in the fishbone diagram | 3 | 4a | 3 | 0 | m4a30-07
13 | 308 | What is the purpose of detailed quality checklists in test and evaluation documents? | Outline project schedule | Guide evaluation | Define quality metrics | Identify project stakeholders | 2 | 4a | 3 | 0 | m4a30-08
13 | 309 | Which methodology aims to minimize defects and improve overall process performance through data-driven analysis? | Flowcharts | Six Sigma | Benchmarking | Quality Audits | 2 | 4a | 3 | 0 | m4a30-09
22 | 310 | What is the common outcome when planned risk responses are not implemented during the execution phase? | Increased project budget | Improved project schedule | Identified risks become actual issues | Enhanced stakeholder communication | 3 | 4a | 4 | 0 | m4a40-01
22 | 311 | Which of the following statements best describes the implementation of risk responses? | It involves creating risk registers. | It translates decisions made during risk management planning into action. | It is limited to the planning phase of the project. | It focuses on avoiding all project risks. | 2 | 4a | 4 | 0 | m4a40-02
22 | 312 | Which project management document helps in tracking and managing changes related to risk responses? | Risk register | Risk matrix | Risk map | Risk assessment form | 1 | 4a | 4 | 0 | m4a40-03
22 | 313 | What are some of the tools and techniques used in implementing risk responses? | Risk analysis and selection | Cost estimation techniques | Resource allocation methods | Expert judgment and influencing skills | 4 | 4a | 4 | 0 | m4a40-04
22 | 314 | When can risk responses be implemented in a project’s life cycle? | Only during the execution phase | Only during the planning phase | Only during the closing phase | Throughout the project life cycle | 4 | 4a | 4 | 0 | m4a40-05
25 | 315 | What is the primary objective of the conduct procurements process in project management? | Creating a project schedule | Obtaining seller responses and making agreements | Defining project scope | Developing a risk management plan | 2 | 4a | 5 | 0 | m4a50-01
25 | 316 | Who is responsible for providing procurement or bid documents such as RFP (Request for Proposal) to potential sellers? | Project sponsor | Project manager | Selling organization | Buying organization | 4 | 4a | 5 | 0 | m4a50-02
25 | 317 | What is a key tool and technique used during the conduct procurements process? | Project management information system | Risk analysis | Stakeholder analysis | Bidder conferences | 4 | 4a | 5 | 0 | m4a50-03
25 | 318 | What is a good reason for approaching a preferred supplier during the procurement process? | To increase competition | To explore different solutions and innovations | To leverage an existing relationship | To promote transparency | 3 | 4a | 5 | 0 | m4a50-04
25 | 319 | What is the purpose of advertising to many potential suppliers in the procurement process? | To promote exclusivity | To limit competition | To attract a wide range of suppliers | To establish a preferred supplier | 3 | 4a | 5 | 0 | m4a50-05
25 | 320 | Which organization provides standard form contracts for construction projects in Singapore? | The Real Estate Developers’ Association of Singapore (REDAS) | The Singapore Institute of Architects (SIA) | The Building and Construction Authority (BCA) | All the options | 4 | 4a | 5 | 0 | m4a50-06
25 | 321 | What is the purpose of standard form contracts in construction projects? | To create complexity in contracts | To discourage competition | To establish fair and consistent contractual relationships | To eliminate negotiation | 3 | 4a | 5 | 0 | m4a50-07
3 | 322 | blank question 1 | a | b | c | d | 3
3 | 323 | blank question 2 | a | b | c | d | 3
3 | 324 | blank question 3 | a | b | c | d | 3
4 | 325 | blank question 4 | a | b | c | d | 3
4 | 326 | blank question 5 | a | b | c | d | 3
4 | 327 | blank question 6 | a | b | c | d | 3
5 | 328 | blank question 7 | a | b | c | d | 3
5 | 329 | blank question 8 | a | b | c | d | 3
5 | 330 | blank question 9 | a | b | c | d | 3
7 | 331 | blank question 10 | a | b | c | d | 3
7 | 332 | blank question 11 | a | b | c | d | 3
7 | 333 | blank question 12 | a | b | c | d | 3
9 | 334 | blank question 13 | a | b | c | d | 3
9 | 335 | blank question 14 | a | b | c | d | 3
9 | 336 | blank question 15 | a | b | c | d | 3
11 | 337 | blank question 16 | a | b | c | d | 3
11 | 338 | blank question 17 | a | b | c | d | 3
11 | 339 | blank question 18 | a | b | c | d | 3
14 | 340 | blank question 19 | a | b | c | d | 3
14 | 341 | blank question 20 | a | b | c | d | 3
14 | 342 | blank question 21 | a | b | c | d | 3
16 | 343 | blank question 22 | a | b | c | d | 3
16 | 344 | blank question 23 | a | b | c | d | 3
16 | 345 | blank question 24 | a | b | c | d | 3
17 | 346 | blank question 25 | a | b | c | d | 3
17 | 347 | blank question 26 | a | b | c | d | 3
17 | 348 | blank question 27 | a | b | c | d | 3
19 | 349 | blank question 28 | a | b | c | d | 3
19 | 350 | blank question 29 | a | b | c | d | 3
19 | 351 | blank question 30 | a | b | c | d | 3
20 | 352 | blank question 31 | a | b | c | d | 3
20 | 353 | blank question 32 | a | b | c | d | 3
20 | 354 | blank question 33 | a | b | c | d | 3
23 | 355 | blank question 34 | a | b | c | d | 3
23 | 356 | blank question 35 | a | b | c | d | 3
23 | 357 | blank question 36 | a | b | c | d | 3
26 | 358 | blank question 37 | a | b | c | d | 3
26 | 359 | blank question 38 | a | b | c | d | 3
26 | 360 | blank question 39 | a | b | c | d | 3
29 | 361 | blank question 40 | a | b | c | d | 3
29 | 362 | blank question 41 | a | b | c | d | 3
29 | 363 | blank question 42 | a | b | c | d | 3
30 | 364 | blank question 43 | a | b | c | d | 3
30 | 365 | blank question 44 | a | b | c | d | 3
30 | 366 | blank question 45 | a | b | c | d | 3

## Sheet1 (2)
cell_index | question_index | question_text | opt_1 | opt_2 | opt_3 | opt_4 | answer
0 | 1 | Projects are temporary endeavours to create a unique product, service, or result. Which one of the following does not relate to the concept of “temporary” in project management? | The project team (including permanent staff from different departments) | The market window status on which the project is capitalising | The project deliverable | The project manager (a permanent staff) | 3
0 | 2 | Which of the following is not a project? | Running a construction yard | Renovating a library | Upgrading the Wi-Fi network in a university | Running a sports event | 1
0 | 3 | Sam and Sarah are in a heated discussion over a new program in the organisation. They are trying to determine who will determine how and when to communicate with stakeholders in the projects within the program. Who manages programs? | Project coordinators | Project sponsors | Project managers | Program managers | 3
0 | 4 | Which statement accurately discusses how projects drive innovation, adapt to market changes, and manage product lifecycles? | Projects drive innovation by incorporating new construction technologies, adapting to market changes by adjusting project scopes, and managing product lifecycles by ensuring the longevity and sustainability of constructed structures. | Projects drive innovation by implementing traditional construction methods, adapting to market changes by maintaining a rigid project scope and managing product lifecycles by focusing on short-term project goals. | Projects drive innovation through stakeholder collaboration, adapting to market changes by sticking to predetermined project plans and managing product lifecycles through regular maintenance and updates. | Projects drive innovation by prioritising cost reduction, adapting to market changes by avoiding modifications to project plans, and managing product lifecycles by focusing on immediate project needs. | 1
0 | 5 | Nicolas is the project manager described as revolutionising the construction project management information system industry. After a few preliminary strategy sessions, he pulls together the core team and notes that they will be defining deliverables early in the development life cycle and progressively elaborating them as the project progresses. What development life cycle is Nicolas following on the project? | Predictive | Iterative | Incremental | Hybrid | 2
0 | 6 | Company A has a standard set of project management procedures, but they are not directly applicable to a new project that has a smaller but more complex scope. Which process should Company A use to ensure that the PM procedures are suitable for the new project? | Perform integrated change control | Develop project management plan | Tailoring | Process configuration | 3
1 | 7 | Which project management document can be utilised for a go/no-go decision in a project? | Project business case | Project charter | Project stakeholder plan | Project management plan | 1
1 | 8 | Before officially initiating a construction project, the project manager must go through pre-initiating processes. Based on the information provided, what activity is the most crucial during the pre-initiating processes for the construction project? | Choose the project manager | Identify the project sponsor | Hold a meeting to review project expectations | Evaluate the need for project division | 2
1 | 9 | All the following are true regarding the Initiating Process Group, except for which one? | The Initiating Process Group is responsible for developing the document that authorises the project. | The Initiating Process Group overlaps with Planning, Executing, Monitoring and Controlling Process Groups. | The Initiating Process Group is responsible for defining a new project or phase by obtaining authorisation to start the project or phase. | The Initiating Process Group has the least project management processes. | 4
1 | 10 | Which project management document gives the project manager the authority to apply organisational resources to project activities? | Project management plan | Resource management plan | Project charter | Resource requirements documentation | 3
27 | 11 | You are the project manager of a large power grid construction project for your company. This project will span across several ASEAN countries. There are key stakeholders in all countries represented. As part of your stakeholder analysis, you’d like to create a document that captures all the stakeholders’ contact information, assessment information, and classification in the project. What type of document are you creating? | Stakeholder directory | Stakeholder engagement plan | Stakeholder register | Stakeholder communications matrix | 3
27 | 12 | The project manager has just determined that three functional managers have a stake in the project. Where is the project manager likely to document this information? | Stakeholder analysis | Resource management plan | Stakeholder engagement plan | Stakeholder register | 4
1 | 13 | You are the project manager for a large construction project, and the kick-off meeting is approaching. The stakeholders include representatives from the overseas client, the construction team, foreign consultants, neighbouring resident representatives, and local regulatory authorities. Considering the importance of stakeholder engagement in the kick-off meeting, which option best aligns with the principles outlined for a successful kick-off meeting in a construction context? | Assigning a team member to take minutes during the meeting | Starting the meeting with a detailed review of the project schedule | Including a virtual component with audio and video for remote stakeholders | Concluding the meeting focusing on the potential risks and issues of the project | 3
2 | 14 | You are a project manager overseeing a large construction project, and you have encountered resistance from some team members who believe that their experience alone is sufficient to guarantee project success without extensive planning. How would you address this misconception and emphasise the importance of planning in ensuring project success? | Acknowledge their experience but stress the importance of planning; at the same time, avoid contradicting them to maintain harmony in the project. | Encourage them to focus on project execution rather than planning; use their strengths in the right processes. | Proceed with the project tasks based on their opinions, as experience often outweighs planning. | Convene a meeting with a diverse group of competent individuals (including members who don’t believe in planning) to openly discuss the importance of extensive planning and the way forward. | 4
2 | 15 | You are appointed as the project manager for a large-scale construction project. Facing resistance and conflicts among staff and stakeholders focused on their duties and key performance indicators. You recognise the need for effective project integration management. In this context, which document is most crucial for facilitating project integration and providing a clear roadmap for stakeholders to understand the project? | Change Management Plan | Business Case | Project Management Plan | Lessons Learned Document | 3
2 | 16 | You are a project manager overseeing the construction of a new office building. The project involves multiple stakeholders, complex timelines, and significant budget considerations. During the initiation phase, you recognise the need to develop a comprehensive plan to guide the project from start to finish. In this context, what should be your primary focus when developing the Project Management Plan? | Identifying potential risks and developing a risk management plan | Outlining the detailed schedule and milestones | Establishing the project budget and cost management plan | Defining the project scope and scope management plan | 4
6 | 17 | You are the project manager for a large residential building construction project. A recent construction site supervision law change will require monitoring personnel and equipment that can significantly increase project costs. What is the first thing you should do as a project manager? | Initiate integrated change control by creating a documented change request | Proceed as planned since the project may be exempted from the new change in the law | Consult with the project stakeholders | Stop all project work to prevent any possible legal implications | 1
6 | 18 | Your organisation uses a predictive approach to managing projects. You have recently started your project and are beginning a series of overview sessions with key users to determine requirements for a new enterprise resource software implementation. What process group are the activities you are performing in? | Initiating | Planning | Executing | Monitoring and controlling | 2
6 | 19 | You are the project manager of the Newton Construction Project. Your team for this project will include internal and external employees. Your project requires an electrician at month eight. The following statements are examples of what type of information? | Organisational interfaces | Staffing requirements | Contractor requirements | Resource constraints | 2
6 | 20 | You are the project manager for a project that will produce a Building Information Modelling (BIM) application that automatically identifies safety hazards during a design’s different life cycle stages. You are in the process of acquiring resources to staff the project and obtaining responses from bidders on work that is being outsourced. What process group are these activities associated with? | Planning | Executing | Monitoring and controlling | Closing | 2
6 | 21 | A project manager prepares to obtain the resources needed to perform the project's work. What project document is the project manager likely to reference as a guide to acquiring and managing the project resources? | Project management plan | Resource management plan | Staffing management plan | Resource requirements | 2
6 | 22 | A project team member has asked you what a scope statement is. Which of the following is a characteristic of a project scope statement? | Defines the scope baseline for the project | Defines the requirements for each project within the organisation | Defines the roles and responsibilities of each project team member | Defines the project deliverables, their characteristics, and user acceptance criteria | 4
6 | 23 | Sally and Joe are two project managers working in the corporate offices of a construction project management consultancy. They are discussing the WBS. Sally is confused and asks Joe to describe what the WBS contains. What is Joe likely to respond with? | The WBS includes a description of the project scope, major deliverables, assumptions, and constraints. | The WBS is a work package containing unique identifiers, which provide a structure for hierarchical summation of costs, schedules, and resource information. | The WBS document provides detailed deliverables, activity, and scheduling information about each component within the project scope statement. | The WBS is a decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables. | 4
8 | 24 | You have been assigned as the project manager for a construction project to build a new residential complex. As you plan for the project, one of your key tasks is to develop the Schedule Management Plan. Which components are critical to the Schedule Management Plan in the construction context? | Determining project stakeholders and communication strategies | Creating a detailed list of project activities and their sequence | Identifying potential risks and mitigation strategies | Outlining the project’s financial resources and budget allocation | 2
8 | 25 | If Activity A has an early start of 10, an early finish of 16, and a late start of 12, what is the total float of the activity? | 0 | 6 | 2 | 4 | 3
8 | 26 | You are the project manager of an underground tunnel design project. You recently created the project network diagram and want to identify the critical path. Which one of the following best describes the critical path? | It is always one path with no float. | It determines the earliest the project can be finished. | It has the most activities. | It has the most important project activities. | 2
10 | 27 | You are the project manager for a new construction technology implementation project. Management has requested that your estimates be as exact as possible. Which of the following methods of estimating will provide the most accurate estimate? | Top-down estimating | Top-down budgeting | Bottom-up estimating | Parametric estimating | 3
12 | 28 | You are the project manager for the ABC construction project. You will meet with your project team to discuss ensuring the project will be completed without any deviations from the requirements. Which of the following processes are you performing? | Quality Control | Plan Quality | Manage Quality | Conduct Procurements | 2
15 | 29 | You are the project manager for a large-scale construction project, and effective resource management is crucial for the successful completion of the project. During the planning phase, you recognise the need to develop the Project Resource Management Plan. In this context, which element is integral to the Project Resource Management Plan for effectively allocating and utilising resources? | Project schedule and milestone identification | Team charter defining roles and responsibilities | Identification of potential risks and mitigation strategies | Budget allocation and financial resource planning | 2
18 | 30 | You are the project manager for the JHG Project. Management has requested that you create a document detailing what information will be expected from stakeholders and to whom that information will be disseminated. Management is asking for which one of the following? | Roles and responsibilities matrix | Scope management plan | Communications management plan | Stakeholder register | 3
28 | 31 | As a project manager overseeing the construction of a new commercial building, you recognise the significance of stakeholder engagement for project success. You aim to develop a Stakeholder Engagement Management Plan during the planning phase. In this context, which element is crucial for effective stakeholder engagement? | Defining project milestones and deliverables related to key stakeholders | Identifying potential risks related to stakeholders and mitigation strategies | Establishing communication channels and frequency | Allocating financial resources and budget planning relevant to stakeholder engagement activities | 3
21 | 32 | A table of risks, their probabilities, impacts, and numbers representing the overall risk scores is called a __________. | Risk table | Probability-impact matrix | Quantitative matrix | Qualitative matrix | 2
24 | 33 | Your company is outsourcing a part of your project and preparing the procurement documents. Which of the following is a typical bidding document? | Request for information | Request for budget | Request for catalogue | Seller proposal | 1
3 | 34 | The integrated change control process is used to manage changes to the project in which process group? | From initiating through closing | Executing and Monitoring and controlling | Executing only | Monitoring and controlling only | 1
3 | 35 | All the following statements regarding the Manage Project Knowledge process are true, except for which one? | It addresses both explicit and tacit knowledge. | It generates the lessons learned register. | It is performed at the end of the Executing process group. | It often results in updates to the project management plan. | 3
13 | 36 | You are managing a precast component design and development project with limited resources. The QA department has discovered many defects in the precast components, and the project sponsor is very concerned about this. You want the maximum number of defects repaired with minimal effort and cost. Which quality-control tool will you use before you direct the project team's efforts to fix specific problems? | Control chart | Cause and effect diagram | Inspection | Scatter diagram | 2
22 | 37 | You are evaluating the probability and impact of a risk by assigning numbers, such as expected monetary value. This is an example of which of the following? | Monte Carlo simulation | Qualitative risk analysis | Quantitative risk analysis | Risk response planning | 3
25 | 38 | You are the project manager overseeing the construction of a new bridge, and you are about to enter the procurement phase. Considering the information on different approaches to selecting sellers, what is a key advantage of approaching several qualified suppliers in the procurement process? | It leverages a history of successful collaboration with a preferred supplier. | It promotes fairness, transparency, and the exploration of different solutions. | It saves time in the selection process and reduces risks. | It allows for open competition and attracts a wide range of suppliers. | 4
16 | 39 | You are the project manager overseeing the construction of a new high-rise building. As part of the project planning phase, you must ensure adequate resources are acquired to support the project work effectively. In this context, what is the primary objective of the Acquire Resources process in construction project management? | Procuring necessary personnel and facilities to support different project roles and responsibilities | Procuring necessary personnel and equipment to mitigate identified risks | Procuring necessary personnel, equipment, and materials to support the project work | Procuring equipment and personnel to support communication channels with project stakeholders | 3
16 | 40 | You are the project manager for a large-scale construction project involving the development of a commercial complex. As part of the project, you are focused on enhancing team performance and fostering positive team dynamics. In this context, what is the primary goal of the Develop Team process in construction project management? | Defining project roles and responsibilities | Improving competencies, team member interaction, and team performance | Identifying potential negative team dynamics and mitigation strategies | Establishing communication channels with project stakeholders | 2
16 | 41 | Rachel is a project sponsor developing a new innovative line of screen doors to attract budget-minded consumers. Most project managers cringe when assigned to a project sponsored by Rachel since she tends to hover over the details and be suspicious of every team member’s behaviour, causing a flurry of issues for the project manager to resolve. According to Douglas McGregor’s leadership theory, what type of manager is Rachel? | Theory Y | Theory Z | Theory X | Theory Y/Z | 3
19 | 42 | You are in the Monitor Communications process . Your organisation has taken on a large, complex, multiyear project. You are coming in as the new project manager (the old project manager left one day for lunch and never came back). After you have spent some time working on the project, you begin to realise that the project sponsor does not want to hear bad news. There is, unfortunately, some bad news related to the project, but you have a plan to get the project back on track. One of the other stakeholders on the project informed you that the sponsor had just told them that the project was proceeding as planned and was on time and within budget. In addition, you found that the stakeholders are not communicating and that since you started working on the project, there have been no regularly scheduled meetings with stakeholders. Based on the given scenario, all the following statements are true except which one? | Regular, timely status meetings will help prevent situations like this. Meetings, which include regularly scheduled status review meetings, are a tool and technique of this process. | You should conduct a thorough risk assessment to facilitate the planning for your status meeting so that communication risks can be mitigated. | You should facilitate the status meetings and provide honest, truthful information to the sponsor. | You need status meetings with different groups of people for a project as complex as this one. | 2
29 | 43 | Carina is the principal project manager of a specialist contractor that creates custom façades for heritage buildings. As part of her latest project, she struggles to rein in the team, who seem to be at each other’s throats. She knows everyone has good intentions, but they are not yet open and trusting with each other. What phase of the team development model is the team currently in? | Norming | Performing | Forming | Storming | 4
4 | 44 | You are the project manager for a large construction project, overseeing the development of a new residential complex. You monitor and control the work progress during the project to ensure it aligns with the project plan. In this context, what is the primary purpose of developing work performance reports in construction project management? | Defining project roles and responsibilities | Communicating project status and performance | Identifying potential risks and mitigation strategies | Allocating resources to project tasks | 2
11 | 45 | Given the following information, is the project schedule ahead of or behind what was planned for this period? EV = 95, PV = 85, AC = 100. | Ahead because the result of the variance formula is negative. | Behind because the result of the variance formula is negative. | Ahead because the result of the variance formula is positive. | Behind because the result of the variance formula is positive. | 3
4 | 46 | Several processes in the Monitoring and Controlling process group involve change requests. Which of the following is false? | Approved change requests are input to the Control Procurements and Control Quality processes | Approved change requests are an output of the Perform Integrated Change Control, and Monitor Risks processes | Approved change requests are input to the Direct and Manage Project Work | Control Scope process generates change requests that are inputs to the Perform Integrated Change Control process | 2
7 | 47 | You are the project manager for a construction project focused on building a state-of-the-art sports stadium. In this context, which of the following best describes how the Validate Scope process is utilised in construction project management? | Confirming potential risks and mitigation strategies related to the project scope | Documenting scope-related lessons learned for future projects | Formalising acceptance of completed project deliverables | Validating resources used in project tasks | 3
7 | 48 | David, one of your project team members, has been making changes to his work, which, as a result, changes the project scope. David’s changes are also known as what? | Scope change requests | Scope control defect | Scope creep | Improvised scope composition | 3
9 | 49 | During the construction of a residential building, the project manager notices a delay in delivering critical construction materials. This delay has the potential to impact the overall project schedule. What would be the most effective action for the project manager to take in this situation? | Proceed with the existing schedule and compensate for the delay in later phases. | Control the project schedule by engaging the supplier in discussing mitigation measures and adjust the schedule if necessary. | Inform the client about the delay and seek approval for a schedule extension. | Delegate the responsibility to the procurement team and ensure that they follow up with the supplier. | 2
11 | 50 | In constructing a large infrastructure project, the project manager realises that the costs exceed the planned budget due to unexpected increases in material prices. What is the most effective action for the project manager to control costs in this situation? | Use the project reserves to compensate for the increased material prices. | Implement cost-cutting measures to compensate for the increased material prices. | Review the cost baseline and adjust it to accommodate the increased material prices. | Seek additional funding from stakeholders to cover the cost overruns. | 3
14 | 51 | In a construction project, the project manager encounters delays in delivering critical construction materials from the main supplier. What is the most cost-effective procurement management strategy to address this issue? | Seek alternative suppliers and terminate the contract with the main supplier. | Negotiate with the main supplier for expedited delivery without any contractual changes. | Implement penalties on the main supplier for the delays in material delivery. | Review the procurement plan and adjust timelines to accommodate the delays. | 4
14 | 52 | In constructing a commercial complex, the project manager identifies a significant deviation in the insulation material used for the building. What is the most appropriate action to address this quality issue? | Delegate the responsibility of resolving the issue to the sub-contractor team and ask for periodic updates. | Document the deviation and inform the project stakeholders. | Continue with construction and implement additional insulation measures during the finishing phase. | Initiate a change request to replace the insulation material and involve relevant stakeholders. | 4
17 | 53 | In constructing a new office building, the project manager observes that a construction team is experiencing delays due to a shortage of skilled labour. What is the most appropriate action for the project manager to address this issue through the control resources process? | Hire additional workers and allocate them to the construction team to mitigate delays. | Shift tasks from the construction team to other teams with similar skills level. | Let the workers accumulate experience and skills by letting them continue with the current allocations. | Procure advanced automated equipment to replace the need for skilled labour. | 1
20 | 54 | You are the project manager for the JGI Project. You have 32 stakeholders on this project. How many communication channels do you have? | Depends on the number of project team members | 496 | 32 | 1 | 2
23 | 55 | The water sanitation project manager has determined that the risks of handling certain chemicals are too high. He has decided to allow someone else to complete this portion of the project. So, he has outsourced the handling and installation of the chemicals and filter equipment to an experienced contractor. This is an example of which of the following? | Avoidance | Adaptation | Mitigation | Transference | 4
26 | 56 | You are a project manager for an engineering company. Your company won the bid to add ramp-metering lights to several on-ramps along a stretch of highway at the city’s south end. You subcontracted a portion of the project to another company. The subcontractor’s work involves digging the holes and setting the lamp poles in concrete. You have discovered the subcontractor’s work is incorrect because the poles are not buried to the correct depth. You review the work and note gaps in the process and a lack of safety standards due to this error. Which of the following is true? | You are in the Manage Quality process, and have performed a quality audit, during which you identified a need for corrective action. | You are in the Validate Scope process and have performed a quality audit to ensure the correctness of work. | You are in the Control Procurements process and have completed a contract audit to ensure that the subcontractor’s performance meets the contract requirements. | You are in the Direct and Manage Project Work process and have completed a performance review of the contractor’s work. | 1
30 | 57 | You have just joined a project that has already been planned. You want to look at strategies to implement and actions to perform to facilitate stakeholders’ creative involvement in the project, such as making project decisions and project execution. Where will you look? | Stakeholders’ engagement assessment matrix | Mind mapping | The stakeholder engagement plan | Project stakeholder register | 3
5 | 58 | When closing a construction project, what is a key consideration to ensure the proper closure of a project and satisfaction of all stakeholders, especially the client? | Conduct a closing meeting and discuss the lessons learned. | Communicate with stakeholders regarding project challenges and delays. | Obtain formal acceptance from the client and ensure the completion of all deliverables. | Schedule a post-project review meeting with the project team. | 3
5 | 59 | What is a crucial step during the project closure phase to facilitate knowledge transfer and future improvement? | Archive project documents and records for future reference. | Conduct an internal team debrief to identify lessons learned. | Review all financial transactions and identify possible errors. | Inform the project team to evaluate their learning needs for the next project. | 2
5 | 60 | Which of the following is not an activity of the Close Project process? | Close all change requests | Ensure all processes are complete and closed | Transfer the project product to the customer | Ensure that all contracts are closed | 1
5 | 61 | Why is finalising the lessons learned register crucial for effective project management? | To satisfy contractual requirements | To identify areas of improvement for future projects | To create a historical archive of project challenges | To identify individual achievements and improve team members’ profiles | 2
5 | 62 | A functional manager says, “We will skip the closing processes. This project does not need formalities; it’s a total waste of time.” For which kind of projects is it appropriate to skip the closing processes? | Agile projects | Small and simple projects | Cancelled project | No projects | 4

## Leftover
cell_index | question_index | question_text | opt_1 | opt_2 | opt_3 | opt_4 | answer | mod | parent | sub | id
4 | 421 | What does monitoring and controlling involve? | Ensuring the project is ahead of schedule | Collecting, measuring, and assessing data and trends | Setting project performance objectives | Creating a project management plan | 2 | 5A | 2 | a | m5A-2a
4 | 422 | Which of the following are inputs to the Monitor and Control Project Work process? | Risk Register, Stakeholder Register, Quality Report, and Cost Estimates | Project Charter, Stakeholder Analysis, Scope Statement, and Lessons Learned | All components of the Project Management Plan, Assumption Log, Basis of Estimates, and Risk Report | Work Breakdown Structure, Network Diagram, Responsibility Assignment Matrix, and Issue Log | 3 | 5A | 2 | a | m5A-2a
4 | 425 | What is the typical frequency for progress reports? | Daily | Weekly, bi-weekly, or monthly | Yearly | No typical; the project manager decides | 2 | 5A | 2 | a | m5A-2a
4 | 426 | What should a project manager do if actual progress falls below a certain percentage of the planned progress? | Celebrate the progress achieved | Take no action | Trigger specific actions to address the situation | Increase the planned progress percentage | 3 | 5A | 2 | a | m5A-2a
4 | 427 | What is the significance of milestone monitoring in project management? | It helps in completing the project ahead of schedule. | It serves as a checkpoint for tracking progress. | It replaces the need for progress reports. | It is optional and not necessary for project success. | 2 | 5A | 2 | a | m5A-2a
4 | 428 | What information is typically described in the resource allocation section of a progress report? | Work completed and resources to be used in the next period | Capture the possible recruitment avenues for labour and suppliers | Detail the cost of different resources used | Highlight any resource constraints, surpluses, or changes in resource requirements | 4 | 5A | 2 | a | m5A-2a
4 | 429 | What is the purpose of forecast report? | Record past project status and progress based on past information and trends | Describe where the project stands at a specific point in time | Describe what the project team has accomplished during a certain period | None of the options | 4 | 5A | 2 | a | m5A-2a
11 | 431 | Which formula is used to calculate the Cost Variance (CV)? | CV = AC – EV | CV = PV – EV | CV = EV – PV | CV = EV – AC | 4 | 5A | 2 | b | m5A-2b
11 | 432 | Which formula is used to calculate the Cost Performance Index (CPI)? | CPI = EV / AC | CPI = AC / EV | CPI = EV / PV | CPI = PV / EV | 1 | 5A | 2 | b | m5A-2b
11 | 433 | Which formula is used to calculate the Estimate at Completion (EAC) if the current cost performance index (CPI) or percent complete (%C) is assumed to remain constant for the remaining portion of the project? | EAC = BAC / CPI | EAC = AC + (BAC − EV)/(CPI x SPI) | EAC = AC + BAC - EV | EAC = AC + Bottom-up ETC | 1 | 5A | 2 | b | m5A-2b
11 | 434 | What does a cumulative CPI below 1 indicate on a To-Complete Performance Index (TCPI) chart? | The project is ahead of schedule | The project is under budget | The project is over budget | The project is on track | 3 | 5A | 2 | b | m5A-2b
11 | 435 | What does a Cost Performance Index (CPI) of 0.833 indicate? | The project is performing better than expected in terms of cost | The project is performing worse than expected in terms of cost | The project is on budget | The project is on schedule | 2 | 5A | 2 | b | m5A-2b
11 | 436 | You are managing a construction project with a budget of $800,000. The project involves two construction teams working for six months, totaling 10,000 hours of labor. According to your project schedule, 38% of the work should be completed by now. However, you've noted that 40% of the work is complete, but 50% of the budget has already been spent. What does this indicate about your project's status? | The project is ahead of schedule and under budget. | The project is ahead of schedule but over budget. | The project is behind schedule but under budget. | The project is on schedule but over budget. | 2 | 5A | 2 | b | m5A-2b
11 | 437 | Nine months into a two-year infrastructure upgrading project with a $4,200,000 budget, you have spent $1,650,000. The project's Cost Performance Index (CPI) is 0.875. Based on this information, calculate the Estimate to Complete (ETC) for the project. Assume future work completes at planned efficiency rate. | 2550250 | 3150000 | 4406250 | 3550000 | 3 | 5A | 2 | b | m5A-2b
4 | 439 | What is the purpose of the Configuration Management Plan as an input to the Perform Integrated Change Control process? | To track configuration changes | To manage changes to project documents | To provide guidelines for handling configuration changes | To document lessons learned | 3 | 5A | 3 |  | m5A-3
4 | 440 | Which of the following is not a common change request in the construction industry? | Scope Changes | Schedule Changes | Quality Changes | Cost Changes | 3 | 5A | 3 |  | m5A-3
4 | 441 | Which of the following is not a common step in integrated change management? | Evaluation of the change | Approval process | Change likelihood assessment | Change communication and stakeholder engagement | 3 | 5A | 3 |  | m5A-3
4 | 442 | What is the term used to refer to the group of selected individuals responsible for reviewing and approving or rejecting change requests? | Change Control Board | Change Review Board | Change Approval Board | Change Management Board | 1 | 5A | 3 |  | m5A-3
4 | 444 | Which document captures the integrated change management process? | Configuration management plan | Risk management plan | Scope management plan | None of the options | 4 | 5A | 3 |  | m5A-3
7 | 445 | What is the primary purpose of the validate scope process in project management? | Validating the accuracy of project scope | Formalizing acceptance of completed project deliverables | Conducting inspections, reviews, and tests to validate project requirements | Creating formal sign-off forms to validate stakeholder satisfactions | 2 | 5A | 4 |  | m5A-4
7 | 447 | What tool or technique is commonly used in the validate scope process? | Meetings | Lessons Learned Register | Inspection | Requirements Traceability Matrix | 3 | 5A | 4 |  | m5A-4
7 | 448 | In the construction industry, what is a key reason for conducting the validate scope process? | Ensuring compliance with regulations and standards | Ensure cost is kept low and affordable for client | To update the Requirements Traceability Matrix | Ensure workers’ safety and health is well-managed | 1 | 5A | 4 |  | m5A-4
7 | 449 | Why is group decision-making important during customer inspection? | To identify errors in requirements documentation | To achieve successful communication | To reflect the consensus of the customer group | To facilitate regulatory compliance | 3 | 5A | 4 |  | m5A-4
7 | 450 | When deliverables are checked for correctness, what are the key things to check for? | Arising issues, customer satisfaction, net promoter score | Accuracy, free from errors, meets quality standards | Specificity, sensitivity, and accuracy | Meets quality, safety, and environmental standards | 2 | 5A | 4 |  | m5A-4
7 | 451 | When a customer expresses dissatisfaction with a project deliverable, what is the appropriate initial action for the project manager? | Immediately modify the deliverable | Refer to the original Statement of Work (SOW) or project requirements for clarification and guidance. | Dismiss the customer's concerns as subjective and continue with the project plan. | Pause all project activities and reconvene the project team for an emergency meeting. | 2 | 5A | 4 |  | m5A-4
7 | 452 | What is one of the primary purposes of the Control Scope process in project management? | Defining project objectives | Monitoring project progress | Managing changes to the scope baseline | Capturing lessons learned | 3 | 5A | 5 |  | m5A-5
7 | 454 | In the context of project management, how can ambiguously defined project scope potentially impact the project's execution and stakeholder perceptions? | It can inadvertently foster enhanced collaboration among stakeholders due to the need for frequent clarifications. | It might lead to an unexpected decrease in the risk of scope creep due to flexible boundaries. | It can result in varying interpretations of project objectives, thereby increasing the likelihood of scope creep. | It may contribute to an artificial improvement in perceived project feasibility and desirability. | 3 | 5A | 5 |  | m5A-5
7 | 455 | In project management, which of the following processes is works synergistically with the Control Scope process to maintain alignment between the project's evolving scope and its overarching plan? | Perform Integrated Change Control | Perform Quality Control | Monitor and Control Project Work | Validate Scope | 1 | 5A | 5 |  | m5A-5
7 | 456 | What factors should be considered when evaluating the impact of proposed changes? | Stakeholder satisfaction and risk | Budget, resources, and project objectives | Project complexity and available resources | Project timeline and scope | 2 | 5A | 5 |  | m5A-5
7 | 458 | What tools and techniques are used in the Control Scope process? | Work Breakdown Structure, Resource Leveling, Critical Path Method | Variance Analysis, Trend Analysis | Risk Assessment, Impact Analysis, Decision Tree Analysis | Benchmarking, Quality Metrics, Control Charts | 2 | 5A | 5 |  | m5A-5
7 | 459 | What risks are directly associated with scope creep? | Extended timelines, additional work, and lower quality | Increased project complexity, lower stakeholder satisfaction | Additional work, increased costs, and extended timelines | Lower quality, increased costs, and lower stakeholder satisfaction | 3 | 5A | 5 |  | m5A-5
7 | 460 | What is essential to prevent scope creep? | Quick response to additional scope | Proactive and disciplined approach | Ignoring power dynamics between clients and the project team | Flexible communications with stakeholders | 2 | 5A | 5 |  | m5A-5
9 | 462 | What is the purpose of the iteration burndown chart? | Monitoring resource utilization | Tracking progress and identifying risks in an iteration | Analyzing project costs | Evaluating stakeholder satisfaction | 2 | 5A | 6 |  | m5A-6
9 | 463 | In controlling contractors and suppliers' schedules, what is an effective way to monitor work progress? | Ensuring accuracy of work performance data | Monitoring milestone status | Evaluating project costs | Reviewing project risks | 2 | 5A | 6 |  | m5A-6
9 | 464 | Which process ensures that any schedule baseline amendments are carefully managed? | Perform Integrated Change Control | Control Schedule | Develop Schedule | Monitor and Control Project Work | 1 | 5A | 6 |  | m5A-6
9 | 465 | When should schedule status reviews and walkthroughs be conducted in controlling contractors' schedules? | At irregular intervals | After project completion | As needed based on contractor requests | Regularly and at milestone points | 4 | 5A | 6 |  | m5A-6
9 | 466 | From a schedule control point of view, what are the purposes of having scheduled walk-throughs? | Ensuring quality of work | Ensure the reported progress are correct | Check that scope requirements are met | Check that the progress on site is ahead of schedule | 2 | 5A | 6 |  | m5A-6
11 | 467 | What is the purpose of an Earned Value Analysis in Control Cost process? | Provide a quantitative basis for updating the budget | Facilitate a quantitative risk assessment on project costs | Provide a basis for approving cost-related change requests | Provide the details needed for lessons learned related to cost management | 1 | 5A | 7 |  | m5A-7
11 | 469 | What is the purpose of tracking costs at different levels, such as by period, work breakdown structure (WBS) component, and activity? | Identifying cost variances | Updating the budget | Assessing project risks | Managing project schedules | 1 | 5A | 7 |  | m5A-7
11 | 470 | Which of the following is not a common project cost control action? | Influencing the factors that create changes to authorised cost baseline | Ensuring that all change requests are acted on in a timely manner | Monitoring work performance against funds expended | Informing the regulator of all approved changes and associated cost | 4 | 5A | 7 |  | m5A-7
11 | 471 | What is the Estimate at Completion (EAC) used for in project cost management? | Updating the project schedule | Assessing project risks | Forecasting the total project cost | Managing changes to the cost baseline | 3 | 5A | 7 |  | m5A-7
11 | 472 | What does the approved cost baseline represent? | The actual cost spent on the project | The authorized budget for the project | The initial budget for the project | The performance measurement baseline | 2 | 5A | 7 |  | m5A-7

## Baseline
cell_index | question_index | question_text | opt_1 | opt_2 | opt_3 | opt_4 | answer | mod | parent | sub | id
4 | 423 | Which tool or technique is used for analyzing project performance using cost and schedule data? | Stakeholder Analysis | Decision-Making | Earned Value Analysis | Alternatives Analysis | 3 | 5A | 2 | a | m5A-2a
11 | 430 | What is Earned Value Management (EVM)? | A project documentation technique | A project performance measurement technique | A project scheduling technique | A project risk management technique | 2 | 5A | 2 | b | m5A-2b
4 | 438 | When are change requests required? | Whenever there are changes | When required by the project management plan | After baselines or configuration management plans are established | After the project management plan is established | 3 | 5A | 3 |  | m5A-3
7 | 446 | What tool or technique is commonly used in the validate scope process? | Meetings | Lessons Learned Register | Inspection | Requirements Traceability Matrix | 3 | 5A | 4 |  | m5A-4
7 | 453 | Which of the following is crucial for effective scope control? | A detailed project management plan | A comprehensive configuration management plan | A well-defined scope | A well-defined project schedule | 3 | 5A | 5 |  | m5A-5
9 | 461 | Which of the following is an input to the Control Schedule process? | Risk register | Resource calendar | Stakeholder register | Work breakdown structure | 2 | 5A | 6 |  | m5A-6
11 | 468 | What is the primary purpose of continuously monitoring cost performance against the approved cost baseline? | Updating the project schedule | Identifying and analyzing cost variances | Forecasting project risks | Managing change requests | 2 | 5A | 7 |  | m5A-7
4 | 424 | What is the purpose of a progress report in project management? | To provide a summary of completed project work | To forecast future project status based on past information | To describe the project's objectives | To analyze project risks | 1 | 5A | 2 | a | m5A-2a
4 | 443 | Which stage of a construction project lifecycle cannot have any change requests? | Close out | Commissioning | Conception | None of the options | 4 | 5A | 3 |  | m5A-3
7 | 457 | What tools and techniques are used in the Control Scope process? | Work Breakdown Structure, Resource Leveling, Critical Path Method | Variance Analysis, Trend Analysis | Risk Assessment, Impact Analysis, Decision Tree Analysis | Benchmarking, Quality Metrics, Control Charts | 2 | 5A | 5 |  | m5A-5